## Knowledgebase LL BBAC
ID | Shop | Project Phase identified | Relevant Project Phase | Subject | Subject Category | Issue Description | Cause of issues | Lessons Learned | Benefits of using the lessons learned | Benefits Category | Responsible for optimisation | Carline/Engine/Battery
1 | Conveyor - Sorter | PT-Phase |  | V214 BIW sorter | Process | new sorter for related carline must be on automode before PT1 is runnunig. All required functions has to be considered from PC-LOG, Conveyor, …. The requirement has to be written down in the IT system (User Story) for the evaluation from COC department.IT requirements should be defined with design approval milestone from conveyor | transparent requirement from each department for the IT functions. | Business unit and IT department must define/align the required IT functions in a early plannig phase (approx. PT1 - 12 month). Budegt should be clarified , who take care for which function (analog IT catalogue) | enough time and budget to realize the required functions | Costs |  | V214
2 | Pilot Plant | B-Phase |  | Special tool | Timeline | The special tool for asesmbly can't be delivered to station on time. |  |  |  | Timeline | PP | V214
3 | Pilot Plant | B-Phase |  | Parts availability | Part | Parts can't be delivered to station completely on time. |  |  |  | Timeline | Logistics Planning | V214
4 | Pilot Plant | B-Phase |  | TV | Timeline | TV car start too early, process is not ready |  | V214 make the first PT as the TV car, in this period, the fixture still in commission. There is no maturity for the quality. | Make the right car as TV in the right time, it can help problem solving, not just done for doing. | Process Maturity |  | V214
5 | Pilot Plant | B-Phase |  | SLT | Timeline | SLT delivery delay |  | SLT delivery delay, losing lots of time for commission, and using temperary solution making a lot of quality issues. | SLT arriving on time can save time and no quality issue. | Timeline |  | V214
6 | Pilot Plant | B-Phase |  | Worker card | Process | V214 Z3 worker card not prepared for BF-phase |  | V214 Z3 worker card not prepared for BF-phase at the right time and kick-ups are wrong. | Z3 assemble process can be verified more earlier and good for the maturity improvement. | Product Maturity |  | V214
7 | Pilot Plant | B-Phase |  | BiW Measurement | Timeline | BiW measurement start too late, measurement date in program is not correct | Program was delived late than expectation , and nobody check the correctness of the program. | Prepone the milestone of program delivery, check the correctness of program in advance before delivery. | Can start dimension optimization earlier with correct report, helpful for quaity rump up | Product Maturity | QM | V214
8 | Pilot Plant | B-Phase |  | Euipment sharing | Process | Cost waste of special equipment only use once for certain car model in B-phase . | Some special technic or body sharp reason, we may need special equipment or tools only for once use, it kind of waste to buy the new by Pilot Plant | Align with PP or maintennance early, first consider sharing the equipment or tools from maitenance, after B-phase then return to maitennance as spare parts | First can verify the quality of equipment and paramater setting, share the experience. Second, saving money on double purchasing | Costs | Pilot Plant | V214
9 | Pilot Plant | B-Phase |  | Prouction Plan of crach car | Timeline | Crash Car start too early to guanrantee the joining quality | Can not get DT report before build up crash car, can't guanrantee the joining quality | In order to ensure the joining quality of Crash Car, all DT reports and optimize time is needed. But the build up plan cannot be changed, after several times discussion. The Project Management should plan it resonable. | Have better joining quality of crash car | Product Maturity | PM | V214
10 | Pilot Plant | B-Phase |  | Confidential issue in transportation | Organization | Responsibility unclear for covering the car body during transportation to Paint shop or CMM. | No department want to take the responsibility | Must have a clear R&R definationbefore B-phase start | Prevent new model information from leaking | Process Maturity | Paint Shop PP/Logistics Planning/Pilot Plant | V214
11 | Pilot Plant | B-Phase |  | EC implementation | Timeline | EC comes too late to implement in a shot time | RDC released the EC or AWB too late, which can not be implemented in short time with a normal process to modify the fixture | RDC should released the EC earlier or postpone the milestone of implementation Single case need to esclate to E3 above for a special process | Good preparation for EC implementation, avoid complice issue of fixture and equipemnt modification process . | Process Maturity | RDC | V214
12 | Bodyshop PP | B-Phase |  | SLT batches provide in good quality | Process | Commissioing considering cycle time - As the YBO test only ten part, the issue with SLT change and sensor is not revealled in early phase. And during PT1 performance test, the issue influence the cycle time. | Internal commisioning is not enough. | Same topic as "SLT batches in poor quality", LOG should encore the delivery of functional SLTs in order to guarantee a smooth PT1. Additional income process check should be done @BBAC as mentioned already in the lessons learned. | Guarantee a smooth PT1 | Process Maturity | Logistic packaging | V214
13 | Bodyshop PP | B-Phase |  | DT Capacity mismatch | Process | QM DT don't have enough capacity to finish enough loops of DT which project requested | DT room space and manpower limitation | QM should have proper assessment before B-phase in order to match project DT loops requirement. If current space and manpower not enough, instead of letting project coordinate during B-phase to get support from other place, DT should consider of increase capacity internally | Guarantee a smooth quality ramp up in B-phase after YBO | Process Maturity | QM | V214
14 | Bodyshop PP | B-Phase |  | TBP amount | Part | Before handing over the TBP amount to logistic, BS should have internal detail planning in order to have enough commissining parts during the ramp up phase | No early phase detail parts usage planning | Plan parts usage in early phase and hand over correct and realiable parts amount | No complicated commissioning parts adding process with logistic or press shop | Process Maturity | Body Shop PP | V214
15 | Bodyshop PP | B-Phase |  | Build up program | Process | With V254 experience, Bodyshop build up program tracking always can't fullfill all stake holders requirement and have many inefficient discussions | Not aligned build up program template and tracking process | With good MFA2 experience, it is better that one colleague from production control the build up program or at least run together with BS PP since production is the one who direct produce the official cars in each phase and do the joining quality control | Smoother cooperation and communication | Process Maturity | Body Shop Production/Body Shop PP | V214
16 | Paint Shop PP | B-Phase |  | Late and less feedback for B-Phase | Process | Late and less feedback from Pilot plant AS much more complain from AS homeline from CC | no enough feedback | Pilot Plant AS record the BIP issues and set up regular meeting to ensure the transparancy |  | Process Maturity | Paint Shop PP/Pilot plant | V214
17 | Paint Shop PP | B-Phase |  | PVC | Product | BIW big gap and body deviation can’t control very well during B-phase | BIW quality | BIW quality should follow BIW CAD data to build and make sure dimension should be in tolerance |  | Product Maturity |  | V214
18 | Paint Shop PP | B-Phase |  | PVC | Product | BIW Quality for PVC bubbles and Leackage | Body glue and quality | Production check the bodies and give feedback to BS in order to reach a good quality as earlier as possible |  | Product Maturity |  | V214
19 | Paint Shop PP | B-Phase |  | AFA | Product | Masking concept/scope and leakage gaps not fixed and need design change | product changes during B-phase | working close with RD and align in early phase |  | Product Maturity |  | V214
20 | Paint Shop PP | B-Phase |  | Flap Jigs | Process | The jigs use the same material as fule flap according RD requirement, but the jig can't use after go though the oven, | not same material as leadplant | currently V254 in discuss with RD and MP, need change the jigs material ASAP |  | Process Maturity |  | V214
21 | QM | B-Phase |  | Lead plant cannot provide DCF standard with a fix timeline | Audit | DCF audit is a part of audit content in B-Phase and PT phase. The standard is available and can be input from lead plant since PT phase. But time is usually not solid fix. | DCF standard is coming from lead plant. The standard making needs also input from R&D and needs data verification, the ready time can varry with different situation. | 1. Regular check with lead plant and ask lead plant to offer a solid timeline 2. Make back-up solution for standard missing, like use draft version and use comparable previous project standard. 3. make the situation transparency with pilot plant, QM, AK etc. | 1. Full transparency between lead plant and BBAC regarding to DCF standard timeline 2. Back-up solution prepared | Process Maturity | QM/QM BBAC/Pilot Plant/BBAC TPA | V214
22 | Assembly PP | B-Phase |  | Shopping carts | Process | 254: SC lessons learned from 254 not available yet (more information after PT1). V206 SC delivererd too late. | 254: PRs got blocked by Controlling R&R for V206 not clear | 254: SC need to be ordered in the very early phase (V254: 2 months before CC) to avoid delays by Controlling and others --> V214: Start ordering after IPV process in June, if possible. | Ensure delivery of SC on time (PT1) | Timeline | Assembly PP | V214
23 | Assembly PP | B-Phase |  | Product and process reliability | Process | 254: IPV release and CC in parallel, therefore delay of PFMEA (catch-up still possible) | IPV release and CC in parallel | 214 CC 1-2 months after IPV release --> OK | Avoidance of PFMEA delay | Timeline | NTP/SP | V214
24 | Assembly PP | B-Phase |  | CN specific special tools/Jigs | Timeline | CN specific special tools/Jigs information in BOZ database not avaiable on time - therefore tool ordering in China not possible and late delivery for B-Phase | CN specific special tools/Jigs information in BOZ database not avaiable on time | Close tracking of Planner in CN and GER to ensure readiness for B-Phase. Order all special tools/jigs early enough to reach B-Phase test. 18 weeks before LOT1 --> V214 implemented. | Special tools ready for LOT1 (delayed due to Controlling etc) | Timeline | Assembly PP | V214
25 | Assembly PP | B-Phase |  | V254 Project | Organization | Lack of PGL on site & English skills | Project team member left during planning phase, FERASIS, COVID situation did not allow travel to China, Local PGL Equipment not experienced to cover the topics. | Mandatory at least per group area ONE ON-SITE PGL during V254 project AGG area was handover 2x and afterwards splited into 3 pieces, but only 1 ON-SITE responsible person (others were in Germany/Indian). | Avoiding misscomunication, missunderstanding and improve the feeling of one planning team. | Process Maturity | Assembly PP | V214
26 | Assembly PP | B-Phase |  | V254 Project | Organization | Lack of cummunication between TPL Assembly/SPS Lack of Project Management structure and TPL Porcess being missused as "Post Officer" | Logistic and Process are running independent in order to reach their needs. Lack of project management structure. Current line function is running well, but project functions still a long journey to improve. During ramp-up series planners are in charge of process implementation (TPL Process/PGL Process are not responsible). | establishing the mandatory project meetings and even using them for better and stronger (project-)communication including the BBAC/Series colleagues to avoid misunderstanding and working against eachother. (and missusing the TPL Process as Post officer). Regular project communication between TPL Assembly/SPS should be established ASAP. By the new organization structure in CHINA, TPL Process should focus after IPV process in change management (until PT2), product issues, closing open topics, action plans to achieve assembly KPIs, escalation topics, and strong support for the L5 etc. | Avoiding misscomunication, missunderstanding and improve the feeling of one planning team. | Process Maturity | Assembly PP | V214
27 | Assembly PP | PT-Phase |  | V254 Project | Organization | ONE Voice to the customer | Lack of TPL Assembly filter during ramp-up issues. Not clear R&R about PGL Equipment during ramp-up. Possible process issues should not be discussed during ET and CC. | Project openeing Workshop with every project member (group) to clarify and define ones more the project R&Rs through all the prject phases (as described many time , by now. | Avoiding misscomunication, missunderstanding and improve the feeling of one planning team. | Process Maturity | WPL / TPL Assy | V214
28 | Assembly Series Planning |  |  | Project work scope is not clear since very beginning | Organization | Project work scope is not clear since very beginning | Cycle1 & Cycle2 & Cycle3 preparation work during same time, but not well considered for Cycle2&Cycle3, caused Cycle2&Cycle3 late preparation and not good result now, such as: Trim 0 line, rear spoiler | Clear handover to be done between WPL PP & WPL RD in advance, so that CII & CIII scopes are defined and project management can commence. Same applies to considering process/equipment planning for all cycles upfront |  | Process Maturity | WPL (PP/RD) TPL Assembly Change Management L4 Process Planning | V214
29 | Assembly Series Planning |  |  | Project management responsibility is missing | Organization | Project management responsibility is missing | 1. CII&CIII budget planning is missing 2. Project responsibility handover from NTP WPL to RD WPL is not clear 3. Decision made at the top not transfeered to the working level in time and properly. 4. Decision making delay | clear RR of the project organition at each phase |  | Process Maturity | WPL (PP/RD) | V214
30 | Assembly Series Planning | B-Phase |  | Special Tools Concept, requirement always unclear and the timeline late | Process | Special Tools Concept, requirement always unclear and the timeline late | Don't know how to use, don't know where should use, don't know need calibrate or not, don't know if calibration tools should be considered. | Special tools engineers should know about the tools and has knowledge about the special tools. Availability of all special tolls/phase to be identified, tracked & delivered |  | Process Maturity | Assembly PP | V214
31 | Press Shop PP | B-Phase |  | Material Age | Part | Aluminum Material Age according DBL 4952 was fullfilled for the pressparts. But was too old according to the requirement in Bodyshop. | DBL | Needs to be discussed in future projects in the early phase to find a solution. Needs to be considered in the definition of the part supply programm dates. | BS process improvement | Process Maturity | WPL/Body Shop PP/Press Shop PP/Logistics Planning | V214
32 | Press Shop PP | B-Phase |  | Clamping Sequence | Process | Long discussion about the clamping sequence in the V214. | New BS Requirement | Based on the V214 expirience on measuring both clamping sequences make a decsision together with the lead plant which way to follow in the future. |  | Process Maturity | QM CMM/QM Parts/Bodyshop PP/Press Shop PP | V214
33 | Press Shop PP | B-Phase |  | Part Delivery Amount | Part | Part Delivery amount was increased several times for the B- and P-Phase. Issue because of material availibility and age. | Changed part demands in BS | Earlier freezing of the part supply demand amount. | Cost Saving | Costs | Body Shop PP | V214
34 | Press Shop PP | B-Phase |  | Feasibility Study | Process | Currently the feasibility simulation by BM is based on the QM requirements from the Lead Plant. This leads to surface issues in the parts that can be accepted in the lead plant, but not accepted by the BBAC Q-Departments. (e.g. Skidlines for inner parts) | Simulation Evaluation Criteria BBAC Quality Standard | BM need to do the feasibility evaluation based on BBAC quality requirements in the evaluation phase. | Release reachable on BBAC Quality requests | Process Maturity | BM/PP/KT/QM BBAC/WPL/Press Shop PP | V214
35 | Press Shop PP | B-Phase |  | Low Part Feasibility of part data | Part | High amount of ECR's for the Rear Door Inner and late EC's because of a packaging issue caused a delay for the part delivery (covered by reduction of logistic time) and part optimization. | Low part maturity status of the product data | If the timeline is shortened such late EC's can't be implemented or lead to a delay of the part delivery. |  | Product Maturity | RD | V214
36 | RLM | B-Phase |  | phosphate sludge | Equipment | Phosphate sludge remove capacity not enough with higher Alu ratio | high ratio Al | modify equipment/employ new phosphate technology |  | Process Maturity | PP & supplier/Paint Shop PP | V214
37 | Paint Shop PP | B-Phase |  | hemming glue material | Product | PVC crack after touch with hemming glue | material incompatibility | modify material |  | Product Maturity | PP & supplier | V214
38 | RLM | B-Phase |  | wax nozzle | Timeline | wax nozzle arrived at BEIJING too late after EC | long time EC period | order the nozzles ASAP |  | Timeline | PP | V214
39 | Paint Shop PP | B-Phase |  | jigs | Equipment | jigs installation fault |  | try jigs ASAP |  | Timeline | PP | V214
40 | RLM | B-Phase |  | MDSfuture Impact | Organization | General topic: each department/function should evaluate its own changes/risks and clearly track the issue solving. | MDSfuture impact, shorter time of preparation | new topic | clear guidance to deal with MDSfuture challenges | Timeline | WPL | V214
41 | QM CMM | B-Phase |  | 3D data in Smaragd | Timeline | 3D data of X294 release too late in Smaragd, affecting programming and fixture design. | BBAC RD or DGRC release 3D data too late in Smaragd | 3D data is available in Smaragd in E phase | More time to finish and update CMM program and reports | Timeline | BBAC IT | V214
42 | QM CMM | B-Phase |  | Low 3D data authority in Smaragd | Organization | CMM programming and CMM program update need to open the Product and Snapshot permissions of V254&X254 in each phase in Smaragd. CMM engineer does not have authority, therefore cannot check lead plant 3D data and need to biuld up V254 3D data part by part with low effiency. Hopes to open the same authority as RD engineer | The CMM engineer does not have the authority to check Product and Snapshot in Smaragd | Permit same authority as RD engineer in Smaragd | CMM programming and update can be completed with high efficiency and quality | Product Maturity | BBAC IT | V214
43 | QM Analysis | B-Phase |  | QM Shaker audit | Audit | Too much vehicle interior pressing noise issues found in B-phase | - Interiors pressing noises, inculding seats, IP, center console and door panels etc. - Supplier did not control the pressing noise well before deliver the parts the BBAC | - The interior pressing noises should be controlled by supplier in the earlier phases, should not be found during the vehicle shaker test, it’s too late - Advance interior noise detection during the Lot phase (RD/QM to audit to initiate the PSP) | To avoid this kind of static noise occuring in the vehicles and to save manpower and material resources. | Process Maturity | RD/C | V214
44 | QM | PT-Phase |  | QM Shower audit | Audit | Sunroof/windshield glue application adjustment process need to be updated. | Shower test is not involved in glue application adjustment. Leakage test not done. | Process need to be double checked. Relevant department need to be involved (QMS, Shower). Process release must be done. | To avoid this kind of water leakage occuring to save manpower and material resources. | Process Maturity | PP | V214
45 | QM | B-Phase |  | QM Shower audit | Audit | V206H/V254 Drain pipe of charging port water leakage | Drain caliber is small as design issue. | Product Engineering should update EC timely according Daimler change. | To avoid this kind of water leakage occuring. | Product Maturity | RD/C | V214
46 | Press Shop PP | B-Phase |  | MO-Testat | Product | First time in V214 involvement from BBAC in the "_"-release MO-Testat and early communication within BBAC (QM, Voca, AK, BS,..) about issues caused by the part geormetry that can not be fixed. | Process Improvement | Contiune and deepen this process | Improved Ramp-Up and cost saving | Costs | PP/KT/PP Stamping | V214
47 | Bodyshop PP | B-Phase |  | Ensure Stud Location | Product | Stud position can't be verified until assembly parts are mounted | CMM can not measue some stud positons | Do a early tryout and send the home line BIW to pilot plant for assembly to verify all stud positions | Product Maturity | Product Maturity |  | V254
48 | Bodyshop PP | B-Phase |  | QL3 checking standard | Process | Checking method standard changed | Checking standard of a joining technology changed | Double check the checking method compare with the series models | Process Maturity | Product Maturity |  | V254
49 | Bodyshop PP | B-Phase |  | Surface Assesment BIW | Process | Surface issues caused by the manufacturing process need to be followed up | There is no Q Loop during B Phase inplemented for the reworkers to judge and adress the surface issues | Critical surface problem assessment & issue tracking bodyshop internal required | Product & Process Maturity | Product Maturity |  | V254
50 | Bodyshop PP | B-Phase |  | Press Part Maturity | Part | Not all press parts in tolerance | Not all delivered parts are in tolerance | Earlier part optimization required and faster reaction on customer feedback | Product Maturity | Product Maturity |  | V254
51 | Bodyshop PP | B-Phase |  | Joining Tech Maturity | Process | Destructive Test results not in target | Destructive test results are not in target | 1.Digital check of the joining situation in the RD data and adjustment of the data if necessary 2.First focus on dimension adjustment and part fitting and after that glue optimization 3.Early comparison of the DT results between the plants 4.Hybrid optimization approach; close cooperation between dimension team and joining / glue process team 5.Earlier destrcutive test loops and early definition for long term measures for joining NOKs required 6.Expert round required between Production, PP; QM & RD to get the same understanding for each joining situation | Product Maturity | Product Maturity |  | V254
52 | Bodyshop PP | B-Phase |  | EC Management | Organization | Information about EC changes not transparent | The information when which engineering change will be implemented is not clear onsite | Transparent communication about upcoming engineering changes | Product Maturity | Product Maturity |  | V254
53 | Bodyshop PP | B-Phase |  | Joining Tech DT | Process | Provide all the information of Destructive Test for joining element, not only for defects | Optimize the joining elements which is colsed to the tolerance limit | Do a early evaluation of quality commissioning | Product Maturity | Product Maturity |  | V254
54 | Bodyshop PP | B-Phase |  | clear organization& responsibility chart for the project | Organization | the project organization chart for the project is not clear enough to gudie that each member's resposibility and working content | when some issue happens no one knows which one shoule take care of this topic and from where the help can be acquired | make a clear declare for the working content distribution for each member of the project organization before the rampup phase starts | Process Maturity | Process Maturity |  | V254
55 | Bodyshop PP | B-Phase |  | reachbility of the cells | Process | it is too hard for the operator and CT to check the process and equipment in some cell and to do TPM | the space of the line is too limited that the design of the line pay less attetion to how to maintain the line | the reachability of the equipment must be taken into consideration | Product & Process Maturity | Process Maturity |  | V254
56 | Bodyshop PP | B-Phase |  | Process card | Process | The font size of process card exported from RDS is too small | Not convenient to check the process card | more convenient to check the process card | Documentation | Process Maturity |  | V254
57 | Bodyshop PP | B-Phase |  | Separation location gripper for LT | Process | For flexable prodution line especially NC locator station, one location gripper used for many types, when adjust one type location smoothly , but for the other one not good. | NC locator position for different types will be adjusted, which may make big difference with nominal. | One LT gripper for each type separately. | Product Maturity | Product Maturity |  | V254
58 | Bodyshop PP | B-Phase |  | In-line measurement | Process | IQ-VIS connection with VMT not 100% done before PT1 | IQ-VIS and VMT connection points not clear | IQ-VIS connection with VMT should be 100% done before PT1 | Product Maturity | Product Maturity |  | V254
59 | Bodyshop PP | B-Phase |  | Hinge turn table design | Product | X/Y direction not adjustable on hinge turn table, hinge position deviation big influece on door stability | Shims are not in design | X/Y/Z direction should be adjustable on hinge turn table | Product Maturity | Product Maturity |  | V254
60 | Bodyshop PP | B-Phase |  | Bestfit sensor | Process | Bestfit sensor number not match between label and Bestfit software | Wrong matching between VMT and Mechanical | Bestfit sensor label should be check before VMT commissioning | Product Maturity | Product Maturity |  | V254
61 | Bodyshop PP | B-Phase |  | Door zero position in Bestfit Line | Product | No separate design for door zero position in Bestfit Line | Two car type have difference on zero position | Bestfit measurement not stable due to wrong zero position | Product Maturity | Product Maturity |  | V254
62 | Bodyshop PP | B-Phase |  | Door hinges | Product | Door hinges in Bestfit Line not same angle in same batch | Door hinges not same angle in same batch when arrived | Influence on hinge stability and adjustment in GEO Station. Need same angle. | Product Maturity | Product Maturity |  | V254
63 | Bodyshop PP | B-Phase |  | Bestfit offset function | Process | Bestfit offset function not 100% work after VMT commissioning is done | Bestfit offset function not tested after VMT commissioning is done | Bestfit offset function need to be tested during VMT commissioning | Product Maturity | Product Maturity |  | V254
64 | Bodyshop PP | B-Phase |  | Pallet report | Process | pallet measurement report shouldn't follow roller bed force situation. Need optimize all pallet onsite. | pallet measurement fixture design did not consider onsite situation | Pallet measurement fixture design should add onsite roller bed force. | Product Maturity | Product Maturity |  | V254
65 | Bodyshop PP | B-Phase |  | studs in-line measurement | Process | the studs position can't be verify 100% by in-line measurement systerm | Didn't plan the fuction to inline systerm. | Implement this fuction to inline systerm | Product Maturity | Product Maturity |  | V254
66 | Bodyshop PP | B-Phase |  | STFP systerm | Process | the measurment and caculation in two robot , result is not stable. | Robot accrucy and temperature is different. | Combine robot or robot warm up before work. Ensure robot in same satuation. | Product Maturity | Product Maturity |  | V254
67 | Bodyshop PP | B-Phase |  | 2.1 tapping | Product | the rear wheel house area big gap after tapping. | The SWI wheel house area can't be fixed. | Add additional tapping in SWI | Product Maturity | Product Maturity |  | V254
68 | Bodyshop PP | B-Phase |  | 2.2 framer | Product | the sidewall wheel house area outboard too much | The SFK point only control small area. | Add big support to control alignment point | Product Maturity | Product Maturity |  | V254
69 | Bodyshop PP | B-Phase |  | side window bottom strength | Product | the sidewall sidewindow bottom is soft. Risk is surface issue | Without reinforcement part | Add the reinforcement part in the SWI. | Product Maturity | Product Maturity |  | V254
70 | Bodyshop PP | B-Phase |  | WHP | Process | it influence Z a little when adjust the punch equipment Y direction. | The equipment doesn't horizontal | Design the equipment horizontal | Equipment Maturity | Process Maturity |  | V254
71 | Bodyshop PP | B-Phase |  | fixture measurement label hole | Product | cover the hole is not standard, the plastic is easily broken. | The hole cover standard is not clearly in ECM | Update the ECM standard. Cover the hole by the rectangle steel. | Product Maturity | Product Maturity |  | V254
72 | Bodyshop PP | B-Phase |  | Hinge turn table design | Equipment | X/Y direction not adjustable on hinge turn table, hinge position deviation big influece on door stability | Shims are not in design | X/Y/Z direction should be adjustable on hinge turn table | Product Maturity | Product Maturity |  | V254
73 | Bodyshop PP | B-Phase |  | Bestfit sensor | Process | Bestfit sensor number not match between label and Bestfit software | Wrong matching between VMT and Mechanical | Bestfit sensor label should be check before VMT commissioning | Product Maturity | Product Maturity |  | V254
74 | Bodyshop PP | B-Phase |  | SLT | Process | Verification of dimensional consistency and stability | SLT , Robot process ,parts match not well | Before LOT4 phase it should be finished matching test for all SLTs. | Process Maturity | Process Maturity |  | V254
75 | Bodyshop PP | PT-Phase |  | Deviation release process | Process | No clear release process for BIW ZB diemension deviation , which have no influence to finished car quality | Press part deviation or RD/AK input leading to ZB deviation, TAMS process only for after SOP, before SOP no process. | Create release process before SOP, or prepone the TAMS process to PT1 code 18. | Process Maturity | Process Maturity |  | V254
76 | Bodyshop PP | B-Phase |  | Press part dimension | Part | Fender press part poor dimension leading to ZB issue and finished car gap and transition issue | Press part supplier of fender can not ensure dinmension in tolerance, and not able for further optimization | Evaluate supplier capability and give risk analysis before B-phase | Product Maturity | Product Maturity |  | V254
77 | Bodyshop PP | B-Phase |  | Module exchange | Process | HOP part dimension is influenced by fixure module exchange, especially for hood downholder station | Fixture locating pin and bush design issue | change for more stable structure | Equipment Maturity | Process Maturity |  | V254
78 | Bodyshop PP | B-Phase |  | gripper fixture clamp | Process | rear door glue spring back | rear door gripper clamp squeeze out the glue | do not set clamps on the glue trail , other wise the glue may spring back. | Product Maturity | Product Maturity |  | V254
79 | Bodyshop PP | B-Phase |  | GHI pre curing | Process | lift door 2K glue spring back caused by the spot welding process | the 2k glue is not cured while spot welding, so the fixture and weld gun squeeze the part, and glue spring back | set the GHI process ahead of spot welding. | Product Maturity | Product Maturity |  | V254
80 | RLM | PT-Phase |  | GFP Audits | Audit | GFP audits not a strong supporting Q-loop in the launch, to support in issue verifcation/VoCA score forecast. Scores not reguarly reported in DRM/WRM, tracking of GFP topic not clear |  |  | GFP Q-loop should be a quciker sensor than VoCA, supporting in quick feedback/PSP | Process Maturity |  | V206
81 | RLM | PT-Phase |  | Quick online IRA Check | Process |  |  | Quick IRA online check in Lot4/PT1a suppported the qucik PSP process, even if not offically confirmed by VoCA Quick online IRA check method to be made more formal | Support in qucik PSP process/forecast of Zeus issue closure rate | Process Maturity |  | V206
82 | RLM | PT-Phase |  | VoCA audit plan | Audit |  |  | Aligning the VoCA audit plan before the PT, supported by the Q-loops held tracked product maturity Amount of vehicles to be aduted to be revirwed. In PT1b 38 veh. Audited, limited benift towards the end of the audit result |  | Process Maturity |  | V206
83 | RLM | PT-Phase |  | BS Destructive test plan | Process | NOK seams found in the destructive test, after the build-up of customer cars |  | Review destucitve test plan before the start of a PT, determine if results can be ready just after "batch 1" of units in a PT have been built |  | Product Maturity |  | V206
84 | RLM | PT-Phase |  | Double usage of DT test cars | Process | Destrucutive test units used for incorrect purpose in BS, risk in delaying the Q-release | - Transparent of required handover dates/DT test vehicle not clear/late esclation of issues | Destructive test plan to be shared before each PT in the DRM. Owner coordinator of DT veh. To be clearly defined |  | Process Maturity |  | V206
85 | RLM | PT-Phase |  | High proportion of PS findings in VoCA from PT2/PT3 | Audit | PS topics not solved in earlier phases, issues not in strong focus |  | Track PS product quality from Lot 1 & try to solve issues as early as possible Have an onsite Quality check at each Lot/PT of a painted veh to highlight surface/PVC/AFA/LASD topics |  | Product Maturity |  | V206
86 | RLM | PT-Phase |  | Vehicle pipe & harness check/veh. Disassembly | Process |  |  | Conduct vehicle pipe & harness check in B-phase & PT phase |  | Process Maturity |  | V206
87 | RLM | PT-Phase |  | No peel test of glass in the B-phase | Process | One sided bonding found in PT phase, related to dirt/type of glue used. No cut out tests done in the B-phase |  | Perform glass/MFW cut-outs checks for glue adhesion in the B-phase/early PT phase |  | Product Maturity |  | V206
88 | RLM | PT-Phase |  | Supplier Performance Test Plan | Process |  |  | MP to define & set its supplier performance test plan. MP to track suppliers according to the original defined plan & report the status in WRM |  | Process Maturity |  | V206
89 | RLM | PT-Phase |  | Test of back-up tools | Process |  |  | Ensure all back-tools/strategies are test before SOP Plan to be defined & implemented |  | Process Maturity |  | V206
90 | RLM | PT-Phase |  | Extended shower test | Process | Water leaks found in the PT phase after vehicles went for extended shower tests, not done in the B-phase |  | Send vehicles for extended shower tests in the B-phase |  | Product Maturity |  | V206
91 | RLM | PT-Phase |  | Morning Car Review Meeting | Organization | Top issues shown on the car, sometime issues are to be followed up. Not always clear who takes the issue, address & give feedback |  | Define more clear formal process for the morning car review meeting | Support in FTC improvement, quick PSP | Process Maturity |  | V206
92 | RLM | PT-Phase |  | Ramp-up down planning | Timeline | Ramp-down/ramp-put plan not clear |  | Share in DRM/WRM ramp-down plan & activities |  | Process Maturity |  | V206
93 | RLM | PT-Phase |  | SOP part availability | Part | Started tracking SOP part availability after issue escalation for the seat belts |  | Define a clear milestone when SOP part availability must start to be tracked |  | Timeline |  | V206
94 | RLM | PT-Phase |  | Parking Plan until DC | Organization | Parking plan until DC unclear for many months Responsibility not clear , who should define the plan |  | Define parking plan until DC from the start of PT2 Responsibility to be clearly defined |  | Process Maturity |  | V206
95 | RLM | PT-Phase |  | AS In Vol vs FOK vol. | Process |  |  | Define a smother AS in Volume vs FOK volume, to make the volume ramp-up easier for production |  | Process Maturity |  | V206
96 | RLM | PT-Phase |  | High downtime on key equipment for all PT's | Equipment | Assembly new equipment commissioning/verification to be reviewed/methods need to bring key equipment fully operational earlier (RLM) |  |  |  | Process Maturity |  | V206
97 | Assembly PP | PT-Phase |  | Failer analysis | Process | No photo documentation possible for support group in Germany and India. | Restriction regarding new car model | Timely special release | faster problem solving | Process Maturity |  | V206
98 | Assembly PP | B-Phase |  | Approval milestone | Timeline | Virtual shipping approval not | Travel restrictions | 1. Travel as soon as possible 2. Better preparation | Early detection of weak points | Timeline |  | V206
99 | Assembly PP | PT-Phase |  | Commissioning parts | Part | Commissioning parts and car bodies not in correct conditions and delivered on time. | Elaborate coordination | 1. Better coordination 2. Clarification and attention of responsibility in an early phase | Avoidance of rescheduling | Timeline |  | V206
100 | Assembly PP | PT-Phase |  | Working groups (AK) | Organization | No predefined working groups defined. E.g.. AK Roof, AK Doors. Only case-related implementation. | Difficult problem solving regarding cross-disciplinary topics | Early establishment of the most important AK work groups | faster problem solving for critical topics | Process Maturity |  | V206
101 | Assembly PP | PT-Phase |  | ASD Jig Trim 1 | Equipment | ASD Jig was not capable with regard to component touch. | Not enough trials | Using better FMEA for critical assembly processes | Avoidance of failures and troubleshooting | Process Maturity |  | V206
102 | Assembly PP | PT-Phase |  | K0 position for Marriage Line. St. 5/9 | Process | In the Car mix 205/213/206/ 206 4M different K0 position with an impact regarding screw-mountability. | Difficult simulation and calculation | Using better FMEA for critical assembly processes. Discussion in the design meeting's Establish precondition for flexible assembly | Avoidance of failures and troubleshooting | Process Maturity |  | V206
103 | Assembly PP | PT-Phase |  | AD and HAG | Equipment | Low acceptance for new equipment during PT's | Adaptability in shop floor and maturity level equipment | 1. Improve Maturity level 2. Training Production staff in due time | Avoidance of failures and troubleshooting | Process Maturity |  | V206
104 | Bodyshop PP | Design |  | turntable | Process | 4 sets of electrical turntable designed but with only 1 type of car model in this line | technical solution in sales phase not proper | There needs to be sufficient preparation for technology in sales phase to avoid misunderstanding between involved people. Technical solution need to be analyzed and cross checked. | technical solution need to be analyzed and cross checked | Process Maturity | PP | V206
105 | Bodyshop PP | All |  | interfaces with other department | Organization | interfaces with facility team and conveyor team cost too much time | too many information transfer channels, lead efficiency very low | Many interfaces will lead to misunderstanding and delay for important information. It only should have a person in charge of one interface and share information to others, which in order to bu more efficient. Define contact window and information transfer rule at the very beginning | define contact window and information transfer rule at the very beginning | Process Maturity | PP | V206
106 | Bodyshop PP | Concept |  | LOG issue | Process | Width of LOG street at the end of Z2.2 is not enough | Didn't pay enough attention on LOG street and storage area when scenario making | When making the production line scenario, LOG issue should take into consideration and communication with LOG planning &LOG operation is needed. Fully communication with LOG planning, LOG operation edg.related department | Fully communication with LOG planning, LOG operation edg.related department | Process Maturity | PP | V206
107 | Bodyshop PP | B-Phase |  | Wrong loading avoid | Product | Rear panel in Z2.3 clinch station is mirror and have no hole on this part which maybe cause wrong loading parts | Rear panel in Z2.3 clinch station is mirror and have no hole on this part | Feedback to RD department should be taken place and modify the part design such as add one hole, when finding this issue. Set a sample on site and train operator. |  | Product Maturity | PP | V206
108 | Bodyshop PP | PT-Phase |  | LCA | Organization | Too many workers in the past plant, waste manpower | HPV increased and spend more HC cost in the life cycle | Promote use of LCA loading system in new projects. |  | Costs | PP | V206
109 | Bodyshop PP | PT-Phase |  | Process PC | Process | Too much process card paper on site, production not easy check the documents, and update it also is a long time process | Too much paper need to print out on site. | Promote process PC onsite and reduce the documents paper. |  | Process Maturity | PP | V206
110 | Bodyshop PP |  |  | Total Automatic Glue | Process | In the past there are many manual glue, glue quality are not good | manual glue need worker long time training, and the quality are not easy control | Promote all the glue used automatic glue. |  | Product Maturity | PP | V206
111 | Bodyshop PP |  |  | Floor marking | Process | New project onsite floor marking need finished before PT2 | if do not have onsite, may be caused LOG and process interface not clear. | V206 Finished floor marking before CNY/PT2 |  | Process Maturity | PP | V206
112 | Bodyshop PP |  |  | Glue scrapped | Process | There is a lot of surplus glue overtime during commission period. Since the new glue is first used in V206 project and the scrap amount of glue will be assessed as BBAC green energy. We should pay attention to this matter in the project. | The amount of car bodies is few, and the capacity of glue barrels is large. There will be a large number of glue expired and scrapped in each commission period. | In the follow-up project, Exchange series production V206 glue barrels with the new project glue barrels to reduce waste. |  | Costs | PP | V206
113 | Bodyshop PP |  |  | Hand over to SP | Process | Production planning department new project team start handover part function to series planning team form PT1. | Duty and responsibilities of function need to be clarified during the transition process | Refer to 206 for future projects. |  | Process Maturity | PP | V206
114 | Bodyshop PP |  |  | Performance test | Process | In the process of perform test of V206 project, the test was divided into internal test and formal test according to the requirements of the production department. And portal software was used in the test process. | Need to communicate with production in the follow-up project to clear the schedule and planning of perform test | Reference for subsequent projects |  | Process Maturity | PP | V206
115 | Bodyshop PP |  |  | design protection | Process | Secrecy protection measures for new products of V206 models have been implemented. | Work measures and implementation of product confidentiality should be considered comprehensively in new projects. | Reference for subsequent projects, planning and measures have been taken for V254 at present. |  | Process Maturity | PP | V206
116 | Bodyshop PP |  |  | PLUS PC apply | Process | In V206 project, due to process technology adjustment, PLUS and RDS technology update, PLUS PC and code scanning gun equipment were applied for too many times in the process of the project | Summarize experience and input lessons for subsequent projects. | Reference for subsequent projects |  | Process Maturity | PP | V206
117 | Bodyshop PP |  |  | Geo pallet related | Process | As 206 model shares the conveying line with 205 model, and the site storage area of 206 project is small, it is impossible to put all the sled in formal production online. Therefore, additional storage areas need to be found and plans for sled online need be made, lead to a long working cycle of sled quality optimization. | The storage and use plan of the skid needs to be planned in the subsequent project | Reference for subsequent projects |  | Process Maturity | PP | V206
118 | Pilot Plant | PT-Phase |  | Antenna cover assembly tool introduction | Process | During PT phase the assembly of the antenna cover showed to be not robust enough in terms of providing a satisfying gap picture (gap let/right not even / transition of antenna cover to BIW sidewall). The problem solving process showed that the introduction of the assembly BEMI did not lead to a robust handling. Import know who from GER failed as the assembly process is different in Bremen (at least in lead plant) | > tool readiness not tracked > handover pilot plant --> series plant not providing stable process | > BEMIs cross check with assembly methods in other plants > VoCA feedback taken for process optimization already in E phase > tool feedback before LOT 4 cars in series plant needed | > reduction of quality issues in series plant | Product Maturity | Pilot Plant | V206
119 | Pilot Plant | PT-Phase |  | ASHD assembly tool introduction | Process | During PT phase the assembly of the ASHD showed the risk of contact between ASHD module and BIW (risk of damage to BIW and to ASHD module) Import know who from GER failed as the assembly process is different in Bremen (at least in lead plant) | > tool readiness not tracked > handover pilot plant --> series plant not providing stable process | > BEMIs cross check with assembly methods in other plants > VoCA feedback taken for process optimization already in E phase > tool feedback before LOT 4 cars in series plant needed | reduction of quality issues in series plant | Product Maturity | Pilot Plant | V206
120 | Pilot Plant | PT-Phase |  | cockpit / steering wheel assembly process not robust in series production (lollipopp tool not robust) | Process | During PT phase the assembly of the steering wheel column to the steering system (during cockpit assembly) showed not to be robust (lollipopp either broke or part was not able to be assembled. | 2 reasons for the problems: 1) the work process to the cockpit supplier was not defined clearly enough - cockpit supplier receives a work in struction by BBAC- the work instruction needed to be updated many times and was late in the project timeline 2) due to local precaution of steering column parts the concept for a certain part of the steering column was not identical to the production in plant GER --> the same lollipopp part works in GER but not in CHN --> problem was not identified until PT phase problems as the partners thought that the same part has the same characteristics. | 1) if the auxiliary material such as lolipop need cockpit supplier assemble on cockpit， PP need give the correct work instruction and enough technical input to cockpit supplier, cockpit supplier is only responsible assemble the cockpit give correct input to suppler is the obligation of BBAC PP. in the V206 lolipop issue, PP updated many times WI to supplier before a correct WI finally confirmed. 2. PP should consider the different version of part which need auxiliary material. for example，V206 steering column have mechanical and electric version two thickness version lolipop is needed but in the beginning only one thickness lolipop give to supplier which cause the lolipop too loose or too tighten issue on the two version steering column. | reduction of quality issues in series plant | Product Maturity | Pilot Plant | V206
121 | Paintshop Production | PT-Phase |  | ED runners | Process | ED runner on trunk lid (Left side hemming and drainage channel) | Volume of BS glue too less | BS optimization the process of glue and hemming, base on tear down result | less ED-runners | Product Maturity | Body shop PP | V206
122 | Paintshop Production | PT-Phase |  | PVC bubbles | Process | The rear doors PVC bubble too much | BS glue and hemming issue | Do cutting analysis, BS optimization hemming and glue filling. Result is Good. | less ED-runners | Product Maturity | Body shop PP | V206
123 | Paintshop Production | PT-Phase |  | LASD and PVC warehouse space not enough | Process | LASD and PVC warehouse space not enough | New type car and new process application | Warehouse modification in order to increase LASD and PVC storage space. | Increase the warehouse space | Process Maturity | Paint Shop PP | V206
124 | Paintshop Production | PT-Phase |  | Skid touch underbody PVC and cause potential risk | Process | Skid touch underbody PVC and cause potential risk | Skid support point close to welding gap | Shorten skid support point size | Make sure skid not touch PVC | Process Maturity | Paint Shop PP | V206
125 | Paintshop Production | PT-Phase |  | left front door closes by itself | Process | V206 left front door closes by itself (right door no issue). In manual painting booth，operator need keep the door open and painting | 1.Left front door hinge torsion lower than right side | Increase the front door hinge torsion 2.5Nm to 3.0Nm torque result is OK | Painting process OK | Process Maturity | Paint Shop PP | V206
126 | Paintshop Production | PT-Phase |  | Robots painting issue | Process | Robot hook damage the paint of trunk lid edge and there are risks of paint dripping. | The structures of trunk lid are different.(V205&V213 trunk lid edges are covered) | PP develop new jig | less painting issue | Product Maturity | Paint Shop PP | V206
127 | Paintshop Production | PT-Phase |  | Manual masking station for AFA | Process | Manual masking station car body temperature is too high | Car body cooling distance not enough to masking station | operator wear gloves and build new AFA masking station after polish line | lower car body temperature | Process Maturity | Paint Shop PP | V206
128 | Paintshop Production | PT-Phase |  | Demasking station | Process | Demasking station slip and not safety | Wax line conveyor have too much wax residue | Optimize the manual rework station，Move to the behind robot cell | less safety issue | Process Maturity | Paint Shop PP | V206
129 | Logistics Planning | PT-Phase |  | KSP and small pre-assembly | Process | No clear definition about KSP planning between PP/LOG No clear definition about pre-assemblies | Target picture planning responsibility of KS in LOG, but only with capacity shift. PP without capacity for KSP planning, therefore low performance. | For the KSP area planning, layout need to be provided by PP and clear definition about the tasks incl. working instruction for the small pre-assemblies | Clear overview to support for example push button installation and line feeding process | Process Maturity | Assembly PP | V206
130 | Logistics Planning | PT-Phase |  | Change management | Organization | Change management/documentation | Documentation quality of changes and information loop towards LOG | to many changes/optimization during PTs by PP/Prod.. The changes are executed on-site without documentation update and late information to LOG | Logistic planning need to be involved to follow up on the changes in time and to keep the timeline | Process Maturity | PP AS/Prod. AS | V206
131 | Logistics Planning | PT-Phase |  | BS SLT | Equipment | Tolerance of ZB SLT do not match with BS requirement. | Tolerance requirement of ZB SLT from BS is higher than SLT design guideline. | Tolerance issue should be discussed with BS in concept audit phase, in especial ZB SLT | Avoid re-working SLT | Process Maturity | Packaging, BS PP | V206
132 | Logistics Planning | PT-Phase |  | BS SLT | Equipment | SLT Quality of PT batches | SLT quality delivered by supplier not according to defined delivery standard | New process to ensure quality of incoming SLT batches needed, for V206 on-site checking process was installed, further development of process for upcoming car models | BS SLT delivered to robot station in right quality | Product Maturity | Packaging, BS PP | V206
133 | Logistics Planning | Digital-Phase |  | PP body shop line feeding cones for autom. stations don’t follow ECM requirements | Process | If PP / line builder don’t fulfill line feeding cone requirements in their layout planning, line stops during PTs and series process will be caused. | Planning interface PP / line builder don’t consider the required areas for the line feeding cones according to ECM. | For V206 autom. kick in stations had to be changed technically + LOG had to provide further areas to PP in order to balance their space deficit. If the line feeding cones are checked within the digital planning phase, problems will not appear. | Line supply in PT phase ensured, no changes in BS layout required | Process Maturity | Body shop PP | V206
134 | Logistics Planning | Digital-Phase |  | Delay of FAC tasks | Timeline | V206 suffers of penty of delayed facility tasks. | Facility construction work timelines not reliable | Regular meeting in an early stage of the project incl. all shops (like SFM regular FAC meeting in V206). FAC needs to take lead and responsibility for meeting + coordination of their tasks and handover to their costumers. | FAC work finished in time | Timeline | Facility | V206
135 | Paint Shop PP | B-Phase |  | AFA | Process | Less issue feedback form pilot plant since Lot2 cause assembly shop complain from lot4 start in AS | New Process, Less knowledge | enhance communication with RD,Assembly PP,SP. |  | Process Maturity | PP - PS&AS | V206
136 | Paint Shop PP | B-Phase |  | AFA | Process | Masking / Demasking process scope not clear. Big difference with Premise. 38 masking points in begnning. Currently more than 120 points. | new process | Workshop and deep dive from digital-phase for each masking/damasking point. RD/PP - PS/AS |  | Process Maturity | PP - PS&AS | V206
137 | Paint Shop PP | B-Phase |  | AFA | Process | HEAD count planning for new process not clear due to process changing during B-phase. | new process | HC planning should be aligned for new process in the early phase |  | Process Maturity | PP - PS&AS | V206
138 | Press Shop PP | PT-Phase |  | The number of blue collar | Organization | Blue-collar workers do not meet the Demand for V206 | Door inner and door outer loading form changes | When the loading form changes, Press planning needs to take into account the changes in the working style and number of blue-collar operators |  | Process Maturity | PP | V206
139 | Press Shop PP | B-Phase |  | Feature line. Request of sharp featurline needs to be defined already in method. Checking equipment to fullfill the product requirement needs to available in BBAC | Product | Door outer, Fender and Sidewall ,feature line not fullfill design requirement | - No technical specification/standard available - No evaluation of the feature line sharpness in BBAC | - Creation of technical standard for sharp feature lines - Early evaluation of the feature line (by designed, by comparison,…) must be made possible. - Product requests need to be defined in the early project phase and the equipment to check this request needs to be planned right in time. Check of (V254, V295, X294 and) V214 |  | Process Maturity | Press Shop PP/QM | V206
140 | Press Shop PP | B-Phase |  | Surface Release supported by release parts shipped from same parts in German plants is highly supportive | Part | Surface issues found on the lead plant parts will help to increase the sensitivity of those areas in Beijing plant. | Late recognition of surface issues. | Sent parts to defined Milestones/at the time of yellow/green released to BBAC can align the Surface Issue classification. |  | Product Maturity | QM PP/KT PP Stamping | V206
141 | Press Shop PP | PT-Phase |  | Delivery Time for press parts to bodyshop. | Timeline | Official delivery date for single parts to BS was planned 2 weeks before BS Start date. Later it has been preponed to 8 weeks without final alignment that lead to less time available for optimization and lead to several additional batch production for Bodyshop. As a result parts had to be scraped and reproduced. | - Time between Press part Request to BS start date very long (8 weeks) | Stick to the aligned timeline (Parts supply program) that is also sent to the supplier and fitting to the agreed quality level. Optional: Add additional Milestones between BS and PS fitting to the PS Q-Loops with adjusted part amount. (PT's) |  | Timeline | Press Shop PP/Bodyshop PP/ Logistics Production | V206
142 | Press Shop PP | B-Phase |  | Clear Lead for optimization and guidance for PE optimizations | Organization | Optimization areas are mainly defined by Presshop. Optimized areas not always fit the bodyshop requirements. | Different directions for optimizations are given. | e.g. empowered strong AK Lead |  | Process Maturity | Press Shop PP/QM/Body Shop Production/BM | V206
143 | Press Shop PP | Digital-Phase |  | Early phase involvement of BBAC | Organization | Currently only information of results (MO-Testat) forwarded to BBAC. Detailed results discussion with all involved departments necessary. | Missing information transfer from Lead Plant | Earlier and more detailed involvement of BBAC Pressshop and Bodyshop |  | Product Maturity | PP RD | V206
144 | Press Shop PP | PT-Phase |  | Trim line Optimization bundled at PT phase | Process | Some areas had to be touched several times because of different change requests | Hemming process and Part dimension optimization not finally finished at the time of trim line optimization | - Align with BS to first optimize surface dimension, Bend line and the hemming process - afterwards optimize the trim line in one time (same situation in Germany) |  | Process Maturity | Press Shop PP/Body Shop Production | V206
145 | Press Shop PP | B-Phase |  | Racks/Stacking not aligned between BS and ST Planning | Organization | Headcount in BS was saved and additional HC in Stamping was necessary | Change of Stacking in the Racks without alignment between PP BS and PP ST | Align stacking in racks between PP BS and PP ST |  | Process Maturity | Press Shop PP/Body Shop PP/Press Shop Production | V206
146 | RD1 BIW | PT-Phase |  | V206 Fuel flap | Product | Fuel flap to sidewall poor gap & transition issues./ Fuel flap part dimension out of tolerance | Supplier's cubing was released by MP, when deviation between supplier's cubing and BBAC cubing hadn't been clarified. | It would be better if in next new carline project, BBAC gets involved in supplier's cubing release process. Deviation between two cubing's should be clarified asap, to avoid negative influence caused in part dimension optimization. | It will help us to solve fuel flap/charger flap's gap & transition issues more quickly, and avoid project delay caused by supplier's unreliable measurement results. | Product Maturity | RD1, QM | V206
147 | RD1 BIW | PT-Phase |  | V206 Fuel flap | Part | Part optimization takes too long time, three months were taken between last two loops. | Local supplier has zero capacity to propose part optimization plan, decide tooling modification plan, or even provide a timeline. Everything depends on its headquarter in Europe, which always delays China project support by not considering BBAC as its own client. | Current situation should be changed. Local supplier should gain its own capacities to answer BBAC basic asks, such as, provide part optimization plan and its timeline. Local supplier gain its measurement capacity. | It will help to accelerate part optimization. | Product Maturity | MP | V206
148 | Assembly Production | B-Phase |  | training vehicle order | Organization | training order based on options and training timeline needed, normally IPV vehicles will transfer to training car,IPV car ordered by PP,but it has to be a whole vehicle | PP order only TA not whole car | keep information transparency between PP and prod. Regarding training cars topic. |  | Process Maturity |  | V206
149 | Assembly Production | PT-Phase |  | organization | Organization | PP internal working content devison and show clear responsibility and during phase | PP-NTP and series PP handover | clear definition for responsibility and during phase, handover standard |  | Process Maturity |  | V206
150 | Assembly Production | PT-Phase |  | EC management | Organization | no window person from NTP-PP side to miniter EC status and big risk for EC implementation |  | EC monitor set up in NTP function |  | Process Maturity |  | V206
151 | Assembly Production | PT-Phase |  | PSP | Organization | QMP and RD1 need to clarify responsibility and tryout phases |  | clear responsibility between QMP and RD1 |  | Process Maturity |  | V206
152 | Assembly Production | PT-Phase |  | ramp up meeting organization | Organization | window person(QMP,PP-series) have to attend the ramp up meeting |  |  |  | Process Maturity |  | V206
153 | Assembly Production | PT-Phase |  | digital tools | Organization | digital tools(e.g. SFMd) need to be as the premise for all dept. |  | clear definition in project premise book and get released in project meeting |  | Process Maturity |  | V206
154 | Assembly Production | B-Phase |  | special tools | Timeline | special tools especially EX33 tools not in time and can not be verification and optimized in time |  | only get design drawing from germany and make the tools localization |  | Timeline |  | V206
155 | Assembly Production | B-Phase |  | IPV issues tracking | Organization | limit information regarding the IPV issues tracking status,e.g. SRA measures sovling status |  | regular meeting set up involve production |  | Process Maturity |  | V206
156 | Assembly Production | B-Phase |  | different process point with germany | Process | special process different process(e.g. axle preassemble,cockpit preassemble) have to be considered seperately |  | consider the operation between BBAC plant and supplier |  | Process Maturity |  | V206
157 | Assembly Production | PT-Phase |  | Process | Organization | body shop rework in assembly share stations with assembly shop |  | PP-BS need to get alignment with PP-AS to avoid this situation. |  | Process Maturity |  | V206
158 | Conveyor - Assembly | PT-Phase |  | Assembly shop conveyor project -Potential failure risk exist in windy power supply system and no evaluation ativity from process planning team | Process | The windy power supply concept changed from external power supply system to HEMS system during V206 project. But there is no complete process evaluation if system malfunction which should be lead by process planning who trigger the new concept | The new windy power supply concept copied by Daimler planning lacks sufficient safety assessment before implementation | Conveyor planning detect the potential failure mode & rate by detail failure mode analysis. The process evaluation should be done by assembly project team in planning phase before implementation | Reduce the impact on production and cost | Process Maturity | Assembly PP | V206
159 | Logistics Planning | B-Phase |  | TA demand | Part | No one track TA parts when ordering, many TA parts will be canceled in BOM according to PN/code change from vehicle side. TA parts picking time not defined. Sometimes, LOT2B TA will be handover after LOT3. LOG only have total number of TA demand, no idea of detailed demand of each TA customer. | not enough parts for TAs | TA customers (DGRC/PP/192) need to follow PN changes to avoid missing part risk. Process still under discussion. BVA will list picking deadline/picking qty based on each TA customer to show transparency. | fulfillment for TA demand | Process Maturity | RD BVA/PP | V206
160 | Logistics Planning | B-Phase |  | transportation | Process | new ramp-up project required high demand for trunk transportation, which series truck capacity cannot fulfill in time/quantity. production delay due to transportation happens in B phase. | not plan new ramp-up transportation demand earlier | before LOT1 BIW production, there should be coordination meeting with 192/BS PP/LOG focusing on transportation topic. Book a truck for new ramp-up project until SOP. Calculate forklift HC until SOP. | transportation successfully to ensure parts supply | Process Maturity | LOG/192/BS PP | V206
161 | Logistics Planning | PT-Phase |  | BS COMM demand | Part | BIW COMM demand released frequently BIW demand added urgently and irreasonably especially glue parts. LOG handover parts according to ordering demand, but always parts shortage. Glue parts have due date, COMM/production mix production, caused that no valid glue parts for vehicle production, then LOG need to speed up delivery | COMM plan adjusted frequently lineside parts management issue | COMM plan needs to consider more buffer in advance training suggested from PP to production. | reduce missing part risk | Process Maturity | Body Shop PP | V206
162 | Logistics Planning | PT-Phase |  | EX33 claim | Part | EX33 claim process not defined. Always need escalation for new order air freight costs as well as old part leftover costs | unclear EX33 claim process | although EX33 ordering always with SDR/PPAP approved, there still may exist Q topic. Proposal is that PPAP done, QMP need to focus claim. SDR done, RD need to focus. If no one feel responsible, then project need to undertake ordering risk for damaged/unusable parts. process under discussion. | fill in the blank of EX33 claim, therefore production can use correct/qualified parts asap | Process Maturity | QMP/RD | V206
163 | Logistics Planning | PT-Phase |  | JIS module supply | Process | JIS module delivery cannot catch production time, for example, rear seat for PT2, roof panelling for PT1 | supplier not highlight quality issue/availability risk ahead of time | MP/P&S need to train supplier, enhance supplier management. | JIS module delivery in time | Timeline | MP/P&S | V206
164 | Logistics Planning | PT-Phase |  | RFQ | Process | PT need to run series ordering process, but failed because RFQ not back, still need EX33 orders | PPAP finalized milestone is SOP not PT1 | push MP finish PPAP before PT, start tracking from LOT4 to report RFQ status. | cost saving | Costs | MP/LOG | V206
165 | Press Shop Production | PT-Phase |  | The number of blue collar | Process | Blue-collar workers do not meet the Demand for V206 | Door inner and door outer loading form changes | When the loading form changes, Press planning needs to take into account the changes in the working style and number of blue-collar operators | Avoid the loss of productivity caused by the shortage of blue-collar workers | Process Maturity | Press Shop PP | V206
166 | Press Shop Production | PT-Phase |  | Racks design | Process | The roof and fender rack can easily cause the parts to deform | The design of the rack has not been fully verified and tested | After the completion of the material frame design, sufficient experiments and verification are required to ensure the accuracy and stability of the parts loading | Avoid deformation caused by loading of parts | Product Maturity | Logistics Planning | V206
167 | Press Shop Production | PT-Phase |  | Feature line process design | Process | Defect of feature line process design of Door outer | Lack of experience in feature line process design | Process design OP10 drawing forming，one sequence cannot be formed，adding OP30 forming process | Accumulate experience in feature line process design, improve part quality and reduce manufacturing cost | Product Maturity | Press Shop PP | V206
168 | Press Shop Production | PT-Phase |  | The process layout | Process | The process layout of door inner is not convenient for parts load and quality inspection | The process design does not fully consider the parts load | The process design should take into full consideration the convenience of loading parts and quality inspection to avoid the reduction of production line efficiency | Improve parts loading convenience, improve production efficiency | Process Maturity | Press Shop PP | V206
169 | Press Shop Production | PT-Phase |  | The process layout | Process | Fender outgoing direction at the end of the E line is not convenient for quality inspection | The process design does not fully consider the quality inspection | The process design should take into full consideration the quality inspection to avoid reducing the production line efficiency and affecting the quality inspection effect | Optimize the outgoing direction of parts,to facilitate the quality inspection of parts | Product Maturity | Press Shop PP | V206
170 | Press Shop Production | PT-Phase |  | The process layout | Process | Hood outer outgoing direction at the end of the E line is not convenient for quality inspection. (The discharging speed at the end of the line is too fast to check） | The process design does not fully consider the quality inspection | The process design should take into full consideration the quality inspection to avoid reducing the production line efficiency and affecting the quality inspection effect | Optimize the outgoing direction of parts,to facilitate the quality inspection of parts | Product Maturity | Press Shop PP | V206
171 | Bodyshop Production | PT-Phase |  | Grounding Block problem of Stud Welding | Process | 1. Resistance of grounding line exceed ECM Standard 2.Grounding Blocks are in wrong position | No clear experience on stud grounding topic | 1.should consider grounding blocks' position in D-phase, avoiding glue, different parts and non-full surface 2.should measure resistance as early as possible | Issues can be solved on time | Timeline | Body shop PP | V206
172 | Bodyshop Production | PT-Phase |  | add the fixture when mig welding | Process | Add the fixture when welding the mig seams on the roof cross grider with side wall. | The seams' gap in this area is more bigger, mig welding seams' quality is no goog by these gap. | Mig welidng the seams on the roof cross grider with the fixture, the seam's gap is less than before and the welding quality have good progress. | make the MIG seam quality progress | Product Maturity | Body shop PP | V206
173 | Bodyshop Production | B-Phase |  | Concavity problem in trunklid upper sheet | Process | For trunklid laser fillet welding/brazing the upper sheet should not have concavity in the welding edge. This concavity from press shop will serverly affect production stability. | Press shop cutting concept | For trunklid laser fillet welding/brazing the upper sheet should not have concavity in the welding edge. If this is not avoidable, the curve shold be as small and smooth as possible. | No scrap for this | Costs | Press Shop PP | V206
174 | Bodyshop Production | PT-Phase | Digital-Phase | spot welding charactiristic definition issue | Process | Many 3 layers spot welding point does not have 2 separate characteristic definitions for each nugget. And the thinnest sheet side does not have FP definition. | in Digital model there is no definition. | All 3 layers spot welding point should have 2 separate characteristic definitions for each nugget. And the thinnest sheet side shold have FP definition. | Decrease the risk of fault definition. | Process Maturity | RD | V206
175 | Bodyshop Production | PT-Phase | Digital-Phase | process | Process | glue application on sidewalls using stationary guns. | poor process | it is recommened to using a robot guided glue gun to apply seams on sidewalls and other big parts. | stable qulity and process. | Process Maturity | PP | V206
176 | Bodyshop Production | PT-Phase | Digital-Phase | process | Process | it is difficult to apply the sealing seams on wheel house (SG area) | apply the seam on sidewall reinforcement panel instead of sidewall outer. And surface is very narrow. | apply the seam on sidewall outer, because the surface is more wide than sidewall reinforcement panel. | stable qulity and process. | Process Maturity | PP | V206
177 | Bodyshop Production | B-Phase |  | Robot programming | Equipment | Before YBO, checking of Robot programming found out several joining process has wrong point number | Man made mistakes while making the program | There should be a check to guarantee the accurancy of programming | Prevent future quality issue | Product Maturity | supplier | V206
178 | Bodyshop Production | PT-Phase |  | Gripper problem casuing HSN not stable | Equipment | HSN point from fixed gun has position shift because gripper could not hold parts stably | Gripper not at good status | Should pay attention to the status of gripper for fixed gun | stable quality | Product Maturity | supplier | V206
179 | Bodyshop Production | B-Phase |  | Cracks problem for HSN | Equipment | HSN points with cast Al as bottom layer are easy to have cracks. Some of them could not be improved and need redefinition of point class | design issue | Pay ateention to the HSN quality with cast Al as bottom layer, take actions when cracks are found | Issues can be solved on time | Timeline | PP/RD | V206
180 | Bodyshop Production | PT-Phase | Digital-Phase | consider the integration | Timeline | for mixed line, not enough consideration the integration of different model at digital phase, decrease the modification as much as possible. | not so flexible and awaste of the commisioning time. | Consider the integration of different model at digital phase, decrease the modification as much as possible. | more flexible and lean. | Process Maturity |  | V206
181 | Bodyshop Production | B-Phase |  | commsioning with consideration of cycle time | Process | As the YBO test only ten part, the issue with SLT change and sensor is not revealled in early phase. And during PT1 performance test, the issue influence the cycle time. | internal commisioning is not enough. | Before PT1, Line bulder need to test the auto running of the production as much as they can to find issues and optimized. | Get the equiment a better status, pay more attention on the quality and process optimization | Process Maturity |  | V206
182 | Bodyshop Production | B-Phase |  | part organization more reasonable | Part | LOT4 and PT1, the quality and commissioning parts are not enough. | cross function communication not engough | Get alignment of the parts requirement with quality, production and commissioning at early phase. | To make the commissioning more fluent and sufficient. | Process Maturity |  | V206
183 | Bodyshop Production | B-Phase |  | pre-bending process | Process | pre-bending inner panel before robscan welding process | new design concept, no pre-bending information import to production before B-phase. | move pre-bending station to after robscan process, and bending on the reinforcement. | ZB X dimension can be controlled. | Process Maturity | PP | V206
184 | Bodyshop Production | B-Phase |  | HD laser welding turn table optimization | Equipment | HD laser welding turn table too high, high risk for adjustment safety and efficiency. | Lack of comprehensive consideration in the planning. | base on current status, add two steps around the turn table. | Safety can be guaranteed, high efficiency for dimension work. | Process Maturity | PP | V206
185 | Bodyshop Production | B-Phase |  | MH corner area transition control | Equipment | Hood ZB Inner corner can't be ajusted in Z direction, which influence the hood to bumper transition. | Lack of experiences in fixture design. | Add fixture in corner area to make Z direction is adjustable. | ZB corner transition can be controlled, which is good to mountimg dimension. | Process Maturity | PP | V206
186 | Bodyshop Production | B-Phase |  | MH inner pre-bending in press part | Process | Pre-bending inner panel before body shop process, but pre-bending data don't be taken into account in body shop fixture design. | No pre-bending information import to production. | Take pre-bending data into account in fixture design stage. | Dimension quality stable and good | Product Maturity | PP | V206
187 | Bodyshop Production | B-Phase |  | MH press part large springback issue | Product | Hood inner panel is very different with press shop fixture and ZB fixture. | The hood inner is aluminium and thin in size, so the springback is large. It's difficult to decide the springback law using the usual compensation method. | Control the press part springback in compensation. | Dimension quality stable and good | Product Maturity | Press Shop PP | V206
188 | Bodyshop Production | B-Phase |  | MH production line poor design issue | Process | Two hood types use same production line, and two downholder/GHI are used. | Save cost and guarantee cycle time | Two hood should be control separatelly. The information of hood GHI and downholder should be marked in plus system | Dimension quality stable and good | Product Maturity | PP | V206
189 | Bodyshop Production | B-Phase |  | glue squeeze out too much influence the PVC status | Process | glue squeeze out too much when glue use right diameter and track. PS complain influence the PVC. BS need taking lots time to clear the glue. | design issue | should consider the glue squeeze out status. Add people or time to clear the glue. Or make standard to squeeze out. | decrease the cost of manpower and material | Costs | RD/PP | V206
190 | Bodyshop Production | B-Phase |  | Gluing issue rear apron upper AS42 | Process | The main problem is the NO. 60004099 gluing: there is a high risk of collision between the glue gun and car body, as well as problems with the quality of the glue. | the sidewall outer panel at ST 020 is only pre-installed(tamping), the outer panel at the NO. 60004099 glue position has poor stability in the Z and Y directions, when the car body go to glue in next station | Add fixture to control the sidewall when gluing | stable quality | Product Maturity | PP | V206
191 | Bodyshop Production | B-Phase |  | PVC issue | Process | PVC painting poor | big gap between tail lamp panel and sidewall | Small rounded radius design of vent parts |  |  | RD | V206
192 | Bodyshop Production | B-Phase |  | Inline reference | Process | Inline did not design reference at the upfront design | Inline used Helix and Emitter. So Lot PT phase add referenc is difficult | Inline upfront design adds reference | High efficiency for dimension work. | Process Maturity | PP | V206
193 | Bodyshop Production | B-Phase |  | Inline shading | Process | Inline station don`t have shading cloth | The strong solar irradiance influence the IMT working stability | Inline upfront design adds shading | High efficiency for dimension work. | Process Maturity | PP | V206
194 | Bodyshop Production | B-Phase |  | Bestfit robot installation position | Equipment | Bestfit robot installed on the crack of two floor | crack between the two floor become bigger | robot installation position should be one side of the crack or install a big plate in the station | more stable quality | Product Maturity | PP | V206
195 | Bodyshop Production | B-Phase |  | SME | Equipment | SME installation environment should be stable, no shaking | the SME is installed on the shaking platform | the environment of SME should be stble and no shaking | SME system can pass the MFU | Process Maturity | PP | V206
196 | Bodyshop Production | B-Phase |  | Equipment protection | Equipment | The welding spatter will damage the equipment of the gripper. | Design a protect cover | Design the protect cover for the gripper need to be disengaged from the robot. | Reduce the downtime. Avoid the equipment damage | Process Maturity | supplier | V206
197 | Bodyshop Production | B-Phase |  | fixture design | Equipment | BS fixture don’t have additional clamp of press part measurement | BS fixture don’t have additional clamp of press part measurement | At design phase consider add fixture like press part measurement to make it easy for dimension control, and better for analysis and dimension control | To make a better dimension control | Process Maturity | Body shop PP | V206
198 | Bodyshop Production | B-Phase |  | laser fixture | Equipment | For laser fixture, too much pipes in station, difficult for fixture adjustment and batch change. | too much Cylinders in the fixture, and every pipe have cover pipe, make adjust space limited | Consider the pipes assemble location and make adjustment space enough, and make sure pipes not damage when batch change | To make it faster and easier for dimension adjustment and batch change | Process Maturity | Body shop PP | V206
199 | Bodyshop Production | B-Phase |  | fixture aviod fix on the ground slab | Equipment | some fixture and equipment fixed on the ground slab, make dimension and process unstable | some fixture and equipment fixed on the ground slab, make dimension and process unstable | AT design phase consider fixture location, avoid fixture on the slab, if cant avoid, make a bag base board to make fixture moving in same direction | to make dimension more stable | Process Maturity | Body shop PP | V206
200 | Bodyshop Production | PT-Phase |  | impact design not match MBN standard | Product | impact quality need engough distant go eage, but design decide can't match | E-phase of product & process match can't found | product and quality requirement match check in early phase |  | Product Maturity | Bpdy Shop PP/RD/Pilot plant | V206
201 | Bodyshop Production | B-Phase |  | Downhold support | Process | Hemming downhold support is not so strong, after loading, downhold moving in hemming bed | Downholder support is far away to the center, cennection in solft, | 1. downholder support should be strong that can be hold it, 2.reduce adjust in the support, make adjustment in the ring to fit with hemming bed GEO pin, 3. Hemming bed Geo pin reduce useless length | To make it running smoothly and make inner panel position stable, and glue process stable | Process Maturity | PP | V206
202 | Bodyshop Production | B-Phase |  | process effect to parts dimension | Part | BIW dimension change after painting shop | heating or process make parts dimension change | after Painting shop BiW dimension change comparion with Z4 status by CMM | consider the change before AS, adjust the presetting or design | Product Maturity | PP/RD/QM | V206
203 | Bodyshop Production | B-Phase |  | parts dimension difference | Part | dimension difference effect the assembly status | press part and ZB part dimension difference | difference cause Z4 or AS status not good | must control in tolerance;all parts monitor all surface difference, not only measure points, in early of phase can scan the difference to optimization | Product Maturity | PP/RD/QM | V206
204 | Bodyshop Production | B-Phase |  | Tech. welding process influence ZB dimension. | Part | for HOPs parts the thermal energy of welding(ex. Laser tech.) always deform the part and big influence to ZB dimension. | the thermal energy of welding (ex. Laser tech.) and no any solution from design side. | the best way to make compensation on the press part or on the BS fixture according to simulation. | build up good CMM ZB and good quality final car. | Product Maturity | PP/RD/QM | V206
205 | Bodyshop Production | PT-Phase |  | Dimension | Product | The specific transmission shaft function dimension deviation in Y direction. | The firewall Y direction deviation cause the issue. | The firewall Y direction have been identified as transmission shaft dimension influencing factors. | The specific transmission shaft Y dimension can be optimized. | Product Maturity | Dimension | V206
206 | Bodyshop Production | PT-Phase | Digital-Phase | Dimension | Equipment | BS PS finish line SME measurement no accurate | SME have no zero function compensation | BS PS finish line SME measurement need zero compensation for the alighment points | mesasuremnt data more accuracy | Product Maturity | PP | V206
207 | Bodyshop Production | B-Phase |  | Dimension | Process | Bestfit setting dimension not accurate | screwing process influence to the dimension | add 180 degree reopen process | Bestfit dimension more stable | Process Maturity | PP | V206
208 | Bodyshop Production | B-Phase |  | CMM pallet | Process | Pallet IMT do not correlation | Pallet do not have CMM report | Pallet adds shading CMM report | High efficiency for Pallet dimension work. | Process Maturity | PP | V206
209 | Assembly Series Planning | PT-Phase |  | Organization | Organization | organization not stable and the team members & managers quit project much earlier than the project finish date, and function missing | work progress stop or slow ,data missing ,decision changing, quality problems. Like no change management function, and no KSP planning function etc. | the working loop members and managers should be stable from the beginning to the end, if someone has to quit , enough time and right person to finish handover | work progress can be ensure, work quality will be good | Process Maturity | WPL | V206
210 | Assembly Series Planning | PT-Phase |  | TA deliverables | Organization | TA deliverables poor quality or missing | output with poor quality, can't be used output missing till deadline w/o notice | make sure TA who is working on BBAC project, really be asked and managed properly and finish the task with high quality on time | Project deliverables can be ensured and deliver on time, risk of production and quality can be guaranteed | Process Maturity | WPL | V206
211 | Assembly Series Planning |  |  | Project scope | Organization | 206 has cycle1, cycle2 and cycle3 and cycle1 only has part of new car types, if the cycle2 and cycle3 are in the project scope is unclear. Some of phases among cycle 1,2,3 are parallel, task and work contect unclear | miss control,miss responsibility, like who should working on V206 Hybrid in cycle3 preparation? | all of new car types should be considered if the timeline is really near to eachother, not only focus on SOP data, tryouts data is more important, the planning should be considered as ealier as possible, if not waste time and cost finally | one time work for one project, good quality and less cost payment | Costs | WPL | V206
212 | Assembly Series Planning |  |  | Premise | Organization | Project premise and planning premise not detailed enough and not aligned with each dept | Project progress slowly or double work, such as the line speed definition is unclear and not aligned, caused 2nd time line balancing ; V213 or V206 as the lead car not clear and not aligned, caused additional line balancing work; the exsiting 205 car type still producing and v213 hybrid will SOP before 206 not considered, caused addtional time line balancing; KSP not in IPV scope, caused several months discussion and meeting etc. | Premises of project, process planning and equipment planning should be clarified and aligned with each dept. before the project starts or at the beginning of project starts, and should be tracked or updated if any changes have to do. | clear task to each work group and much less waste of time, cost and manpower etc. high work efficiency | Costs | WPL | V206
213 | Assembly Series Planning |  |  | Decision | Organization | Decision not be followed or decision too slow | such as many decisions about NLC implementation, especially small pre-assembly w/o tools to LOG, all of process planning are ready based on the decision, but not be followed by LOG, no reasonable reply, KS to LOG as well; Headcount risks decisions about equipment and process, not get decision before PT3 start,even SOP starts, normally should be clarified during or after PT2. | WPL should has highest power in the project and make decision in time if all of data shows that have to be happened soon. | ensure project tasks finished on time and high quality, reduce waste of communication, double work, waiting etc. | Timeline | WPL | V206
214 | Assembly Series Planning | B-Phase |  | premise | Organization | IPV decision not followed by LOG | IPV have decided the samll pre-assembly parts ,but LOG reject following the decision during PTs | IPV confirmation signed by LOG | Avoid open discussion during PTs | Process Maturity | Management / ipv L4 | V206
215 | Bodyshop PP | PT-Phase |  | A Pillar area black glue one-sided bond - MRA DT | Process | A Pillar area black glue one-sided bond | Gluing system not be correctly dealt with during the glue type change | To focus on the whole gluing system when there is black glue type change, to eliminate potiential risks for glue defects. | To avoid the black glue one-sided bond issue | Process Maturity | PP | V206
216 | Bodyshop PP | PT-Phase |  | Fender hemming glue not cured - MRA DT | Process | Fender hemming glue not cured | 2K glue weight ratio not correct | 1. Measure the 2K ratio before each production batch 2. Follow lead plant experience timely, correctly setting the equipment parameter. | To avoid the hemming glue not curred defect due to 2K glue weight ratio not correct | Process Maturity | PP | V206
217 | Bodyshop PP | PT-Phase |  | A Pillar water pipe clip melt - MRA DT | Product | A Pillar water pipe clip melt | Current clip A0009959677 melting point is 165°C, E-coat oven temperature is about 180°C. Part was melted in E-coat oven. | Change the clip form A0009959677 to A0039955177 (use on VW205) through EC change. | To avoid the wrong use of water pipe clip and futher issues caused by the wrong use. | Process Maturity | RD | V206
218 | Bodyshop PP | PT-Phase |  | supplier part main floor spot misssing issue - MRA PAB | Process | supplier part main foor spot misssing issue | 1.Wrong operation for welding adjustment for welding splash optimization 2.No effective checking after adjustment and no cross checking from quality to verify the adjustment | 1.Optimize PLC program: Adding welding points quantity check function. 2.Optimize the change management procedure: make verification for at least 3 parts and make record after adjustment | To avoid spot missing batch issue | Product Maturity | MP&Supplier BS | V206
219 | Assembly PP | B-Phase |  | Wiper motor tightening process missing - Torque | Process | BBAC Wiper motor tightening process missing | Supplier make pre-tightening to 1.5Nm before part delivery to BBAC. BBAC need tightenign to target 10Nm. The tightening in BBAC missed when planning for the process. | Process deep check before B phase to aviod same issue happens | Avoid torque loose battch issue | Process Maturity | PP | V206
220 | Assembly PP | PT-Phase |  | Trunk-lid hinge tightenign process missing - Torque | Process | Trunk-lid hinge tightenign process missing(BS tightening in AS) | this joint is tightened in AS by BS. BS PP forget planning for the process. | Process deep check needed. Espersially for the connections tightening in AS by BS. | Avoid torque loose battch issue | Process Maturity | PP | V206
221 | Assembly PP | PT-Phase |  | Door hing torque loose issue after RGA test - Torque | Process | Door hing torque loose issue after RGA test | the connection is designed by supplier with target 23Nm, but the target for V206 is 20Nm | Pay more attention for the result after RGA to clarify whether the target is suitable or not before PT phase; | Avoid big issues happen after delivery. | Product Maturity | RD | V206
222 | Paint Shop PP | PT-Phase |  | PVC - MRA PAP | Equipment | Paint shop skid contact with PVC and cause leakage | Paint shop skid not match with V206 model | 100% check the match of skid with new models | Avoid rework | Product Maturity | Paint Shop PP | V206
223 | Paint Shop PP | PT-Phase |  | PVC - MRA PAP | Equipment | PVC contact with brake oil pipe | PVC too thick | Control the thickness of PVC | Avoid rework | Product Maturity | Paint Shop PP | V206
224 | Paint Shop PP | PT-Phase |  | PVC - MRA PAP | Equipment | Rear doors' PVC bubble | BS hemming glue | For hemming glue, BS should make more adjust to match with PVC | Avoid rework | Product Maturity | Body Shop PP | V206
225 | Paint Shop PP | B-Phase |  | color release - MRA PAP | Product | 1. Color deviation between antenna panel and C-pilla 2. Color deviation between door handle and door | 1. C pillar is not normal check point on other models, no special attention is paied. 2. For new color, hue direction not aligned in advance. | 1. For new model, special check points should be distinguished in advance. 2. For new color, hue direction need be aligned as early as possible, and small part supplier should also be informed. | Color release efficiency can be increased | Product Maturity | PP-paint Paint shop R&D QM/PAP MP | V206
226 | Paint Shop PP | B-Phase |  | color release - MRA PAP | Process | Color should be OK released before customer car produced. | 1. tryout start time 2. tryout body quantity | 1. tryout start time as early as possible 2. More try out bodies should be planned | All colors can be OK released before customer car produced | Product Maturity | PP-paint R&D QM/PAP MP | V206
227 | QM | PT-Phase |  | MRA PAF | Organization | No DCF standard input, BBAC define the standard until PT2 | China speicile carline, and Germany standard can not apply directly | QM/RD/germany QM/germany central Q together workshop/alignment | the experience can implement in furture car lines | Process Maturity | QM/PAF | V206
228 | QM | B-Phase |  | MRA PAF | Organization | B-phase gap/transition standard input responsibilty not clear | Pilot plant think the standard should input by QM Planning QM Planning only get standard with mother plant, not Germany Pilot plant, but in B-phase mother plant has no standard | 1. for resposibility BBAC pilot plant and QM planning still not alinement 2. for V254, pilot plant helped to get the standard from Germany Pilot plant | enhance working effeciency reduce the communication cost | Process Maturity | R&D Pilot plant QM/Planning | V206
230 | Assembly PP | B-Phase |  | Door on assembly | Process | With the new concept from the door hinges with striker the Assembly must stop the Line for every car to install the doors | The Door on Assembly is not easy to fullfiel. The optimasations from the Equipment , Lights, Training are not the simular Process like MFA. | MRA and MFA Concepts are different. The Pit a big step under the car is helpful. | No down time in the Production | Process Maturity | WPL | V206
231 | WPL office | B-Phase |  | Product and process reliability | Process | PFMEA is not finish before the PT | PP start late | Start the PFMEA analysis early and finish before PT | Identify the risk first, and avoid the failure | Process Maturity | WPL | V206
232 | WPL office | B-Phase |  | Product and process reliability | Process | Control plan is not finish before the PT | PP start late | Start the control plan early and finish before PT |  | Process Maturity | WPL | V206
234 | Assembly PP | B-Phase |  | Equipment | Equipment | The scanner can not scan the new QR-code on the new parts | The old scanner can not scan the QR code, not enough verification before | Have enough verification during pilot plant | Ensure the process can be done by the plant | Process Maturity | Jens Schloesser-TPL/PP | V206
235 | Logistics Planning | PT-Phase |  | Equipment | Equipment | The vehicle black label print wrong information | Wrong label print by the back up printer, could because the template wrong in the back up printer. | Update the right template into the printer for both main and back up printer, and verify after update. | Ensure the product quality | Product Maturity | Logistics Production | V206
236 | Assembly PP | PT-Phase |  | Equipment | Equipment | Front windshield and rear window glue are different, but share the same glue nozzle. Risk to mix the glue. | Gluing concept of the design | Use different nozzle to gluing different glue | Aviod glue mix to ensure the product quality | Product Maturity | Jens Schloesser-TPL/PP | V206
237 | Q-Control | PT-Phase |  |  | Organization | Verification result forecast not accurate and short time to prepare | RRM close to last phase audit, and far from next phase | The RRM should not be so early. Or Q-control team will not provide the failed issue and forecast summary at RRM. | More accurate summary information | Process Maturity | RLM | V206
238 | Q-Control | PT-Phase |  |  | Product | ZEUS/SFMD not reach target | Audit time period too long, even not finished before next phase tryout. | Audit time due date should be one week earlier than Q-milestone workshop | More reaction time | Timeline | WPL | V206
239 | Q-Control | PT-Phase |  |  | Product | ZEUS/SFMD not reach target | The target was defined in subejective way 2 years before, and is not feasible for every MFA/MRA new project | For next NPP, Q-control and PLQ align together to redifine the target. MRA and MFA maybe need split, and the derive model also could be defined separately following different lead model | More feasible target | Process Maturity | Q-control/PLQ | V206
240 | Q-Control | PT-Phase |  |  | Process | FTC issue was not escalated in Q in a smooth way | There is no regular FTC highlight report publish, and no follow up plan in working level And no escalation rule for production highlight topics. | 1, Suggest to put the FTC top issues in regularworkshop in production, 2, Invite highlight topics IRA to present in WRM as separate topic, no need every time esclatae to AK Maturity when issue is become urgent. | More smooth and clear defination for tracking, | Process Maturity | Production/CEP | V206
241 | CMM | B-Phase |  |  | Product | Trunk lid CAD (open position) can not evaluate the real status in body shop very well | After Bodyshop there will be lamp\lock hinge assembly, when it is closed, some area will be in force and deformed. So there are 2 status in CAD, close position and open position. But during our tryout, we found open status can not evaluate the real status in body shop very well. | 1. Input close/open position information 2. Input release files about open/close status simulation. | save a lot of time for quality issue solving and BS testing part. | Timeline | RD | V206
242 | Body Shop PP | B-Phase |  | KFU is too early for Dimension Team | Part | Quality Status of In-house press part [RED] - Press part die home line integration start with LOT3 - Less Optimization Time until KFU /LOT3 Big effort to come close the KFU Targets[QZ/DT] during LOT3. Verification of open topics in LOT4 | Press parts supply to body shop too late. | Need minimum Yellow In-house press parts to optimize the Dimension and Joining Quality in Target Range of KFU. Keep the BS Internal Quality Milestone KFU in LOT3 - Take Audit mark of KFU only as reference of stability. Final KFU Verification of open Topics in LOT4 | body get more maturity and stablization before PT1 code 018. | Product Maturity | Stamping / BS | V295
243 | Bodyshop Production | B-Phase |  | Production & TSS achieved all tasks with high effort and limited qualified Manpower during B Phase | Organization | Complex Technologies are implemented for a young growing up plant with half year series production experience with X247 Limited qualified Manpower in the earlier Phase available for V295 | Lack of qualified manpower | LL for further Integration Projects @ Shunyi: V295 /X294 Headcount and qualification are planned Technologies Trainings for Eva2 models done Shunyi Body shop is also qualified to run further Integration Projects LL -Further greenfield Project@BBAC Consider in the earlier Phase Qualified Manpower to attend Design Meeting from Beginning Qualification for New Technologies in advance for new Plants [Frontloading Prinzip] | production and TSS will dedicate less efforts with a better outputs | Process Maturity | Body Shop Production | V295
244 | Bodyshop Production | B-Phase |  | New technology training & STA | Organization |  |  | - A Team support for Ultrasonic device commissioning. UT STA onshore support Qualify/Update MRA1 HOP Center; Local technical team at BBAC incl. qualification plan - MRA1 for new technology, HSN/Impact/FLS/Alu-laser BS&ST Project ¦ MRA1 lead Shunyi plant New technology check list Yellow Buyoff checking together Engineers and blue collars are trained in MRA1 - Shunyi for Alu-spot welding, HOP Alu spot welding Shunyi lead MRA1 plant Alu spot welding check list Engineers are trained in Shunyi plant DT standard sharing with MRA1 |  | Process Maturity | Body Shop Production | V295
245 | RLM | B-Phase |  | Issue tracking / transparency | Process | SRA as official process issue tracking tool not handy for production to use, Excel list & SFM Digital as compensation parallel running caused redundant work, common picture need to be aligned btw Prod / PP | Station Readiness System is not handy to use for BBAC production colleagues (Language / Access issue) | Parallel tracking process issue in Excel list / SRA / SFM Digital Currently aligned btw PP / Prod to classify Priority 1 issues to transparently track in SFM Digital Further alignment needed | improve the tangible efficiency and aviod the double work for nothing. | Process Maturity | RLM | V295
246 | Assembly PP | B-Phase |  | Special tools | Organization | Reporting | During b-phase V295 reporting only to pilot plant, focus on tools for pilot plant | Reporting: 1 overall report for special tools With B-phase X294 start same report to pilot plant and production | Transparency on status special tools | Process Maturity | Assembly PP | V295
247 | Assembly PP | B-Phase |  | Special tools | Process | Ordering/delivery process | Due to long EX33 order process (~8month) and short time between LEAD plant and China No availability of design and concept of tools early Late release of tools in Germany No guarantee of delivery for start b-phase (only local special tools possible) | With reporting creating transparency Local special tools for start B-phase available | Specials tools availability in time | Timeline | Assembly PP | V295
248 | Assembly PP | B-Phase |  | Special tools | Process | Verification | During B-phase verification special tools by pilot plant and later production – different verification results | Verification from production and pilot plant during B-phase together only one voice to planning Additional verification during IPV release of special tools production and planning together (tools which have been not verified in b-phase) | Special tools readiness | Timeline | Assembly PP | V295
249 | Assembly PP | B-Phase |  | Special tools | Process | Calibration | No clear process and lots of discussion for calibration requirements and process | PP is providing WI and calibration fixtures for special tools which are required by German planning as Input Production is in responsibility for the calibration with input from planning Additional Deep Dive between Planning and production for input will follow | Special tools readiness | Timeline | Assembly PP | V295
250 | RLM | B-Phase |  | STA support onshore / offshore | Organization | Onshore STA is facing great challenges under epidemic situation, TA offshore and digital global exchange conducted as compensation. BBAC local A Team concept is in development to further enhance BBAC launch capability | Onshore STA is hard to get under unstable global epidemic situation. Dynamic STA plan need close alignment with A Team & Production Shops. Large budget was spent due to quarantine (3 weeks or more) | Knowledge transfer for critical points by digital ways. Central coordination in lead plant for resources. Global product WS focus on critical areas door / front / rear. AQF exchange on the car to compare BRE/CN issues. Concept Local A-Team Establish BBAC local A-team and training transfer system Working together with Pilot Plant, Production and Training Center | Savings of onshore budget | Costs | RLM | V295
251 | Logistics Planning | PT-Phase |  | Reorder | Process | From PT, reorder caused by damage during production occurs quite frequently, stock cannnot fullfill the reorder in time. | RD cannot predict the reorder demand in BOM, which cause logistics cannot order reorder demand based on BOM. | Based on V295 PT1/2 reorder experience, PT3 &X294 PTs, RD can add more reorder demand for easily damaged parts. | Short leadtime for reorder, Avoid waste of manpower and material resources | Costs | RD2, LOG, Proc. | V295
252 | Logistics Planning | PT-Phase |  | Linefeeding | Process | PT2 Linefeeding manually | Push bottom not ready for all line | Before Push button is ready, LOG Operation pick all parts manually. After Push bottom is finish, linefeeding way transfer to automatic. | Benefits for linefeeding parts to lineside on time. | Timeline | Logistics Planning | V295
253 | Logistics Planning | PT-Phase |  | GBP | Part | Parts had quanlity issue when assembling parts | Supplier quality issue after Q release | Let lamp unit check parts before sending outparts. | Assembly good parts without delay. | Product Maturity | Logistics Planning | V295
254 | Logistics Planning | B-Phase |  | Truck capacity | Organization | During B-Phase, truck capacity effect 192 linefeeding | Truck capacity not aligned within BDA | Truck capacity to be aligned between LOG Planning/192/LOG | Linefeeding on time | Timeline | LOG Planning/192/LOG LCM | V295
255 | Logistics Planning | PT-Phase |  | Parts availability | Part | Parts late delivery | The pandemic and the global semiconductor shortage | Track with SC/WTO earlier for risk forecast. | Report risk of late delivery. | Timeline | Logistics Planning | V295
256 | RLM | PT-Phase |  | Battery ID bond with Production number | Organization | Different Batteries for different purposes especially during the Ramp-up period of the battery itself. | Will lead to rework and cost especially to delay of Handover | Is Better to aligne with Production Control and Battery project, which Battery ID must go into which Production no. | PP, LOG, Production, Customer | Costs | Battery Plant PP | V295
257 | QM | PT-Phase |  | Late ASL code change may trigger campaign | Organization | it may cause campaign, also waste management resources and project resources for campaign related discussion afterwards | not sufficient alignment before PLS, and also not in-time decision in PLS | every late ASL code change dicussion in PLS must include the aligned campaign pre-alignment results (with SPL and BMBS) | it can ensure the high-quality decision, and avoid the back and forth campaign necessity discussion | Process Maturity | PM | V295
258 | QM | B-Phase |  | No suffient focus on painting issues in B-phase | Audit | no planned audit from Lot1 onwards, no system recording, no centralized failure management | not planned in B-phase audit plan | set-up the loop to earlier decect and solve the painting issues in B-phase. This idea may also rollout to other series Q-sensors audit | better maturity before car build-up in series plant | Product Maturity | Pilot Plant | V295
259 | QM | PT-Phase |  | Late logger installation | Timeline | Long time installation of logger which takes time of RGA testing and cannot be tracking in time | Logger installation plan is not in day by day plan | Put logger installation plan into day by day plan | Better RGA testing | Process Maturity | RD1&3 AK Ramp up | V295
260 | QM | B-Phase |  | Try out phase Body diamention maturity progress not obviously | Process | Current try out phase Bodys diamention maturity optimization progress not visible from phase to phase | Limited commisionning volume | Commisionning volume should be fitting Body maturity opimization plan | Low risk for Body diamention maturity | Product Maturity | PP | V295
261 | AK | PT-Phase |  | Product | Product | seat noise on test track 1. seat headrest 2. rear armrest | rattling generated by headrest normal freeplay , when driving on special road profile ; carry over part from serial production , concept | need to consider China road profile in early design phase , different requirement from China | reduce the risk from filed complaint | Process Maturity | RD/C | V295
262 | AK | PT-Phase |  | Product | Product | IP trim panel noise | concept related of IP trim panel , China complaint Brement car worse , but no complaint; | need to consider China road profile in early design phase , different requirement from China | reduce the risk from filed complaint | Process Maturity | RD/C | V295
263 | AK | PT-Phase |  | Part quality | Part | door panel grab handle noise while twisting | grab handle noise occurred again during PTs , with more parts produced , supplier process not stable | supplier should stablize the process , avoid similar issue happens again and again | insure the maturity of PTs and less retrofit | Product Maturity | MP | V295
264 | AK | PT-Phase |  | Frameless door adjustment | Product | framless door related noise topic | framless door adjustment not stable, several noise topics are related | process stablize as early as possible | less noise issue and down time | Process Maturity | BS/AS | V295
265 | AK | PT-Phase |  | V295 tail lamp | Process | assembly not follow the design concept to assembly the tail lamp , detail JES need in the beginning , PP always later to add to SMP. |  | PP should write more JES in the project beginning phase |  | Process Maturity | PP, Production | V295
266 | AK | CC |  | CMM measurement | Equipment | CMM room didn't have the ability to measure the all V295 cars in CC phase |  | CMM should take the responsibility of the ability of carline measurement. Should be ready on LOT3 . |  | Product Maturity | CMM | V295
267 | AK | B-Phase |  | adjsutment process | Process | there is no body shop learn how to adjust the trunk lid in pilot plant and no templete for adjustment process |  | PP/192 pilot plant should ensure the same process of prodcution line of new carlines , including adjustment process and responsibility. |  | Product Maturity | PP/Production/Pilot Plant | V295
268 | AK | PT-Phase |  | special tools | Process | Cubing sent to shunyi plant too early in LOT3, and Cubing can‘t measure by CMM in shunyi CMM room. Part dimension check impossible, only do fitment test not enough | Cubing sent to shunyi plant too early | suggest cubing sent to shunyi after PT2 | AK.RD1.MP.RD/C. | Product Maturity | QM CMM | V295
269 | AK | PT-Phase |  | V295 VSG window localizaiton | Process | localization of VSG too late, fitment test in end of PT1B result NOK,switch in PT3 from import to local, not time for optimization. Rebulid press mold to replace roller mold by supplier during PT2 to PT3. risk for PT3 supply | localization of VSG too late | localization of VSG should start tryout in lot1 fitment test and tryout should finish before lot4. | PS,MP.RD/C. RD1,AK.AS.BS,QM | Process Maturity | PS.MP | V295
270 | AK | PT-Phase |  | V206/V254/V295 DCF | Process | Three projects in lot phase no offical DCF standard or standard tolerance is big, after PT phase, awalys narrow the tolerance range interally , and increase high FTC issues. but without any concept change.DCF only can reduce by production control and more monitoring. V206 Prio2>90.W206>95, V254 Prio2>90.X254>110.V295 bbac Prio2>130.V295 BR Prio2>140 | No official additional demands and complaints from Chinese quality to R&D or BTV Standards are always inconsistent with Germany | Official announcements require different quality control standards and require input to design R&D for special design for DCF | PS,MP.RD/C. RD1,AK.AS.BS,QM | Process Maturity | QM | V295
271 | AK | B-Phase |  | KD part Q-release due date | Part | KD part optimization and Q-release due date cannot match with BBAC project, which will lead local part optimization due date too late. |  | only get design drawing from germany and make the tools localization | reach high maturity early. | Product Maturity | RLM | V295
272 | AK | B-Phase |  | process | Process | JES needed to show how to adjust FEM, headlamp, and also ajdust hook in CH3 also needed. |  | PP should write more JES to cleaify how to operate in adjust step. | reach high maturity early. | Product Maturity | PP | V295
273 | Assembly PP | B-Phase |  | special tool availability | Timeline | The availability of special tools did not speed up after V206 (ASD, windshield). | Delay of tools | We need to further follow up the process. We already see in V254 and X294 that the process is stabile. | verification of tools in pilot plant phase. | Timeline | PP | V295
274 | Part Availability | B-Phase |  | part ordering based on E/Q- level | Part | The ordering process of parts during B phase based on E/Q- level will have a positive impact --> keep the implementation running. Examples: Star panel, import headlapms | potential to speed up problem solving | The FAP80 inititiae to order parts during B phase with E/Q level shall be followed. The implementation shall be supported. | faster problem solving. | Timeline |  | V295
275 | Pilot Plant | PT-Phase |  | meeting conflicts | Organization | The meetings invited for problem solving (ZEUS Klausur, PSP, DCQ) have conflicts with other problem solving meetings such as ZEUS Klausur of other carlines. As the commodities are set to handle all calrines the meetings cannot be handled at the same time. | alignment between Q Control teams. | Q Control teams need to align the meeting times. | faster problem solving. | Timeline |  | V295
276 | Assembly PP | B-Phase |  | Pipe&Wire Harness online check | Process |  |  | V295 have online check in B-phase each Lot start from LOT1b, to ensure pipe and wire harness relevant issues detected in early phase | Detected issues in early phase and ensure customer cars quality | Product Maturity |  | V295
277 | Logistics Planning | PT-Phase |  | Old Parts scrab management | Part | V295 PT2 cars use PT1b old status parts, and caused VoCA complaint | VoCA complaint | Resposible engineers should comfimed with BVA that PT2 have new parts in BBAC already, and inform BVA and LOG to scrab old parts in the stock | Avoid VoCA complaint | Process Maturity | RD | V295
278 | Launch and change MM | PT-Phase |  | Important changes have tryout ealier | Timeline |  |  | Some important changes such as affect production or cross changes have sample parts tryout on vehicle ealier, to ensure production process and also make sure cross change Ecs change at the same time. | Ensure production process | Process Maturity | RD | V295
279 | Press Shop PP | PT-Phase |  | Material waviness (surface) | Process | Rear door outer V295 shows waviness. After analyze this isseu can already be found on the material sheet from blank supplier. | Material of supplier | - Coordination between PP Press-Shop and material supplier. - Improvement of material quality with supplier. - Testing of material with production. - Feedback to QM, Voca and purchasing. - Issue is now known and countermeasures are defined. - Clear process must still be defined and adressed to all departments for common understanding and action plan. | Avoid misunderstanding and define clear action plan to solve the issues with all departments and supplier. | Product Maturity | QM, Voca, Purchasing, Press-Shop Production | V295
280 | Press Shop PP | PT-Phase |  | Roping Lines on material surface | Process | Roping Lines caused by material supplier. Can be seen on press-parts and finish car (Fender, Trunk Lid Upper) | Material of supplier. | - Coordination between PP Press-Shop and material supplier. - Improvement of material quality with supplier. - Testing of material with production. - Feedback to QM, Voca and purchasing. - Issue is now known and countermeasures are defined. - Material supplier quality must be improved. - Clear process must still be defined and adressed to all departments for common understanding and action plan. - Paint Shop Bremen and BBAC have a different process (Coating). In Bremen the roping lines on the press parts do NOT occur after painting anymore. - Different Paint Shop process between factories, leads to different material quality acceptance. Must be defined at BBAC by QM. | Avoid misunderstanding and define clear action plan to solve the issues with all parties. | Product Maturity | QM, Voca, Purchasing, Press-Shop Production | V295
281 | Press Shop PP | PT-Phase |  | Hood Inner Rack part amount not changed | Part | Germany Hood Inner rack (LT) amount reduced from 45 to 27. Logistics Shunyi did not take over this change (no Inforamtion share). Press-Shop got feedback from Body-Shop that ZB Hood dimension is not stable. Root cause: Hood Inner gets deformation in rack due to many parts stacked on each other. | 1. Too many parts in rack (LT) 2. With new hood inner design consider different rack design. | - Support check deformation of parts together with Logistics. - Check if part amount in racks is correct and do make sense. - Feedback Logistics Germany communicate changes to Logistics at BBAC - Handover the problems from production caused by racks to Logistics | Define responsibility of racks (Logistics) and support Logistic with this kind of problems. | Process Maturity | Logistics Planning | V295
282 | Press Shop PP | PT-Phase |  | Trunk Lid Upper/Lower Flange curviness | Process | Stamping method process causes flange curviness. Flange curve has negativ impact in Body-Shop welding process of Trunk Lid Outer panels. | Forming process | Problem must checked in early phase during simulation. Feedback to RD for design change of Trunk Lid or change stamping method process plan, to produce parts without curviness. | Avoid same mistakes for next carline or change stamping method process plan. | Process Maturity | RD/KRE, PP Press-Shop, BodyTec, PP/K | V295
283 | Press Shop PP | PT-Phase |  | Trunk Lid Upper Flange collision with clamps in Body-Shop | Process | If the flange of trunk lid upper is in minus tolerance or general in minus, it will have collision while clamping process in the welding station. | Tolerance concept and Body-Shop station (clamping design) is not matching. Risk in the process if press-part flange is in minus. | Produce flange of press-part in plus tolerance (+). Use single sided tolerance. Feedback to Body-Shop Planning and RD/KRE. | Review tolerance concept and Body-Shop clamping process for Trunk Lids and Liftgates. | Process Maturity | RD/KRE, PP Body-Shop | V295
284 | Press Shop Production | PT-Phase |  | Racks | Process | The dimension of hood inner wheel arch area deviation comparison between the bottom and upper parts, resulting in the instability of ZB | The parts stacked horizontally, also affected by the product shape | This issue can be checked earlier and deep communication with German plant. |  | Product Maturity | Press production/ Press PP/ Logistics | V295
285 | Press Shop Production | PT-Phase |  | Production | Part | Cracked sidewall press parts on two BIW customer cars | The limit test parts cracked , and transfer the cracked parts to BS by mistake. | The limit test part all scraped. Before divery the PT parts, prodution check the label and quality. Discuss with BS, clear up the old parts in stock in time. |  | Process Maturity | Press Shop PP/Press Shop Production | V295
286 | Press Shop Production | PT-Phase |  | Surface quality | Process | Rear door outer stripe line issue | The process of blanks production in suplier plant not reasonable | Clear the aluminum outer part stripe line release standard. The blanking line prodution check the defect earlier. |  | Product Maturity | Press Shop PP/Press Shop Production | V295
287 | Body Shop PP | PT-Phase |  | Parts | Part | Production dimension/joining team/supplier/PP with too much argument for part usage, complain not enough part supply and planning at the beginning | 1.All commissioning parts function is not defined clearly. 2.Parts usage should be combined with some function or quality test in same purpose. | 1.All commissioning parts function should be defined with all parties. 2.Part quantity order aligned with all parties before Planning. 3.Part usage and managed with transparent share in weekly meeting. | 1.It will help us to reduce the argument during commissioning and effectively improve the parts usage. | Process Maturity | PP | V295
288 | Body Shop PP | PT-Phase |  | LOG interface | Organization | Logistics parts occurred some problems, e.g. transport delay, quality problems, wrong amount etc. Every bodyshop Z-planners contact with logistics at the same time and different routes, disorganized and dismanagement. Bodyshop internal coordinater and interface people should be clarified to LOG. | Non fixed person is defined to be coordinater and interface to logistics. | One interface person handle all the issues with the TA parts, checking status, transportation or quality feedback. Defined responsibilties and strictly follow in BS team. | 1.Improve the efficiency of part feedback. 2.Well organize and only one window person with all information control. | Process Maturity | PP | V295
289 | Body Shop PP | PT-Phase |  | RD rework WI | Process | RD rework WI regarding the new tech. scantech, Aluminum welding delay too much and impact the onsite work. | No planning in advance from RD. | Escalate the new technology rework WI in LOT phase and require RD to finish WI before PTs start. | It will benefit production to rework the onsite parts and make the rework training more earlier. | Process Maturity | RD | V295
290 | Body Shop PP | PT-Phase |  | EC(CR) | Organization | Information transfer of EC(CR) is not timely from design phase so that many members don't know the EC and don't prepared for the EC. | Information transfer is not timely and less specified responsible person. | 1.With the AMEA system,overall control the EC; 2.Organize regular meeting with RD to clear the EC; 3.Determine the responsible people of EC for every areas | Avoid forgetting the EC and finish it on time. | Process Maturity | PP | V295
291 | Body Shop PP | PT-Phase |  | EC | Process | Some ECs will be implemented in longer time period, even after SOP. But sometimes PS/AS expect to implement it more earlier to improve the quality and reduce the onsite rework. | 1.Not feedback the implement timeline requirement to Daimler RD from production side; 2.Not consider the special case in BBAC, sometimes the Ecs will be implemented global wide. | 1.Enough communication and discussion with PP/production/RD to finalize the implement date; 2.Expect RD department could release the Ecs with special timeline in different plant. | 1.It will help onsite EC implementation more efficient and reduce the argument for the EC timeline. | Process Maturity | RD/PP | V295
292 | Body Shop PP | PT-Phase |  | Spare part | Part | PP spend too much unnecessary energy to frozen the spare parts list with TSS, they are more focusing on the list; sometimes they preper to buy local spare part with less budget, but actual the prices are already defined in contract. | Spare part is used by TSS but PP is responsible for the spare part list. | 1.Discuss the possibility if the 3% budget of spare parts could be moved out of contract, and transfer the budget to TSS; 2.Define the responsibilitybefore awarding with TSS, TSS should be totally responsible for spare part list frozen and track the purchase process. | 1.Reduce unnecessary workload of PP and accelerate the spare part purchase; 2.Benefit for TSS to buy some spare part from local. | Timeline | TSS/PP | V295
293 | Body Shop PP | PT-Phase |  | Training | Organization | Production/TSS don't have enough manpower to attend the training of new technology and knowledges in EVA2 line, so that the effectiveness evaluation is insufficient, lead to poor running of EVA2 line even still handle by supplier during PT2. | Not enough manppower support from production/TSS due to HPV limited in EVA2 line. | 1.Do the training plan in advance to avoid production/TSS don't have enough time in the plan of training; 2.Organize training for many times, people on day work and people on night work should be training separately; 3.The people who attend the training need to sign the training effect, and take the exam to make sure the training result is OK. 4.Check if the mnapower could be planned in advance. | 1.Ensure all the members to get the training knowledge. 2.Make sure the line could be running smoothly during PTs phase and coming SOP. | Process Maturity | PP/TSS/Production | V295
294 | Body Shop PP | PT-Phase |  | Documents | Process | 1.The handover documents from supplier is not accurate, especially for the fixture/simulation modified onsite because of EC or cycle time adjust. 2.PP/TSS can not check the detailed documents because limited timeline. | 1.Too many changed happened onsite and did not transfer from supplier onsite team to design team, lead to poor documents accuracy. 2.PP/production do not have the tools and software to check the fixture/simulation. 3.Not check document carefully enough. | 1.Supplier should double check the handover documents internally and transparent information exchange between onsite team and design team. When the process change, the document should be corrected on time; 2.BBAC local PP must leave enough time and effective tools to check the document to avoid finding mistakes after final buyoff. | Ensure the accuracy of document and avoid causing unnecessary problem in series planning | Process Maturity | PP | V295
295 | Body Shop PP | PT-Phase |  | Meeting land scape | Organization | There are too many meeting land scape, such as core meeting, Milestone readiness Meeting, EVA2 weekly meeting, pre-task meeting, iPR pre-meeting, etc. Pay so much time to attend meeting and some of the meetings make no sense because of no topics sometimes. | 1.There was no overall planning for the meeting. 2.Too many meeting in different level and BBAC/Daimler side requirement. | 1.To reduce some unnecessary meetings or consider to combine some of them together. 2.For some common problems, we can arrange for a representative to attend the meeting, and transfer the content to other people. | Save time and improve work efficiency. | Process Maturity | PP | V295
296 | Body Shop PP | PT-Phase |  | SLT | Equipment | SLT Quality of PT batches can't reach the requirement.The dimention of SLT is out of tolerance, which influence the process of gripper putting parts, even intervene with gripper | SLT quality delivered by supplier not according to defined delivery standard | New process to ensure quality of incoming SLT batches needed, for on-site checking process was installed, further development of process for upcoming car models | BS SLT delivered to robot station in right quality | Process Maturity | Logistics Planning | V295
297 | Body Shop PP | PT-Phase |  | Monitering system | Process | Not all monitoring system like spot welding UI, quiss and vitronic could be ready during PT2 phase according to planning, backup solution will be support from production onsite manual check. | Monitoring system commissioning is not considered with risk delay. | 1.Take the monitoring system within consideration under whole timeline planning; 2.Clear defination in ECM standard when the monitoring system could be ready to reduce the arguement. | Accelerate the project schedule and reduce the argument. | Timeline | PP | V295
298 | Body Shop PP | PT-Phase |  | Supplier management | Organization | Supplier pushed hard on individual issue,such as gap issue which cause welding spatter very large and not easy to solve quickly. | 1.There is no effective means of the constraints of the supplier; 2.The issue may be out of the contract and could be solved by supplier because of part issues. | 1.Understand the supplier's demands; 2.Make purchasing involved, put pressure on suppliers from the business contract; 3.If the problem is out of contract and does not affect the normal use of the line,communicate with the introducer and close the open issue. | Improve the management of supplier and speed up problem solving | Process Maturity | PP | V295
299 | Bodyshop Production | PT-Phase |  | Shortage of Commissioning Parts for Q Loops | Production | Rebalance the usage of commissioning parts between PP & Production. |  | Realignment workshop for part usage and update part supply program |  | Process Maturity |  | V295
300 | Bodyshop Production | PT-Phase |  | Timeline | Timeline | Officials cars production start too early |  | Before Officials cars production start need give more time for DT& CMM to get result |  | Product Maturity |  | V295
301 | Bodyshop Production | PT-Phase |  | digital tools | Equipment | Condition monitor system not ready |  | Condition monitor&SME and other tool should be used in PT phase |  | Product Maturity |  | V295
302 | Body Shop PP | PT-Phase |  | Project management | Organization | The decisions on weekly morning meetings are often forgot or denied after a long time. | 1.Make the decision on the meeting, and no meeting minutes sent out. 2.Production/TSS who join the weekly meeting always change because of manpower limitation, the new collegue will deny the decision sometimes. | 1.Organize regular meeting with process/TSS/dimention/production; 2.After meeting, send out the important meeting minutes on time; 3.When send out E-mail, we should copy it to production/TSS leader to make sure they are involved in the decisions and even new collegue comes, they also will know the decision quickly. | Ensure that every decision can be implemented | Timeline | PP | V295
303 | Paint Shop PP | PT-Phase |  | E-coat runners | Product | V295 has a lot of E-coat runners at door edge, hinge, trunk lid edge, B-pillar, rear tri-angle area | Body shop glue filling issue | Body shop need optimize the BS-glue from beginning. PS need feed back the E-coat runners as early as possible. |  | Product Maturity | Pilot Plant | V295
304 | Paint Shop PP | PT-Phase |  | Spot repair IR lamp baking | Product | V295 bottom of B-pillar metal panel could happen dent in under IR lamp baking with 140C/22min. | the dent in issue happned in Bremen also. Root cause could be the side wall panel issue. It is not identified by RD | when new model come in PS, need test this dent in issue with IR lamp baking first. |  | Product Maturity | Paint Shop PP | V295
305 | Paint Shop PP | PT-Phase |  | 842 Sodalith Blue | Product | this color is two direction color. The body color data is in the OK range with Yellow direction. The bumper is in Blue direction. Then the color match is COK. | VBT does not give the color direction, both directions are OK. Could happen diviation between Paintshop and supplier | Workshop for the special case needed to get a aligned direction for all relevant party |  | Process Maturity | Paint Shop PP, QM, MP | V295
306 | Paint Shop PP | PT-Phase |  | QL3 Audit time | Audit | CC/Lot4/PT1 phase, the production time in PS is 5 days for production, for delivery date is tight. | need 100% Audit, but the day by day plan does not conisder QL3 Audit time. | Day by day plan need consider additional 1 more day for QL3 Audit. |  | Process Maturity | AK Ramp-Up | V295
307 | Paint Shop PP | PT-Phase |  | FAD PVC nozzle | Equipment | QM complain the FAD PVC nozzle appearance is not so smooth | FAD is different application technology with Swirl. FAD has more limitation area than Swirl. | FAD is not comparable with Swirl. PP can only try the best to optimize appearance from early phase.We need align a Q-Standard earlier |  | Product Maturity | PP-PS QM | V295
308 | Paint Shop PP | PT-Phase |  | TC Skid design | Product | TC skid pick up points has a very small gap with V295 bottom. | FP define the pick up point is locked between X247 and V295. cannot make this gap bigger. | Need FP define a flexiable pickup points for future models |  | Process Maturity | Facility | V295
309 | Paint Shop Production | PT-Phase |  | V295 Water flap and charging flap poor appearance | Product | Marks and loss of gloss on the outer surface | Material defect | After the issue occurs, find the root cause, feedback to the responsible department, promote the responsible department to solve this defect | It will help us to solve water flap/charger flap issues more quickly | Product Maturity | QMP/RD | V295
310 | Paint Shop Production | PT-Phase |  | PVC Q-Stop | Process | The 295 model cannot be continuously produced | Too much PVC brush point | Optimize the PVC robot program, reduce the manual brush points as much as possible, improve 295 production efficiency | Improve 295 production efficiency | Process Maturity | PP | V295
311 | Paint Shop Production | PT-Phase |  | E-coat runner | Process | After ED oven the body has too much E-coat runner, affect the quality | The hemming process isn't perfect | Push Body shop to adjust the hemming process and BS glue process, Paint shop to adjust the oven temperature curve | Improve 295 production efficiency and quality | Product Maturity | Body shop PP | V295
312 | Assembly PP | PT-Phase |  | Issue tracking | Organization | Station Readiness System and Process difficult to implement to actual working structure and access to the SRA system. To many different Tracking systems. |  | Issue tracking list and priority topics in SFM ongoing no SRA usage from CC on for readiness check of production and issue tracking for X294, also implemented in V295 |  | Process Maturity | PP, Production | V295
313 | Assembly PP | B-Phase |  | special tools | Organization | further transparency and communication of special tools (calibration, WI, verification, back up processes). Handover to production |  | Earlier involvement of production in the status report to pilot plant for X294. Start translation for WI earlier and share to production. Handover to production earlier | PP,Production, Pilot Plant | Process Maturity | PP | V295
314 | Assembly PP | B-Phase |  | Commissioning | Part | parts availability (delay) and bad conditions of TA/TS, communication and alignments with all departments for tests onsite in advance – PP and pilot plant |  | Closer tracking of TA and commissioning cars from PP side. Detailed plan for Commissioning onsite for X294 | PP | Process Maturity | PP | V295
315 | Assembly PP | PT-Phase |  | Equipment Back up processes | Process | missing clear communication to production with back up process |  | Share and communicate the back up process more active in earlier phase | production | Process Maturity | PP | V295
316 | Assembly PP | PT-Phase |  | Equipment tact time diagrams check | Process | Discussion if equipment can reach the tact time or not, and comparison to the available AVOs |  | The input tact time diagramm from supplier need to be checked earlier and fit to the AVOs |  | Process Maturity | PP | V295
317 | Assembly Production | PT2 |  | quality standard clarification | Organization | quality issue standard clarification with VoCa | objective & clear standard should be clarified to AS Q-loop by VoCA | regular meeting implemented | avoid to redundant quality complain, decrease the rework | Product Maturity | AS/QM | V295
318 | Assembly Production | PT2 |  | process switch | Process | line process switch and internal training (including audit) should have a good coorperation | AS internal training & audit (2nd skill) are almost finished, after line switch the skill have a big step drawback | AS should know the detail of line switch, PP can inform in advance | avoid the internal training wasted and audit plan delay. | Timeline | Assembly PP | V295
319 | Assembly Production | PT2 |  | special tools | Process | special tools issues finding & optimization should be done as soon as possible | quality issue happened due to the defect of special tool. (arrival time delay, optimization slowly, when the loading amout are rising, many quality issue caused) | 1. special tool or equipment should arrive in advance 2. risk point perdiction 3. IRA quick response |  | Product Maturity | Assembly PP | V295
320 | Assembly Production | PT2 |  | rework parts storage | Part | no parts for rework waiting parts to handover, especially for autoshow cars | no backup part ordered | 1. risk parts prediction 2. parts ordered for rework | reduce the rework (parts waiting) time, handover on time | Timeline | AS/LOG/RD | V295
321 | Logistics AS Planning | PT1 |  | Pick by Light | Process | Pick by light not running during first vehicles | - Late changes - Port80 - OneGuide Error if part on Picklist not maintained as storage bin | - Maintain all parts as storage bin - Update subzones - Maintain all parts as early as possible and then react to changes instead of waiting for the last TEO from PP |  | Process Maturity | LOG P CoC | V295
322 | Logistics AS Planning | PT1 |  | Missing Parts in Picking Zone | Part | Parts that are on the pick list are not in the picking zone | - Late changes - Dialog information unclear | Manually maintain all parts as storage bin as far as available |  | Process Maturity | Logistics Production | V295
323 | Logistics AS Planning | PT1 |  | Small Parts (Suxi Parts) | Part | Small parts are listed as normal parts and vice versa | Wrong input from Dialog/PP | Manually maintain all parts as storage bin as far as available, step wise improvement afterwards |  | Process Maturity | Logistics Production | V295
324 | Logistics AS Planning | PT1 |  | Smallest Pre-Assemblies | Process | Production expects smallest pre-assemblies which were refused | Information about accepted/refused not forwarded by PP to Production | - Training of LSP - Printout of Instructions - Clear handover document to PP |  | Process Maturity | LOG OPS | V295
325 | Logistics AS Planning | PT1 |  | Shopping Cart Positions | Process | Downtime due to parts not found on SC | Insufficient input by PP | - Picking of first vehicles together with PP - Updates of SC Positions from PP - Rework of SC by PP |  | Process Maturity | PP/SP LOG P | V295
326 | Logistics AS Planning | PT1 |  | KSP | Process | Production takes parts off SC to assemble KSPs. Parts were handed over to Production prior to line feeding | - No “line switch” for KSP by PP - V295 KSPs not assembled in sequence | - PP needs to clearly define KSP processes before PT1 |  | Process Maturity | PP/SP | V295
327 | Logistics AS Planning | PT1 |  | Manual Check | Process | Production asks for SC check in advance, picking in sequence not possible. Parts get lost in the process Results in manual work for Log Operations with HO List + Signature | - Bad SC input by PP - Parts availability of first PT1a car | - Pick SC in Sequence |  | Process Maturity | LOG OPS | V295
328 | Logistics AS Planning | PT1 |  | EX33 Parts Lineside | Part | There are still many EX33 parts which are managed by ramp up team and go directly lineside | - Late changes - Non Series Status | - Maintain all parts as storage bin - Maintain CCs for non-series parts |  | Process Maturity | LOG P CoC Ramp up | V295
329 | Logistics AS Planning | PT1 |  | KLT Push Buttons | Process | KLT push buttons don’t work | - Production is moving complete rack from one line to the other - Production is changing KLTs from on rack to another - KLTs are planned to already occupied storage bins | - No more maintanance of Push Buttons for PT1 |  | Process Maturity | PP/SP Prod. | V295
330 | Logistics AS Planning | PT1 |  | CH3/CH4 | Process | CH3/CH4 lineside completely different as previously planned | - Line switch as planned by PP was not accepted by Production - Over night, all changes were revoked - No space for V295 parts - H473Processes and fitment points change on daily basis | - New planning for PT1b - Clear line switch - Delivery of CH3+4 with line feeding list for PT1 |  | Process Maturity | PP/SP Prod. | V295
331 | Logistics AS Planning | PT1 |  | New BoM V3 released 5 days prior to PT1a | Process | - Logistics respected BoM freeze as aligned RD, PP and Production continued with latest BoM version - New parts have no master data - Old parts are supplied to line | - Disregarding aligned BoM freeze - LOG declined supplying the new parts - Part supply should have been done by Ramp Up team but was not informed by PP | - Accept late changes - Setup of process to quickly implement changes when they come |  | Process Maturity | Logistics Production | V295
332 | Logistics AS Planning | CC |  | Small parts for CC+LOT4 | Part | Small parts are normally delivered on SC. For CC+LOT4, there is a counted quantity for all small parts. With distribution on SC, parts get lost | CC+LOT4 not in Series condition, picking in specific area. Too much manual effort | Deliver Small parts in Batch to Production for CC+LOT4 |  | Process Maturity | Logistics Production | V295
333 | Logistics BS Planning | PT-Phase |  | No press parts in system | Part | No press parts in system. Implementation of manual processes for new production building necessary. No LOG series process possible until SOP. | press parts in system 1 month before SOP. - no chance to test the system before - alu washing process can not be tested - printing process at HOP stations can not be tested |  |  | Process Maturity | Press Shop PP | V295
334 | Logistics BS Planning | PT1 |  | MRP area | Timeline | MRP area not ready | integration of MRP area took longer than expected | prepone warehouse customizing in the planning timeline |  | Timeline | Logistics Production | V295
335 | MOE | PT1 |  | BMS Vedoc data missing issue | Process | Vedoc data missing from BMS ECU | HV battery issue | Already aligned to run full EOL test for all rework battery, never allow PLC engineer to use EKS key for series production, PP and Production | Make sure vedoc data always valid from BMS ECU. | Process Maturity | Battery Plant PP | V295
336 | MOE | PT1 |  | BMS connector installation issue | Process | No high voltage measured at control unit 'EPT20INV2'. HV system cannot be activated. | Assembly issue | SOMA: Fixed 2 affected vehicles and perform HV commissioning again. LAMA: RD3 transfer further training to SY AS./Change product design(Material/Edge, June/July, 2022). | Improve assembly process | Process Maturity | Assembly PP | V295
337 | Press Shop PP | B-Phase |  | Secondary data for front and rear door inner | Process | Risk unstable Body Shop process and water leakage | Without the implementation of the secondary data in the press part the ZB will be too much outboard | Future projects with door window frame like F294 must have the secondary data (overbending) in the door development process included. Check in the MO-TESTAT. | vehicle and process quality | Product Maturity | Body Shop PP | X294
338 | Press Shop PP | B-Phase |  | Liftgate upper and lower welding surface issue | Process | Curling at end of the flange caused an unstable welding process in the Body Shop. | Flange design issue | Set additional measuring points at the end of the flange to see accurate values. Reduce the clearance of the flange steel. Flange design for F294 will be changed in the future by R&D. | Part quality | Product Maturity | PP ST, PP BS, MP, RD | X294
339 | Press Shop PP | B-Phase |  | Sidewall opening flange waviness | Product | Waviness is visible for the customer caused by the method | Flange method | Adjust the method and die design in the early phase (design phase). | Part quality | Product Maturity | PP ST, supplier (design phase) | X294
340 | Press Shop PP | B-Phase |  | Alignment issue (Tail light opening too small) | Process | Opening too small, gap and transition out of tolerance. Prio 2. | Insufficient communication flow | Clarification in the early phase about the local alignment STFP calculation base. Deviation between local alignment and net results in the cmm report. STFP not stable in Body Shop. |  | Product Maturity | BS, PP ST, CMM, pilot plant | X294
341 | Body Shop PP | B-Phase |  | Integration windows | Process | The alignment integration windows cannot be kept and followed. Program planning is quite chaotic. | unstable production program overall issue | Further discussion to keep the night shifts & weekend for X294 commissioning. For F294, project needs to confirm the integration windows for weeks, night shifts and shutdown days. E1/E2 confirmation for RFQ documents | BS integration in time | Timeline | Body Shop PP | X294
342 | Body Shop PP | B-Phase |  | R&R Design failures | Organization | Product issue, HSN distance, glue clarification should be raised and resolved | Communication & process | Align with Pilot Plant R&R to be responsible for Design issues till they are solved/released in general till Code 18 release.Pilot Plant is responsible for the design issue tracking | Part quality | Product Maturity | Pilot Plant | X294
343 | Body Shop PP | B-Phase |  | IT commissioning not enough capacity | Process | PFM, Buffer commissioning delay RDS transfer PLUS delay | Communication | Expect more experts for IT commissioning | IT commissioning to be finished in time | Timeline | IT | X294
344 | Body Shop PP | B-Phase |  | Q-Loops from Press shop | Process | Long decision phase of improvement needs press parts Clarify premise in advance | CMM capacity issue | Only with more cars (PT1-results) changings needed not according to CAD. PP-Press need to improve Press-Parts according to single part CMM report to green in general. | Part quality | Product Maturity | PP ST | X294
345 | Body Shop PP | B-Phase |  | Limited man power | Organization | Production & TSS achieved all tasks with high effort and limited Manpower for EVA2 Lines during B-Phase | Limited man power | Already Increase additional HC for the PT1-PT2 Expect more People for F294 B-Phase& Ramp UP Meeting participation can be promised. | more transparency expectation on stable process | Process Maturity | Production/TSS | X294
346 | Body Shop PP | B-Phase |  | Logistics MHD Mobsy some function not ready | Process | Logistics MHD Mobsy some function not ready | comminication | For F294, Logistics server should be ready before LOT3 production. | Availability of all LOG functions | Process Maturity | Logistics Planning | X294
347 | Paint Shop PP | B-Phase |  | Sample Jigs availability before B-phase | Process | EX33 cannot deliver sample jigs at beginning of B-phase. Especially for PVC hood and trunk lid jigs. Start local jigs development from B-phase start. | Communication & process | There is no sample PVC hood/trunk lid jigs from EX33. Local development and continue testing during PT1. Continue testing local AFA plug-chain. All others jigs are ready For F294, project needs Provide the jigs concept before B-phase start. | Jigs availability | Process Maturity | Paint Shop PP | X294
348 | Paint Shop PP | B-Phase |  | E-coat runners | Product | X294 has a lot of E-coat runners at door edge, hinge, trunk lid edge, B-pillar, rear tri-angle area at B-phase | Process & quality standard setiing | BS did some optimization of BS glue, continue monitor and record the status of E-coat runners. Check the 3D data from RD, check the body runner status as early as possible. | Less rework effort | Product Maturity | Paint Shop PP, Bodyshop PP | X294
349 | Paint Shop PP | B-Phase |  | Spot repair IR lamp baking | Product | X294 bottom of B-pillar metal panel could happen dent in under IR lamp baking with 140C/22min. | Wrong temperature | Optimized based on the experience of V295 Put Spot repair IR lamp baking test as a standard | Quality | Product Maturity | Paint Shop PP | X294
350 | Paint Shop PP | B-Phase |  | Color Release | Process | 842 (blue) color match shows difference between device measurement and visual, analog V295 | Process | Make the alignment with Q-loop 3 for the color direction for new colors; Ask the paint supplier to adjust the parameter. For difficult color, make color direction alignment with Q-loop 3 as a standard | Color match | Product Maturity | Paint Shop PP, QM | X294
351 | Paint Shop PP | B-Phase |  | WAX nozzle collision with TC skid | Product | 2 wax nozzles has collision with TC skid MFA pick up points. | Product Reason is main floor deformation | RD cannot modify the carbody main floor. Can only modify the wax nozzle and skid. Will testing the modified skid and nozzle in PT1. Check the wax nozzle collision as a standard | prevention of wax nozzle collision | Process Maturity | PP PS, PP CV | X294
352 | Paint Shop PP | B-Phase |  | Charging flap/Star hole PVC appearance | Process | The Straight nozzle cannot reach this area, need modify PVC Robot to hook nozzle | Communication with lead plant | Start apply budget to modify the PVC Robot based on the concept of Tuscaloosa. Manual brush for PT1 Check the Robot reachability at the Lot1 beginning. | Robot reachability | Process Maturity | Paint Shop PP | X294
353 | Paint Shop PP | B-Phase |  | Body deformation | Product | Main floor deformation at skid pickup points area B- pillar bottom deformation after PVC oven | Product design | Main floor deformation is accepted by RD, brush wax for the pick up points. B-pillar bottom area, continue investigation during PT1 Check the body deformation at Lot1 as a standard | Quality | Product Maturity | Paint Shop PP, RD | X294
354 | Assembly PP | B-Phase |  | Equipment try out in pilot plant | Equipment | Successful test of AD ATC for process improvement before first installation in Plant |  | Try out to get good knowledge for the assembly process, that leads to a stable process already for CC/LOt4 in the plant. In next project for critical process, use b phase for first try out | process stability | Process Maturity | PP AS, Production, pilot plant | X294
355 | Assembly PP | B-Phase |  | Special tool | Process | successful implemented verification process between production, pilot plant and PP |  | Use the established process for all projects | Availability of special tools | Process Maturity | Assembly PP | X294
356 | Assembly PP | B-Phase |  | Commissioning parts | Part | parts availability and conditions of TA/TS better compared to V295, but still close communication and alignments between PP and pilot plant for future |  | Close tracking of TA and commissioning cars from PP side in each project required. | Availability of commissioning parts | Process Maturity | Assembly PP | X294
357 | Assembly PP | B-Phase |  | Process | Process | Process verification result with OK ratio is reported by pilot plant, but for Hard assemble issue is not fully identified and tracked. | process setting and unclear R&R | Identify hard to assemble issue and open ZEUS point | more transparency info flow | Process Maturity | Pilot Plant | X294
358 | Pilot plant | B-Phase |  | B-phase body production number creation | Process | B Phase body number long term solution and clear process need to be defined. | dummy order creation process not clarifed | ONLY manual corordination is valid in every project, project could running, but requires lots of additional efforts. | gain efficiency | Process Maturity | Bodyshop PP, LOG | X294
359 | Pilot plant | B-Phase |  | Blue colar manpower support alignment process | Process | Blue colar manpower support shall be supported by Shunyi production due to limited operators and parallel projects in 192. | process and communication issue | A clear alignment process is needed for future Shunyi projects. | smooth work coopration | Process Maturity | IE (industrial engineering), Target Plant, Pilot Plant | X294
360 | Pilot plant | B-Phase |  | Special tools status transparency | Process | Special tools status not transparency enough | process and communication issue | Special tools still improvement possible. Further delivery status needs to be more transparent and early warning. | enhance the info transparency | Process Maturity | Assembly PP | X294
361 | Pilot plant | B-Phase |  | Part delivery and order process cause vehicle and TA handover delay | Part | Part delivery and order process | process and communication issue | Regular part tracking meeting with relevant dept. for delay parts. Part miss order shall be avoided to ensure handover process. | enhance the info transparency | Timeline | LOG, RDC/ET | X294
362 | Pilot plant | B-Phase |  | Import part quality control and delivery control process | Part | quality not good, and delivery process lack of transparency | process setiing | Import part quality and delivery should have a transparent and control process | enhance the info transparency in order to recall the quality issue | Product Maturity | LOG, MP | X294
363 | Launch and change MM | B-Phase |  | CPL1 failure with late notice | Process | during LOT4 & PT1, some CPL1 parts are failed to be handled via CPL1 process. This information was provided days after the MRD @ BBAC which does not leave enough lead time for implementing countermeasures. | process and communication issue | In checking with CPL1 availability, not only supply status between China and Germany side will be checked, the Germany side and its suppliers’ supply status shall also be checked to prevent similar situation happened at X294 PT1 which the supplier refused to send out CPL1 parts due to obligation reasons. | transparency info help better reaction to the dynamic status | Process Maturity | WTO series | X294
364 | Launch and change MM | B-Phase |  | CCC process delay caused parts scraping | Process | Before CC, since the CCC process is not finished. Some parts (i.e. headlamps) have to be retrofit afterwards with CCC qualified parts, which leads to extra effort and cost. | PROCESS | CCC application milestones shall be defined, monitored and recorded on the timeline. | guarantee on-time delivery | Timeline |  | X294
365 | Launch and change MM | B-Phase |  | LOG timeline adjustment due to global supply chain instability | Timeline | As the instability of global supply chain under current situation, the lead time for material flow is visibly increasing. And shortage situations are more frequent than the period when LOG timelines were aligned. This leads to a high chance to postpone the production. | instability of global supply chain | As the increase lead time of material flow and shortages on many critical components, an adjustment of LOG timeline is recommended to further ensure the parts availability. In general proposal for future projects under long term supply chain disruption. | stable ramp up | Process Maturity |  | X294
366 | RLM | B-Phase |  | Q loop feedback before customer car | Timeline | Very small time gap between Lot4 & PT1, which lead hard to get complete Q loop feedback before customer car | program and ramp up setting | Adjust PT1 loading plan to add additional Q loop based on VOCA result out of Lot4 Ensure Q loop time in timeline | benefit to a better Q feedback | Product Maturity | AK Ramp-Up | X294
367 | RLM | B-Phase |  | many projects in parallel | Timeline | CC / Lot4 cars loading parallel with other new projects (V295 C2 / V295 SOP / X247 MY) | global project overall issue | Balance the new project timeline in early phase |  | Timeline | AK Ramp-Up | X294
368 | RLM | B-Phase |  | car amount & usage | Process | CC / Lot4 car amount & usage hard to meet the requirement, production training car amount min 3 cars as basic requirement | project preliminary planning not precision enough, always have additional demands pop up in the procedure | Increase CC/Lot4 car amount （also need to consider MDS future） | ensure production training maturity | Process Maturity | WPL | X294
369 | Body Shop PP | PT-Phase |  | NTP Integration Time | Process | No enough integration and commissiong time on the series line, especially on the servaral model combined cell, there is no time left for supplier cycle time optimization and commissioning. | 1. Unstable production system; 2. Conflict between series production and new type integration; 3. High volume required for series line. | 1. Integration window should be aligned with all parties as early as possible even in design phase and high level; 2. Production control should be informed and aligned, and commissiong plan can be considered and arranged. |  | Timeline | AK Ramp-Up | X294
370 | Body Shop PP | PT-Phase |  | PFM | Process | PFM SOA order for DT/CMM/Performance test, etc. need to be checked and deleted ontime, otherwise SOA will occupy the DFZ and impact the series production and following commissioning. | Commission flexibility and uncertainty lead to some SOA can not be finished at the same time, then occupy the DFZ areas. | Set up the weekly meeting to track the finished SOA and feedback to IT to delete ontime. |  | Timeline | BS PP / IT | X294
371 | Body Shop PP | PT-Phase |  | Commission Parts | Part | No separated storage area defined for project, lead to NTP commission parts and cars were moved many times because of 5S and visiting requirement | Shop areas function not defined. | Storage areas should be aligned with production before commission phase start. |  | Process Maturity | BS PP / Prod | X294
372 | Body Shop PP | PT-Phase |  | IT RDS | Process | There was no Halldata for torque in RDS for X294 & V295, all the points need manuel maintane, which can cause the false data tansfer and output Process sheet with wrong/missing information. At the same time there is no data transfer between RDS & PLUS for torque, therefore we need configure the PLUS and also RDS twice. | No Halldata for torque and no connection between RDS & PLUS | For 3rd cartype, communicate with Daimler IT to set up the Halldata for torque in RDS, and perform the data transfer between PLUS and RDS like other joining technology. |  | Process Maturity | BS PP / IT | X294
373 | Body Shop PP | PT-Phase |  | SLT Commission | Process | LOG SLT part labels not in the right position or lost during PT1/PT2 phase, and then station barcode reader can not read the part information and lead to many line break down. | SLT part label position and tolerance not be strictly follow and carry out. | Label position and tolerance should be clarified and defined with LOG planning during design phase, part supplier should follow and finish during LOT commission. |  | Process Maturity | BS PP / LOG PP / LOG Operation | X294
374 | Body Shop PP | PT-Phase |  | EC Management | Process | NTP product EC: no clear process and responsibility, only series EC engineering change process can be found in BBAC. | NTP product change can not be transfer to BBAC RD ontime before SOP | Share with production/TSS/QM EC information before every PT phase and make sure all the changes have been carried out. |  | Process Maturity | RD | X294
375 | Body Shop PP | PT-Phase |  | Spare Part | Part | TSS spare part test on the series line can not be well organized and performed, especially which one impact the carbody quality. | TSS equipments spare parts ordered in LOT phase and arrived during PT phase, the tryout and exchange will impact the series line. | 1. Try to frozen the spare part list during design phase; 2. Push the supplier to delivery the spare part in LOT phase and leave more time for TSS to test them. |  | Product Maturity | Body Shop PP | X294
376 | Body Shop PP | PT-Phase |  | Technical documents | Process | Customer required additional technical documents out of ECM standard, supplier need to pay more effort and ask the cost for the requirement. | The technical documents not according to ECM. | 1. Align with customer for the technical document content; 2. Put the document templates in the ECM before awarding. |  | Costs | Body Shop PP | X294
377 | Body Shop PP | PT-Phase |  | Training | Organization | Equipment training requirement frozen during PT ramp up phase, it is hard for supplier to organize the sub-supplier come onsite when we start to produce the offical cars. | 1. Training was not realized its importance; 2. Line owner should start mangement the equipments more earlier. | 1. Try to frozen the training list during design phase; 2. Track and push the supplier to finish all the training before PT1. |  | Process Maturity | Body Shop PP | X294
378 | Bodyshop Production | PT-Phase |  | Dimension | Process | there have some G/F issue in AS, example the hood fitment to fender and front bumper, the transition is not very good | BS engineer focus the points different with AK team | Commissioning, need talk the key points with AK team and focus on it Official car, need double check the body CMM status with AK team before send it to PS |  | Product Maturity | BS Prod / AK | X294
379 | Paint Shop PP | PT-Phase |  | Main floor deformation | Product | Main floor deformation at skid pickup points area, influence skid clearance between skid MFA support point and car bottom. | Main floor only one single layer metal sheet, not strong enough. deformation is accepted by RD, brush wax for the pick up points. | Check the body deformation at Lot1 as a standard; brush wax for the pick up points. B-pillar bottom area, this is a design issue, feedback to RD. |  | Product Maturity | RD | X294
380 | Paint Shop PP | PT-Phase |  | B-Pillar bottom deformation | Product | During PT1 TC Audit, found B- pillar bottom deformanced. After investigation, found X294 run through PVC oven, will get deformation, run through TC oven will get worse. | There is no reinforcement structure at B-pillar bottom area, it is different with V295. | RD creat a EC based on the testing result to make a reinforcement structure at B-pillar bottom area. ST Shop finish the DIEs modification before PT2. feedback to RD to update the structure for F294. |  | Product Maturity | RD | X294
381 | Paint Shop PP | PT-Phase |  | PVC Jigs development | Process | No PVC hood and trunk lid jigs sample from EX33. hood/trunklid get Robot camera alarm. | Bremen or Tuscaloosa, the hood/trunk lid is opened by Robot, there is no jigs available. | For F294, project needs Robot supplier define the the jigs concept for BBAC. And we need get 3D model ealier(Could be E-version) and send to supplier.Start local jigs development from B-phase start. |  | Process Maturity | PP | X294
382 | Paint Shop PP | PT-Phase |  | PVC Applicaton for S-Pillar Front Door | Process | The appearance is not be ensured as there is fold which is not accepted by Q-loop. | The issue is caused by body shop glue in this area.If there is too much body shop glue, there will be folds on the PVC. | Body shop glue quality control is the cooperation job between BS & PS.We should share the PVC quality status of special area and give the direction of optimization for BS. |  | Product Maturity | PP | X294
383 | Paint Shop PP | PT-Phase |  | PVC Manual guns choosing standard | Process | X294 front door manual gun suggested by leading plant is not handy to use in Shunyi plant. After testing , found one V253 nozzle is more suitable to apply this sealer for X294. | Due to difference of PVC manual station height between Tuscaloosa and Shunyi. | Need to comprehensively consider issues. No need to completely copy experience from leading plant, we can think more combining with actual situation. |  | Process Maturity | PP | X294
384 | Paint Shop PP | PT-Phase |  | Rock panel missing wax | Process | Inside rock panel missing wax, increase wax volume from 20ml to 80ml for PT2 phase. | AP70/25 wax has higher viscosity; this area 2 wax nozzle need to be modified for these screw. | Wax injection quality must be evaluated as eraly as possible. Feedback the nozzle designer for upgrade nozzle based on the new wax material viscosity. Expect new nozzle coule be onsite in PT3. |  | Product Maturity | PP | X294
385 | Paint Shop PP | PT-Phase |  | EC changes | Process | in PT1, AFA Robot has collision with X294 car body, cause 12 bodies are touched by Robot. | before PT1, some EC changes happened, the AFA injection holes area changed, need adjust Robot programming. But, after adjustment, do not double confirm the collision between Robot and car body, cause 12 bodies are touched by Robot. | After any Robot programming adjustment, must double confirm the collision between Robot and car body, even a slight change. Before each phase start, take one body check the Robot programming collision for PVC/TC /AFA Robot. |  | Process Maturity | PP | X294
386 | Paint Shop PP | PT-Phase |  | AFA windshield Injection | Process | AFA windshield AAW standard is 550g. While 555g is maximum injection quantity from one hole, only one hole for injection in lot 4 phase. And Injection with one hole is difficult to meet the AFA required 550g, the robot running with nearly full load. | Design issue (analog Tuscaloosa). | One hole will be divided to two holes, 285g per hole. | Reach AAW injection standard, improve AFA quality, increase the robot life cycle. | Product Maturity | Paintshop PP, Paintshop Production | X294
387 | Paint Shop Production | PT-Phase |  | Plate grinding mark | Product | X294 has 100% severe marks on the truck lid inner area. | Low roughness after grinding | The standard of the roughness of X294 truck lid inner area needs to be the same as the current V295 cars' |  | Product Maturity | MP | X294
388 | AK Ramp-Up | PT-Phase |  | Ramp-up day by day poor stabilized | Process | Ramp up day by day program plan was frequently changed | multi-factor: Parts shortage, shop readiness, pandemic etc. | Parts shortage is always the top reason impact the day by day plan stabilization, although there have some irresistible reason like pandemic, but contract issue and WTO transparency info missing was purely human-made issue; and shop readiness is not always satified (e.g. body shop stress test consecutively postponement finally caused the PT3 postponement, you could also argue the stress test arrangement delay caused by the plant overall volume inefficiency). Hereby, you are very easy to see actually the root reason is the whole ramp up system instabilized, lots of interrelated factor in the system caused we have to frenquently change the day by day plan, that eventually makes our ramp up even more uncontrolable,complicate, and low efficiency. | have to futher deep dive and figure multi-point issue, to make the info more transparent --> then make the parts ETA more predictable, as soon as we know how many parts are secured for plant we will have a quite stable plan relatively-->eventually enhance the overall ramp up quality. | Timeline | AK Ramp-Up | X294
389 | Part Availability | PT-Phase |  | Glue parts FIFO | Part | 1 batch of glue parts expired in PT2. | Glue parts first in first out principle not executed in PT2 | Warehouse implement FIFO strictly | No expired glue parts stuck in warehouse | Costs | LOG O | X294
390 | Part Availability | PT-Phase |  | Splitting parts order due to vehicle quantity change | Part | Multiple orders placed for each part demand due to Vehicle quantity change after VOI | Demand adjustment brought order quantity change which increases work load and delivery risks in parts supply chain | Vehicle demand adjustment must implement before VOI milestone in project timeline | Reduce duplicated workload and delivery risk | Process Maturity | RD | X294
391 | Part Availability | PT-Phase |  | Additional quantity ordering of Local parts | Part | Production cannot have reorder parts in time for rework/replacement | Long lead time of reorder local parts under COVID situation in China | Put addition demand of potential reorder parts in the BOM based on previous experience | Reduce the hand over risk from long reorder parts lead time. | Timeline | RD | X294
392 | Part Availability | PT-Phase |  | Late KEM implementation | Process | Late KEM implementation brings part number change which has potential delivery risks | KEM implementation time scheduling topics | KEM implementation before KEM freeze milestone in the project timeline, invole logistics at the early phase | Reduce part late change, reduce parts availability risks | Timeline | RD | X294
393 | Part Availability | PT-Phase |  | Parts availability pre-check | Part | parts cannot supply via EX33 or series for China | Parts are from leading plant elsewhere than Germany, (i.e. NAFTA parts) | Parts availability pre-check when leading plant elsewhere than Germany, (i.e. NAFTA parts) | Ensure parts available for China | Process Maturity | SC-WTO/MP | X294
394 | Logistics AS Planning | PT1 |  | Pick by Light | Process | Pick by light not running | - Late changes - Port80 - OneGuide Error if part on Picklist not maintained as storage bin | - Maintain all parts as storage bin - Update subzones |  | Process Maturity | LOG P CoC | X294
395 | Logistics AS Planning | PT2 |  | Sushi parts | Part | Sushi parts are planned by PP and Log but process is not followed | Acceptance by operations / lack of training | Training for sushi parts process | Sushi process implemented, reduced waste in operations | Costs | Logistics Planning | X294
396 | Logistics AS Planning | PT-Phase |  | reorder | Process | From PT, reorder caused by damage during production occurs quite frequently, stock cannnot fullfill the reorder in time. | RD cannot predict the reorder demand in BOM, which cause logistics cannot order reorder demand based on BOM. | Based on V295 PT1/2 reorder experience, PT3 &X294 PTs, RD can add more reorder demand for easily damaged parts. | Short leadtime for reorder, Avoid waste of manpower and material resources | Costs | RD2, LOG, Proc. | X294
397 | Logistics AS Planning | PT-Phase |  | Linefeeding | Process | PT2 Linefeeding manually. | Push bottom not ready for all line | Before Push button is ready, LOG Operation pick all parts manually. After Push bottom is finish, linefeeding way transfer to automatic. | Benefits for linefeeding parts to lineside on time. | Process Maturity | Logistics Planning | X294
398 | Logistics AS Planning | PT-Phase |  | GBP | Part | Parts had quallity issue when assembling parts. | Supplier quality issue after Q release | Let lamp unit check parts before sending outparts. | Assembly good parts without delay. | Product Maturity | Logistics Planning | X294
399 | Logistics AS Planning | B-Phase |  | Truck capacity | Process | During B-Phase, truck capacity effect 192 linefeeding. | Truck capacity not aligned within BDA | Truck capacity to be aligned between LOG Planning/192/LOG | Linefeeding on time | Timeline | LOG Planning/192/LOG LCM | X294
400 | Logistics AS Planning | PT-Phase |  | Parts availability | Part | Parts late delivery | The pandemic and the global semiconductor shortage | Track with SC/WTO earlier for risk forecast. | Report risk of late delivery. | Timeline | Logistics Planning | X294
401 | Logistics AS Planning | PT-Phase |  | TEO quality not good | Process | Parts are planned on the same location as parts of other vehicles, leading to confusion and a lot of manual work for logistics to find solutions | Manual planning and data hand over to logistics | Usage of iLOG for future vehicles (available beginning of 2023) | Integrated planning | Product Maturity | Logistics Planning | X294
402 | Logistics BS Planning | PT2 |  | Hood Oven LC | Equipment | LC for special process not ready for PT1 (Baking process) | start too late, material quality not good | planning according the project milestones | series process ready for PT1 | Process Maturity | Logistics Planning | X294
403 | AK | B-Phase |  | Front area BIW adjustment points JES | Process | For front area, Hood to fender, fender to body, liftgate to SW, fixation and adjustment method and standard should be described clearly in JES or SMP | BS always do not know how to prepart a qualified Z3 setting in PT phase, and cost much time to optimize. | 1. BS sent blue colar to Pilotplant to discuss and learn how to instal and adjustment; 2. PP side should also arrive in Pilotplant to check new carline, and add more details to JES, and also arrange training to BS colleague; | 1. Ensure high quality with high effciency 2. Lower rework resource cost | Product Maturity | BS PPBS | X294
404 | AK | PT-Phase |  | Important parts tryout in BIW directly | Process | Important part (FEM, tailamp, rear lightband, bumper etc.) can tryout in BIW directly, For BS and part supplier, they can clealy understand the BIW status and optimization direction; | If no tryout, only BIW arrive in AS, can we know the vehicle status. It always too late and result in many FTC issues | Every phase (PT1-PT2-PT3), arrange one set new status parts to BIW tryout (Just like the Cubing workshop) | For BS and part supplier, they can clealy understand the BIW status and optimization direction; | Process Maturity | I do not know who can responsible for it. | X294
405 | QM | PT-Phase |  | Reaction plan implement in PT's | Process | Issues found by Q-sensor during PT phases didn't follow the reaction plan requirements like series production, especially dynamic check missing | 1.Lack of quality awareness, understanding and execution of reaction plan, especial production group leaders, Q-gate and GFP 2.Issues are not systematically recorded and feedback with system, such as PLUS, Q-Live | 1.Production should enhance the quality control and improve the quality awareness training according to reaction plan, and process audit should check the reaction plan implement status during PT phases 2.Establish systematic tracking and recording methods | Identify batch issues timely and detect more issues early to reduce the expansion of the campaign or repair scope and the impact on ramp up | Process Maturity | Production(Press Shop/Body Shop/Paint Shop/Assembly Shop) Process Audit | X294
406 | QM | PT-Phase |  | Open ZEUS handover process and B-phase findings tracking logic | Process | About 50% issues opened after handover from Pilot Plant are B-phase findings without opening ZEUS and tracking and verification not OK that need to be reopened, and Lot4 findings no tracking | 1.Lack of communication between RGA and Pilot Plant on the problem recording and tracking 2.The FRC verification process and logic is not clear 3.Lot4 new findings didn't record, track and handover 4.KPI for pilot plant improperly defined and assigned | (1) Deep dive the reaction plan referring to series production, all the issues complained by Q-sensors that need to be solved should be tracked in PSP meeting(project meeting & ZEUS Klausur) (2) Strictly control FRC process together with Q sensor (3)All the Lot4 new findings should be tracked in ZEUS Klausur (4)Handover KPI should also be taken over by IRA departments | More efficient to push the PSP | Process Maturity | Pilot Plant | X294
407 | QM | PT-Phase |  | Shortage of information with high EC-NIO | Process | The high EC-NIO issue without immediately feedback, difficult to find the issue. More PT cars are affected, also delay the issue solving process | No feedback from AS&PP | Operator also AS&PP colleagues inform the QM with high EC-NIO issue as early as possible. | Early to find and solve issues | Process Maturity | Assembly PP | X294
408 | QM | PT-Phase |  | Hemming glue quality | Product | In the PT phase, HOP hemming glue status are still not very good of X294. | Parts dimension and hemming process are not adjust properly | Should optimized the hemming glue quality eariler and faster. | improve the glue quality and maturity. | Product Maturity | PP, Production | X294
409 | QM | PT-Phase |  | Issue tracking | Process | BiW parts issue no clear MP/SQE responsible involved timely, transmission of BiW parts issue information not in time. | The interface of MP/SQE corresponding to each BiW parts is not clear | PAP audit presontation and report should involve MP/SQE colleagues as early as possible (LOT4). MP/SQE colleagues should take more attention to the PAP audit results. | BiW parts issue could be optimized at early phase | Process Maturity | QM Parts/MP/QM | X294
410 | QM | PT-Phase |  | Car status before HO for audit | Audit | PT1 RGA cars handed over to RGA without Final OK, which cause RTM not posible to activiated, also some telemetics function cannot be activiated and test. | hand over process not totally followed | From PT2 the vehicle already confirmed to HO with final OK status | So far test runs smoothly. | Process Maturity | Assembly PP | X294
411 | QM | PT-Phase |  | Pay attention to late PPAP parts | Part | Some parts has reletive late PPAP timeline, even covered with SDR AE, the critical topic could happen. (like rear seat air bag and HV PTC) | Late PPAP | frequently check late PPAP parts status | find the issue earlier | Process Maturity | MP import and local | X294
412 | AK Ramp-Up | PT-Phase |  | The LOG timeline update | Timeline | When each PT phase starting is adjusted due to some reasons, the LOG timeline should be updated accordingly. | the late update will cause the confusion and might impact part status. | Frequent checking with SC/WTO for updating. |  | Timeline | AK Ramp-Up | X294
413 | AK Ramp-Up | PT-Phase |  | Issue tracking for order customer change | Process | The new request from customer on the PT demand | ownership changes is needed in some cases. | the process for differnet type of change should be much clearer to face different situation. |  | Process Maturity | AK Ramp up, Prod. Ctrl. | X294
414 | AK Ramp-Up | PT-Phase |  | Battery change for PT orders | Process | Battery change for EQE350 orders finished in system but cannot be tracked and reviewed in tryout plan. |  | More transparent information sharing is needed to show the update. The info need to added in demand lsit and day by day plan. |  | Process Maturity | PP, AK Ramp up, Prod. Ctrl. | X294
415 | RD1 BIW | B-Phase |  | certification process of import parts to China | Process | The certification timeline for the import parts to China from EU/USA/MEX in some areas doesn't match the demand of production. This causes either additional efforts to rework parts or cannot get parts at all (example: headlamps) | timeline alignment for component certrification and importing timeline | > need to define a way how to import parts which do not have the certification yet (either adapt timeline for the certification or define process for these parts how to import) > identify critical parts and define acitons (e.g. do not offer the code in early phase) | reduced effort in part tracking/ rework | Process Maturity |  | X294
416 | RD2 | PT-Phase |  | Cross change ECs managemnet | Process | Some cross change ECs not implement in the same phase and cause rework effort | Cross change ECs implementation phase not well aligned | Change Management team will filter Cross Change ECs and inform responsible engineers One Month before ECs’ Planning Introduction Phase, to double confirm with commodities engineers, and cmmodity engineers need well aligned with each other. When cross changes parts assemble online, responsible engineers need Check Online to ensure the right technical status | Decrease rework effort caused by cross change Ecs, ensure tryout phase run smoothly | Process Maturity | RD | X294
417 | RD1 BIW | PT-Phase |  | Sidewall deformed | Product | X294 sidewall B pillar lower area found deformed in paintshop | Concept issue, too big flat surface in B pillar lower area | Need to add embossment feature to increase the local stiffness. Also need to check new carlines to avoid similar issue. | Avoid body deformed in paintshop | Product Maturity | Paint Shop PP | X294
418 | Press Shop Production | PT-Phase |  | four link mechanical sensor guide replaces laser sensor guide | Process | when producting the outer panel of front door ,the OP10 laser sensor flashes,causing the " s " line to stop. | when blank is put into the die, it's move up and down, cause the reflected light shake. Signal output interrupt. | in the future project, the door panel and other large drop parts OP10 sensor guige use four link mechanical |  | Process Maturity | Press Shop PP/Press Shop Production | X294
419 | Press Shop Production | PT-Phase |  | Gas and circuit labels need to be made before pt1 | Process | In the process of mold debugging, the location of alarm sensor and gas path system cannot be found timely and accurately, so it is necessary to test out manually | The mold has no air path and circuit identification plate before SOP | Gas and circuit labels need to be made before pt1 |  | Process Maturity | Press Shop PP/Press Shop Production | X294
420 | Assembly Production | PT-Phase |  | VoCA performance improve | Audit | Thers is no buffer between VoCA presentation and audit car delivery, some issue contermeasure haven't be acted. | not fully communication with RGA audit | align with RGA to create check buffer for issue check and rework. | improve VoCA perfermance | Process Maturity | Production, QM | X294
421 | Assembly Production | PT-Phase |  | Q-loop feedback | Audit | Internal Q-loop need monitor VoCA result and feedback to IRA and escalate more quickly |  | Update issue checklist in production system and trigger PSP from FTC | improve quality issue solving process | Process Maturity | Production | X294
422 | Press Shop PP | PT-Phase |  | Trunk Lid Upper/Lower Flange curviness | Process | Stamping method process causes flange curviness. Flange curve has negative impact in Body-Shop welding process of Trunk Lid Outer panels. | Forming process | Problem must checked in early phase during simulation. Feedback to RD for design change of Trunk Lid or change stamping method process plan, to produce parts without curviness. | Avoid same mistakes for next carline or change stamping method process plan | Product Maturity | RD/KRE, PP Press Shop, BodyTec, PP/K | X294
423 | Press Shop PP | PT-Phase |  | Door Inners tolerance smaller | Product | some surface and holes of Door Inners tolerance is smaller smaller than ZB, cause ZB can be easily out of tolerance. | data design issue | check and feedback to RD in early phase to consider some adjustment or align between press shop and body shop. | Avoid same misunderstanding for next carlines, improve release process. | Product Maturity | RD/KRE, PP Press Shop, BodyTec, PP/K | X294
424 | MOE | PT-Phase |  | Trunk lid can't close | Product | The body with bad setting and high CLD sealing, cause the trunk lid cannot close | bad setting , high CLD sealing, body status not so good | Optimize the setting and body status, sealing can't be too low, because it will cause the noice. |  | Product Maturity | AK | X294
425 | MoE | All |  | Data Provision | Organization | Owner of EE input data not clear (VPD, PQD, IMA,...) | No clear processes, tasks and responsibilities | Processes and tasks and responsibilities need to be clarified and implemented |  | Process Maturity | IT, PP and ME | Z177
426 | MoE | PT1 |  | Preponed Vehicles | Process | Preponed vehicles without any prior notice to production | Erros occurred which caused a long EE analysis. If the change would be known before, we could save a lot of time, as we don't need to do this investigation, as the root cause would be clear | Preponing of vehicles only if it is accepted by all related departments. Change is only possible if all requirements are fullfilled (documentation, released version,…) |  | Process Maturity | RD | Z177
427 | MoE | PT2 |  | Unreleased Software | Process | Parts where changed in the line by RD without notice to any other department (e.g. PM2.5 sensor - unreleased Software | Erros occurred which caused a long EE analysis. If the change would be known before, we could save a lot of time, as we don't need to do this investigation, as the root cause would be clear | Change is only possible if all requirements are fullfilled (documentation, released version,…) |  | Process Maturity | RD | Z177
428 | WPL office | PT-Phase |  | Ramp-up planning | Organization | Difficult ramp-up planning and alignment | No clear responsibilities per shop, lack of participation in AK Ramp up, counterpart at BBAC unclear | Setup efficient AK Ramp up with clear responsibilities per shop and clear counterpart at BBAC |  |  |  | Z177
429 | Press Shop PP | B-Phase |  | Ordering process | Process | Parts for PT production are not included in the SAP system. Delivery and using mixed and difficult to track between BS and SS. Bring add. rework and 2nd transport. | Out of SAP system | Define process |  | Costs | ME/StampShop/LOG | Z177
430 | Body Shop PP | All |  | Change process | Process | Compliance risk during project phase to quick react on product and process change. Long process | Current official purchasing process can not fit project requirement. | Setup change process for project which fit to project and quick react on changes to minimize compliance risk. |  | Process Maturity | P&S/IPM | Z177
431 | Body Shop PP | All |  | Logistic interface | Organization | Logistic area occupied issue onsite. Glue ordering during tryout. Internal Logistic coordinate not smooth. | To much interface from Logistic to shops: LOG NTP; LOG SP; LOG operation; LOG Packaging; LOG ramp up; LOG consumable | One LOG coordinator are needed for each shop and can coordinate all LOG topic internally in Logistic. |  | Process Maturity | Logistics Planning | Z177
432 | Paint Shop PP | PT2 |  | Wax Nozzle ordering | Process | Wax Nozzle odering long process | EX33 handling not transparent. enough and difficult to track delivery status | Track more frequently and give pressure to EX33 more earlier (Weekly tracking with standard Onepager in SFM implemented, early escalation) |  | Process Maturity | EX33/ P&S PP | X247
433 | Paint Shop PP | PT2 |  | New Color | Process | Color release | For difficult color like digital white and padgonia red take longer time for color release | Using existing color for ET and PT1 |  | Process Maturity | IPM | Z177
434 | Paint Shop PP | PT1 |  | Code 18 in PT1 | Process | Start too early Code 18 too less time for preparing the customer quality body | A lot of rework and checking | Launch a batch Pre-PT1 between ET and PT1 |  | Product Maturity | IPM | Z177
435 | Logistics Planning | PT1 |  | Changes in fitment points | Process | Changes of fitment points & documentation (~40% after ME takeover) | Delays in planning and handover from ME Lack of interface between SC and ME | Clear Milestones defined in project schedule and stick to it ->BOM - Freeze in time to plan warehouse, route etc. Establish interface between ME and NTP |  | Process Maturity | LOG and ME | Z177
436 | Logistics Planning | B-Phase |  | Parts maturity level | Part | Bad parts maturity lead to the circumstance series condition is not achieved, manual ordering and repacking of 60-100 parts in PT2, 45 in PT3 and 30 in SOP | No sampling, no purchasing deal, no load carriers, late decision of acquisition type, late “blank” release | AK Krit needs to focus more on this issue and push it |  | Process Maturity | P&S | Z177
437 | QM | PT1 |  | MP release | Audit | KTMA audit result was different with MP dimension release report. 2 dimension process in supplier. | MP release do not consider complete dimension report. | Harmonization of MP dimension release process as KTMA. |  | Process Maturity | MP C | Z177
438 | QM | PT-Phase |  | Ordering process | Part | New PT parts can not be arrived in short time during PT tryout. | Quick ordering process for new part is missing. | PT parts ordering process. 1 suggestion: RD1 should order new parts once they know current part is NOK (if new parts are available). Otherwise campaign have to wait till SOP to get new parts. |  | Process Maturity | BBAC RD1/BVA/WPLs | Z177
439 | QM | B-Phase |  | Product audit standard | Audit | Q-specification (product audit standard) resource is unclear. | Due to Z177 specific model in China, Daimler Q do not make Q-specification alone. | Q-specification resource need to be clarified with Daimler Q/DGRC RD/BBAC RD. |  | Product Maturity | QM BBAC | Z177
440 | QM | PT1 |  | E/E release testing | Process | Air package 3.0 and Parkman come too late for testing (between PT1&2) | HW and SW release too late by Daimler RD. | All HW/SW should be available before B-phase, if not, delete or put it in the risky list for regular tracking. |  | Product Maturity | RD/C | Z177
441 | QM | PT-Phase |  | Import part | Organization | From Null Series to now, it’s always a big pain for solving import parts issue without any local interface. | No local interface | Project should have clear local interface for import parts quality issue. |  | Process Maturity | GRC/PM & WPL | Z177
442 | Conveyor - AGV | All |  | IT | Organization | Coordinator for IT topics missing in project. | No clear IT coordinator defined from process team. | 1.must define a clear IT interface 2.project team plans an IT coordinator to track IT issue in each project |  | Process Maturity | IT | Z177
443 | Paint Shop PP | PT1 |  | Surface Quality of BiW PT1 | Audit | Surface Quality is not compelete accept by QM-Voca | a lot of rework time happen in PS | Surface quality of BS outerpanel should be discussed earlier at the realease state. |  | Product Maturity | PRD/BiW QM | X247
444 | Body Shop PP | All |  | RDS | Organization | key user with sufficient training needed; | No clear process in BBAC and RD India | Define process for New type and Series planning; Data preparation India vs. RD China should be discussed |  | Process Maturity | PP | X247
445 | Paint Shop PP | B-Phase |  | Commissioning Carbody Source for TC Process | Process | Commissioning Carbody Source during the Phases is too low. | Commissioning Carbody Source for Color Release and also Color Optimization during the LOT3 -PT Phase is too low. | Paintshop PP will order Commissioning Carbodys from BS if the Carbody Source from BS is not matching with PS Color Integration Plan. |  | Process Maturity | Paint Shop PP | H247
446 | Paint Shop PP | LOT3 |  | Commissioning Carbody Source for PVC Process | Product | Commissioning Carbody Quality for PVC Appearance Optimization and Leackage issue solving very poor! | The Quality of the Scrap Carbodys which are handovered from BS (Yellow Buy off: Performance Test; etc.) to PS is not accure enough for PVC Commissioning. | BS to check if the Maturity of the Carbodys before PT1 Phase can be produced with a better Maturity. |  | Product Maturity | Paint Shop PP, Bodyshop PP | H247
447 | Paint Shop PP | PT-Phase |  | Color Release Code 18 | Product | Colors with low take rate are not stable and are difficult to reach COK / OK Status for PT1. | Material of Paint Suppliers are not stable due to low take rate. Serial carlines are facing the same issue. | For PT1 Phase only high Runner should be considered. PP PS and PS Production to establish a Task Force and push Paint Suppliers to stabilize the Materials. |  | Product Maturity | Paint Shop PP, Paintshop Production | H247
448 | WPL office | PT-Phase |  | Assembly integration responsible missing | Organization | No 1 face to the customer for assembly & MOE issues | No responsible defined | TPL Plant & Assembly discuss integration responsibility for overall Assembly (incl. MOE, LOG, …) issues as also available in Body Shop |  | Process Maturity | RLM | Z177
449 | WPL office | All |  | Product issue communication | Organization | Product issues are not always clear and early communicated | Different channels for SPL and RD China (PLS, GM Meeting, …) | Establish clear communication channels |  | Product Maturity | WPL/RD | Z177
450 | Press Shop PP | B-Phase |  | Ordering process | Part | Parts for PT production are not included in the SAP system. Delivery and using mixed and difficult to track between BS and SS. Bring add. rework and 2nd transport. | Out of SAP system | Define process |  | Process Maturity | ME/StampShop/LOG | Z177
451 | Press Shop PP | LOT3 |  | Aluminum order management | Process | Based on current timeline premises dies are in BBAC for appr. 1 year homeline integration. Maximum aluminum storage time of aluminum blanks from production to stamping is 6 month. HI timeline exceeds aluminum blank storage time. That has lead to production batches with overaged blanks and corresponding bad quality | One time order is preffered by Stamping Shop to achive lower sourcing prices | Define smaller delivery batches to fullfil aluminum storage requirements |  | Product Maturity | Press Shop Production, Press Shop PP | Z177
452 | Body Shop PP | Concept |  | Q-Loop2 | Organization | The responsibility is not clear for Q-Loop2 planning. | 1. Q-loop2 planning belong to PP from Daimler side. 2. Q-loop2 organization change to production from BBAC side 3.Q-loop2 planning responsibility not clarified from BBAC side. | Option1: QM continue responsible for Q-loop2 planning. Option2: add QL2 planning task to ME with additional head count. |  | Process Maturity | QM/ME | Z177
453 | Body Shop PP | Awarding |  | Commissioning parts ordering | Part | Bodyshop project always need to order commissioning parts from Local supplier whom also need to verify their own quality issue and improve it. | The amount of commissioning part is not in contract. | Option1: put the amount of commissioning parts in contract with Local suppliers. Option2: ask for free delivery due to supplier also need to approve there equipment and process. |  | Process Maturity | P&S and ME | Z177
454 | Body Shop PP | All |  | Logistic interface | Organization | Logistic area occupied issue onsite. Glue ordering during tryout. Internal Logistic coordinate not smooth. | To much interface from Logistic to shops: LOG NTP; LOG SP; LOG operation; LOG Packaging; LOG ramp up; LOG consumable | One LOG coordinator are needed for each shop and can coordinate all LOG topic internally in Logistic. |  | Process Maturity | Logistics Planning | Z177
455 | Body Shop PP | All |  | IT | Organization | Less capacity from IT, Coordinator for IT topics missing in project. | No clear IT coordinator defined from process team. | 1.BBAC must define a clear IT interface. 2. project team plans an IT coordinator in BBAC to track IT issue in each shop |  | Process Maturity | IPM | Z177
456 | Body Shop PP | Design |  | Equipment | Process | IMT/STFP/Bestfit/ISRA glue stations VS blue sky | Blue sky influence not identified in early phase | Install black curtain onsite/close cell.Update ECM: supplier responsible for solve the light impact to equipment with the curtain. |  | Process Maturity | PP/ME | Z177
457 | Body Shop PP | Awarding |  | Price of BOM list | Part | Big discussion on BoM price with supplier after awarding regards changes. | 1.0 item in the quotation existed during awarding phase in the BOM list.2.Manpower cost can not be checked and confirmed by BBAC. | 1.Awarding BOM list must be aligned and signed one month after awarding. 2.0 item is not allowed in BOM list. 3. Manpower calculation function needed. |  | Process Maturity | PP/ME/IPM | Z177
458 | Body Shop PP |  |  | LOG | Timeline | Late delivery of SLTs | SLT interfaces and process: - SLT design not available/finalized during design phase by SLT team - BS gripper design depending due to SLT Team deliver the design update not on time - late feedback from press hop regarding SLT change - request load carrier team put 100% SLT CMM&gauge check by load carrier-supplier for the load carrier shipment release buyoff. | Regular meeting with SLT team to exchange the information and define a key person in logistic to track open points for drawing and manufacturing no SLT concept changes for 2nd or 3rd model |  | Process Maturity | Logistics Planning | Z177
459 | Paint Shop PP | B-Phase |  | Quality optimization | Process | Using the B-Phase-bodies to start quality-optimization in topcoat | too less body in ET for optimization and we get directly Code 18 in PT1 | Production should check the bodies and give feedback to us in order to reach a good quality earlier than with Z177. |  | Product Maturity | Production | Z177
460 | Paint Shop PP | B-Phase |  | Manuel Training | Process | Using the B-Phase-bodies to start training in PVC | In PT1 Code 18 require 100% Soap water Test. | Not apply and brush the whole car offline. |  | Product Maturity | Production | Z177
461 | Paint Shop PP | B-Phase |  | Missing HOP`s | Process | Missing HOP's can cause additional containmination to atomizer and influence the normal production | Specific Test Purpose from RD | Install HOP's for all B-Phase Body |  | Process Maturity | RD and Pilot Plant | Z177
462 | Paint Shop PP | PT-Phase |  | Roughness of substrate | Process | Roughness requirements from stamping does not matach with the roughness requiement from PS, it leads to rework in PS | Different standard of Stamping and PS | Alignment and use same standard |  | Process Maturity | Press Shop PP, ME | Z177
463 | Assembly PP | Concept |  | Concept Alignment | Organization | The alignment process between ME/PP is very bad/long regarding the equipment | Miscommunication | Earlier involvement of ME to align and avoid discussions |  | Process Maturity | PP and ME | Z177
464 | Assembly PP | All |  | Communication with suppliers | Organization | Bad communication with suppliers because too many people are in contact with each other without transparency | No defined R&R and transparency | Define one window person to communicate with supplier at beginning of project |  | Process Maturity | PP/ME and L4 | Z177
465 | Assembly PP | All |  | The communication within the project is not sufficient. | Organization | As a result of the limited communication, the TPL had restricted insight into the daily doings of the PGL | No regular communication | Installation of planning review once a month, at which each PG has more than 30 minutes |  | Process Maturity | PGL/TPL | Z177
466 | Assembly PP | Concept |  | Involvement of the control team | Organization | Not enough involvement of the control team by both Daimler PP and BBAC ME. Resulted in misplanning and long discussion with ME. The specifications contained errors and mistakes that could have been avoided. | Lack of involvement of controls team | Including the control team into the signature-set for the specifications. More involvement of the control team into the communication loop |  | Process Maturity | TPL | Z177
467 | Assembly PP | All |  | Buffers in funding not transparent | Process | If the planned budget is higher than the PR, the residual amount of budget will be cut and will not be maintained inside the part-projects funding. | Lack of transparency | The planned values and budgets should be estimated realistically and if possible, it should be estimated at a lower boundary. Chances and risks should be listed transparently in the C/R-list. |  | Costs | PGL/TPL | Z177
468 | Assembly PP | Design |  | 3D Data Transfer for CN equipment by ME | Product | Transfer of product data from Daimler to supplier took several weeks and was available in last minute. | Purchasing process was too late | Purchasing process need to be considered with realistic timeslot and 4 weeks need to be considered for Data transfer in timeline. |  | Timeline | L3 or higher | Z177
469 | Assembly PP | Awarding |  | Time-consuming EX33 process for Special Tools | Process | Some special tools were not available for B-Phase because the EX33 process took a lot of time and the process was intransparent at the beginning | Long and intransparent EX33 | Consider XX month for EX33 process and track the steps regularly in Shop Floor and Ramp Up Meetings |  | Timeline | L4 and Working Level | Z177
470 | Assembly PP | All |  | Cooperation Conveyor | Organization | BBAC Conveyor doesn‘t participate in Assembly Subproject as participant (e.g. regular meetings etc.), just report to WPLs, à difficult communication and cooperation | Matrix organization with Daimler L4 not accepted | Clear commitment between PP/CN and BBAC ME hierarchies that conveyor reports to TPL and participates in exchange meeting |  | Process Maturity | L2 ME/PP | Z177
471 | Assembly PP |  |  | AVO name translation via BRAVO software | Process | Quality of automatic translations into Chinese languages is not satisfactory according to Chinese ME and Production colleagues. | AVOs cannot be understand by Production blue collar | Automatic AVO name translations via BRAVO software has to be improved (if possible). As an alternative: Implementing of software function to shut-down BRAVO for particular AVO (if necessary due to insufficient translation quality) |  | Process Maturity | Working Level | Z177
472 | Assembly PP |  |  | Handover material expectations | Organization | Expectations regarding handover material content deviated between PP and ME process planners. | Within PP no standard (documents) exist for such a handover since this interface does not exist in the any other Daimler plant. Handover from PP to ME already after IPV Process was executed the first time at BBAC. | Handover content had to be clarified. Standard documents were / to be prepared and discussed. |  | Process Maturity | Working level | Z177
473 | Assembly PP |  |  | Premises and targets are not reliable | Process | Premise and targets are not followed by all planners at all time. Process planning guidelines (NLC) are not followed by all planners. Both caused by China specific topics and different point of views. | Planners were blocked to continue their work. Extra/double work was necessary and affected the quality of IPV workshop preparation. Escalation meetings needed to take place. | Support of alignment process by management.Clear and jointly communication of the made alignments to the planners. Management attention that alignments are respected and followed. |  | Process Maturity | L3s-L5s, WPLs, TPLs | Z177
474 | Assembly PP |  |  | IPV timeline | Timeline | Conflict of NLC IPV standard timeline with Productions timeline for ramp-up activities. Documents could not be completely finished in time according to customer preferences (but were finished according to IPV timeline). | Extra/double work was necessary and affected planning resources. | Strongly requested documents on certain dates were afterwards not used.Topic to be discussed and to be fully understood. |  | Costs | L3s-L5s | Z177
475 | Assembly PP | Digital-Phase |  | Dialog data quality | Product | Dialog data quality is not satisfactory. As source data this affects process planning data quality in DPE and ILB. Parts / option codes appear which are not produced in Chinas cars. | Extra work by MO and LOG to manually fix output lists. Uncertainty if everything is considered. | Dialog data quality needs to be improved by RD. |  | Process Maturity | L3 or higher | Z177
476 | Assembly PP | Digital-Phase |  | MoLog interface | Process | Fire fighting actions by assembly and logistics planned were needed to clarify undefined part delivery locations in the system and to define shopping cart parts. | Data quality in Dialog are not satisfactory. Logistics participation in IPV procedure as back-up were not satisfactory. | Data quality in Dialog needs to be improved. Logistics needs to fully attend the IPV workshops. |  | Process Maturity | L3s-L5s, working level | Z177
477 | Assembly PP |  |  | KPIs | Organization | KPI targets for BBAC 2020 were defined by Production without consideration of planning point of view (ME). Requested KPI targets does not match with current situation/premises in assembly shop. Moreover high degrees of utilization are not accepted by Production on group leader and working level and immediately declared as bottle stations. | Conflicts between Production and Planning | Fine line between ambitious and unrealistic targets. Frustration and decreasing motivation within process planners due to far unrealistic targets. Goal to align (very) ambitious but still not far unrealistic targets by PP + ME. |  | Process Maturity | L3 or higher | Z177
478 | Logistics Planning | B-Phase |  | Load carriers | Timeline | Delay for Inhouse SLTs | SLT design phase with contrary targets BS<>PS and copy W371, many alignment loops required | define hard freeze dates, earlier escalation |  | Timeline | LOG TPL, BS, PS | Z177
479 | Logistics Planning | B-Phase |  | Load carriers | Timeline | Delay for Inhouse SLTs, missing delivery plan information, continuously postponed delivery plans | Communication by P&S, general supplier situation, late reaction of P&S | Involve Packaging Team in choosing suitable suppliers - earlier info to LOG - Increase P&S responsibility |  | Timeline | P&S and project | Z177
480 | Logistics Planning | PT1 |  | Changes in fitment points | Organization | Changes of fitment points & documentation (~40% after ME takeover) | Delays in planning and handover from ME. Lack of interface between SC and ME | Clear Milestones defined in project schedule and stick to it -> BOM freeze in time to plan warehouse, route etc. Establish interface between ME and NTP |  | Process Maturity | Logistics Production, ME | Z177
481 | Logistics Planning | B-Phase |  | Changes in delivery method | Process | Switch to route delivery even though POR was delivery via forklift and KLT route costs a lot of delay and double work (layout, BOM, master data, equipment, headcount, process, etc.) | The late decision for GLT and saladbar route delivery implementation | The internal delivery method to lineside has to be defined much earlier. |  | Costs | Management, Bodyshop | Z177
482 | Logistics Planning | B-Phase |  | Parts maturity level | Part | Bad parts maturity lead to the circumstance series condition is not achieved, manual ordering and repacking of 60-100 parts in PT2, 45 in PT3 and 30 in SOP | No sampling, no purchasing deal, no load carriers, late decision of acquisition type, late “blank” release | AK Krit needs to focus more on this issue and push it |  | Process Maturity | P&S | Z177
483 | QM | B-Phase |  | Product audit standard | Audit | Q-specification (product audit standard) resource is unclear. | Due to Z177 specific model in China, Daimler Q do not make Q-specification alone. | Q-specification resource need to be clarified with Daimler Q/DGRC RD/BBAC RD. |  | Process Maturity | QM BBAC | Z177
484 | Facility |  |  | Collision check | Process | Many collision on side | 1. In the contract from Designer not clear described what is to do | Before we start the PR the contend is definite |  | Process Maturity | Facility | Z177
485 | Facility |  |  | CRs | Organization | FP is not invited in the BBAC procedure and signature process | FP can not checking the paper work of possibility | In the early phase of the project the processes have to be coordinated |  | Process Maturity | Facility | Z177
486 | Facility |  |  | Documentation | Organization | FP is not invited in all Handover procedure | No documentation for FP in all Buildings | In the early phase of the project the processes have to be coordinated |  | Process Maturity | Facility | Z177
487 | Facility | Design |  | FM | Process | Official GC timeline for all Buildings not accessible | Important Milestone for example BREI or compress air ready and in function, whit out official timeline tracking from Milestone not possible | Working model and deliverables from documents is to change |  | Timeline | Facility | Z177
488 | Facility - Press shop | Design |  | Equipment | Timeline | LOI for Schuler too late | 1. Design phase whit out detail information from Schuler 2. Too many changes in the end of design phase from Process | Press shop start early with the LOI approval |  | Timeline | ME | Z177
489 | Facility - Press shop | Design |  | Specification regarding soil requirements | Process | Soil requirements different China to Germany | Ground unevenness outside from the tolerance for equipment from Schuler, no input from Schuler, different measure methods Germany/ china | Adjustment clarification in the early phase |  | Process Maturity | ME | Z177
490 | Conveyor - Bodyshop | Design |  | Conveyor platform Interferes with other parties | Process | Before installation of platform, many collision points were found | Supplier did not check layout in faplis with facility or process equipment. | Faplis update must be in time and checked. |  | Process Maturity | PP/supplier | Z177
491 | Conveyor - Bodyshop | Concept |  | Slate Conveyor in process line | Organization | To much interface between conveyor and process in MFA2 prefinish line and finish line. | Prefinish and finish line conveyor equipment done by conveyor team. Process equipment done process. | In the future project all process related conveyor need to be done process supplier. |  | Process Maturity | PP | Z177
492 | Conveyor - AGV | Concept |  | Kick in/out station | Process | For a long time, it is not clear, whether there are 2 or 1 kick in/out station/s | Number and costs are not specified at the beginning of the project | Specify at the beginning of the project how much stations are used. |  | Process Maturity | PP/ME | Z177
493 | Conveyor - AGV | Installation |  | AGV area floor unevenness | Process | AGV has a high requirement on floor evenness. Onsite situation cannot meet, repair work is needed. | Stations are not parallel to the floor. Vehicle slows down because sensors recognize hills, gaps on the track and in station | Make sure early: 1.station and floor is parallel 2.floor is as eaven as required 3.no big gaps in floor |  | Process Maturity | PP | Z177
494 | Conveyor - AGV | Installation |  | Unstable wifi connection | Process | WIFI documentation must be specified; AGV settings caused WIFI problems | Different settings of WIFI onsite | WIFI documentation must be specified |  | Process Maturity | IT | Z177
495 | Conveyor - AGV | Commissioning |  | AGV Safety | Process | Danger of crashes because scanning filed only detects objects with 170mm hight on the driving track. Overhanging objects are not detected | Lack of scanner for higher positions | 1.Add panel to trolley. Avoid entrance of forklifter or people in AGV area 2.Add scanners on AGV |  | Process Maturity | Supplier | Z177
496 | Conveyor - AGV | Awarding |  | Contract with subsupplier | Organization | For a long time, OAS did not accept the contract with KUKA. That's why KUKA started to work on the Layout by themselves. | OAS did not agree to the legal terms and penalties | Clarify contract terms earlier |  | Process Maturity | PP/supplier | Z177
497 | Conveyor - AGV | Concept |  | Internal standards | Process | For AGV not enough standards are available. Misunderstanding from supplier. | AGV is relatively new, specified standards are missing. | Clear specified standards are necessary. Such as checklist, interface, safety concept, battery… |  | Process Maturity | PP | Z177
498 | Conveyor - Sorter | Concept |  | Transfer station needs floor lowering | Process | When handling different car bodies, no room to modify height and position of fork | Modification work, waste of time and money | Transfer station needs floor lowering, This requirement could be clear at the beginning. |  | Timeline | PP | Z177
499 | Conveyor - Sorter | Installation |  | Create a flow chart for BIW, BIP | Process | People don´t understand the flow of skids and bodies | No flow chart | Create a flow chart for BIW, BIP, dip skids, paints skids and ETS skids for all levels and PLCs |  | Process Maturity | PP/ME | Z177
500 | Conveyor - Sorter | Design |  | Camera amount and position | Process | To less 2-D cameras or at the wrong position | No concept | Check Functions of Sorter for Body tracking and create PPT File and mark necessary or possible positions of 2D-Camera |  | Process Maturity | PP/supplier | Z177
501 | Pilot plant | B-Phase |  | ProcessClarification | Process | General support and coordination from Production BIW : Transport; IT system and Routing ; Skates; Racks Assy: EC tools calibration | Related department should prepare all related data and tools to fulfill the requirement of Pilot Plant. | Pilot Plant will also send out requirement to all related departments. |  | Process Maturity | Pilot Plant | Z177
502 | Pilot plant | B-Phase |  | Issue Clarification | Product | Implementation of China specific quality sensors only in Chinese B-Phase | Since China has with Noise, odor and sometimes also other Sensors a different perception of Quality, the Issues come up extremely late, when only found in the very short B-Phases in China. | Let the Sensors of QM already start their own audits in German BF with lead-Phase / lead-vehicle. |  | Product Maturity |  | Z177
503 | RLM |  |  | No early involvement of BBAC | Product | Activities lead carline and expected Top-issues in early phase are not visible | Unclear status of the activities and impact (i.e. MO-Testate, PPG, Absicherungslandkarte, Zeus, VoCA) | Frequent update of activities from the lead carline and crosscheck the possible impact to China |  | Product Maturity | WPL | Z177
504 | RLM |  |  | No clear KPI- / target based tracking during project phase | Process | Consistent reporting tracking through the phases. | Readiness of processes are not ensured to PT2 | Generate KPI-based dashboard and overview to show which report incl. presenter will be presented in which committee in a defined timeline. |  | Process Maturity | RLM | Z177
505 | RLM |  |  | Decisions & escalation (less details in management meetings) | Organization | Late or no decsions keeps the organization in an uncertain mode | Example: 2nd GHI station ready during PT3. Code 18 working direction defined, but where and when is the final decision? |  |  | Timeline | WPL | Z177
506 | RLM |  |  | Improve problem solving process and speed | Product | Round about 150 open Zeus issues six weeks prio SoP |  |  |  | Product Maturity |  | Z177
507 | Maintenance | White Buy-Off |  | Project spare part | Part | The spare part lists are delivered late. Project spare part late arrival. | Suppliers don't pay more attention to it. Line builders’ offer exceeded budget. Re-sourcing and budget application took time. | Need earlier spare part list deliver from supplier. Price of line builder need to be reasonable |  | Costs | PP/ME | Z177
508 | Maintenance | Concept |  | Integra standard training | Organization | Maintenance don't know the new Integra standard | There is no training for maintenance. | The Integra standard training should be given to maintenance before they joining in the project. |  | Process Maturity | PP/ME | Z177
509 | Maintenance | PT1 |  | Technology Training | Organization | Training content and supplier were not clear from beginning. | Training standard was not clarified during bidding. | Need to require standard training content and original source from supplier from early stage. |  | Process Maturity | PP/ME | X247
510 | Maintenance | White Buy-Off |  | Cooling water quality | Process | Cooling water was found with rust inside. | Rust in pipe was not cleaned before installation. | Pipes need to be rinsed before connecting. |  | Process Maturity | PP/ME | X247
511 | Maintenance | Design |  | Documentation | Organization | FFT documentation has language and content problem. (BS) Many supplier even don't know how to build SLE documentation. (AS) | Documentation direct copy & paste from German project. (BS) Supplier lacks training. (AS) | Need supplier re-work on documentation preparation. (BS) Give suppliers training for SLE. (AS) |  | Process Maturity | PP/ME | X247
512 | Maintenance | Design |  | Illumination | Organization | Fluorescent lamps instead of LED lamps were implemented | Supplier chose fluorescent lamps as previous project. | Lighting standard need to be clarified at design phase. |  | Product Maturity | PP/ME | X247
513 | Maintenance | Awarding |  | Supplier choosing | Organization | MRA and MFA should same equipment use different supplier, increase spare parts cost | Different suppliers Maintenance need to prepare more spare parts | Same equipment use the same supplier |  | Costs | PP/ME | X247
514 | Maintenance | Concept |  | Planning | Process | Pre-finish line has 2 kinds of function position planning, because it is built by conveyor project and Z2 project. | In pre-finish line, the platform and conveyor equipment are belong to conveyor project, but the process equipment is belong to Z2 project. It cause the pre-finish has 2 kinds of design with different function name. | One line should be planned as one project so that the line has one kind of function position planning. |  | Process Maturity | PP/ME | Z177
515 | IT | Commissioning |  | Issue escalation (time) | Organization | IT only got to know from the issue 2 days earlier than the escalation started | IT was not informed in advance of a issue | More efficient communication between business and IT and an IT integration meeting with all shops business owner |  | Process Maturity | WPL/IT PM | Z177
516 | IT | Commissioning |  | Clear responsibility | Organization | Each separate Project Leaders for MFA2 and Project Leader for Engine Plant, engine plant leader not responsible for imported engine, responsibility was missing during the project | No clear roles and responsibilities for imported engine, no one planned this topic | One single responsible person for the imported engines for planning and execution |  | Process Maturity | TPL / IT PM | Z177
517 | IT | Commissioning |  | Lead time for IT readiness | Timeline | IT readiness is asked too late and than there is not enough time to do the IT activities | IT applications and especially infrastructure have a lead time (for example. Order processes) that can not be shortened, IT readiness is not asked enough time in advance | IT should be informed well in advance to have no problem with IT lead time |  | Timeline | WPL/IT PM | Z177
518 | WPL office |  |  |  | Process | Handover new type project to series production not clearly defined (product & process) | [5 empty] | Z177
519 | WPL office |  |  |  | Process | Current purchasing process does not enable fast and efficient change requests (especially body shop) | [5 empty] | Z177
520 | WPL office |  |  |  | Organization | Clear definition of task, responsibilities and decision authority for ramp up planning necessary (SC/VTO, RD1 BBAC, LOG BBAC ) | [5 empty] | Z177
521 | WPL office |  |  |  | Organization | Strategy for pilot plant china and pilot plant Germany to be reviewed (number of cars, maturity work collaboration) | [5 empty] | Z177
522 | WPL office |  |  |  | Organization | Clear alignment between QM, press shop and body shop concerning press part release status required (color logic) | [5 empty] | Z177
523 | WPL office |  |  |  | Process | Further optimization of working equipment and working infrastructure at BBAC MFA (fast IT and WiFi, amount and reliability of VC equipment, process planning software insufficient) | [5 empty] | Z177
524 | WPL office |  |  | Color Release Planning | Process | In B-Phase only white is planned, always shortage of commissioning vehicles for Color Match, delays Release Not enough vehicle in specific color available for Q-release | Paint Shop not involved in B-Phase ordering QM didnt address need | 1. Utilize B-Phase vehicles for Color Matching, use high take rate colors, important colors, but no new colors. 2. Consider for PT2 ordering RGA and Process Validation requirements (Input by Bora), don't use special colors for RGA vehicles (e.g. magno) |  | Process Maturity | Paintshop PP Log/QM | X247
525 | WPL office |  |  | Color Implementation & Interface PLS Magno & special colors | Timeline | FBC timeline & color implementation timeline does not match | FBC not available for Cycle 1 | Before Decision when to implement Magno, check FBC necessity & availability timeline |  | Timeline | PLU | X247
526 | WPL office |  |  | Color Implementation & Interface PLS also MRA topic | Timeline | Color Implementation timeline unrealistic, Paint Shop Capacity not considered Communication of Different Timelines | Delay of Paint Material Release, squeezes timeline at PS BMBS timeline differs from premise handbook status | Early escalation in PLS and consideration of capacity. PLU/BPL responsible. Added to process decriptin. only ONE timeline, update premise handbook in case of prio changes |  | Timeline | WPL | X247
527 | WPL office |  |  | After Sales Spare Parts | Organization | Late information from MP/After Sales, needs to be clarified early and follow the standard (lead plant provides all spare parts, CHN only china specific parts); |  |  |  | Process Maturity |  | X247
528 | WPL office |  |  | AK Ramp-up | Process | A Lot of changes of timeline due to late integration of pipecleaners & transparent vehicle | no clear premises | Transparent Vehicle + Pipecleaner planning, needs to be considered from beginning one; standardize and align lead times; |  | Process Maturity |  | X247
529 | WPL office |  |  | Transparent Vehicle | Process | Utilization of results - how can be best utilize the knowledge? | premises of shops for utilization not clear | Define detailed timeline with premises |  | Product Maturity |  | X247
530 | Paint Shop PP | LOT4 |  | Voca Feedback | Audit | Late feedback from B-Phase Eg. Feedback of lot1 receive at lot2 | Less and big time gap of Voca meeting arrangement during B-Phase | Speed Voca for painted body, get feedback from QM in short time |  | Product Maturity | Pilot Plant | X247
531 | Paint Shop PP | PT1 |  | Surface Quality of BiW PT1 | Product | Surface Quality is not compelete accept by QM-Voca | a lot of rework time happen in PS | Surface quality of BS outerpanel should be discussed earlier at the realease state. |  | Product Maturity | PRD/BiW QM | X247
532 | Paint Shop PP | PT-Phase |  | Meko-D result | Timeline | Late feedback from Meko-D | During PT1 we get the Meko-D result from B-Phase, which cause additional rework for Production | Feedback timeline optimization |  | Costs | WPL | X247
533 | Paint Shop PP | B-Phase |  | Zeus Responsibility | Product | Poor PVC apperance due to special Hemming design | BiW feedback follow the body data for producing. It take too much extra efforts for PS close that point | Zeus should be adressed to responsible party correctly |  | Process Maturity | QM | X247
534 | Maintenance |  |  | BS Maintenance | Process | Specific car type needs to be planned for line recovery after commissioning |  |  |  | Process Maturity |  | X247
535 | Maintenance |  |  | BS Maintenance | Process | Car bodies for special function test needs to be planned. Suppliers needs to finish function without too many problems. |  |  |  | Process Maturity |  | X247
536 | Maintenance | Commissioning |  | BS Maintenance | Process | NOK process needs to be checked during yellow buyoff. |  |  |  | Process Maturity | PP electric | X247
537 | Maintenance |  |  | BS Maintenance | Process | Supplier staff should staty onsite after big modification in night shift |  |  |  | Process Maturity | PP | X247
538 | Maintenance |  |  | BS Maintenance | Process | There should be centralized and regular update for spot welding gun change to maintenance. |  |  |  | Process Maturity | PP | X247
539 | Logistics Planning |  |  | Load carrier quality (automatic load carrier) | Process | Two different suppliers for one load carrier (idea for was to save time to get small pre-series batches earlier), but finally awarding date was at the same for both suppliers |  | already close tracking of timeline and regular communication with P&S |  | Process Maturity | LOG and P&S | X247
540 | Logistics Planning |  |  | Load carrier strategy | Process | Load carrier between 2 automatic robot stations must be designed and purchased by line builder to avoid additional interfaces (e.g. ZB Mainfloor) |  |  |  | Process Maturity | Project, LOG, BS | X247
541 | Logistics Planning |  |  | Load carrier quality (automatic load carrier) | Process | If 100% CMM checking is done and simulation is done - then load carrier is qualified to work in the station. Afterwards changes of load carrier is not easy. If there are some changes the packaging team has always to be involved. In the past mainfloor line builder and supplier made changes on their own and therefore root cause analysis if any problem is very difficult. |  |  |  | Process Maturity | Body Shop PP | X247
542 | Logistics Planning |  |  | Responsibility of robot tests | Organization | Robot tests were lead by packaging team which do not know the free timeslots in production. The result was that robot test times were not reliable and sometimes did not take place at all. After handing over the qualified load carrier the lead for robot tests has to be in Bodyshop, Packaging team will support. | Lead of robot tests is with packaging team. | Lead should be with Bodyshop as with MRA, needs to be aligned |  | Process Maturity | Body Shop PP | X247
543 | Logistics Planning |  |  | Robot test load carrier | Timeline | Delay of release for load carriers | Programming is done by different operators in robot station, therefore no experience and knowledge transfer possible. In some cases there were also different persons in one station. The result was that the load carrier could not be released by unexperienced operator. |  |  | Process Maturity | Body Shop PP | X247
544 | Logistics Planning |  |  | Robot test load carrier | Process | Set up a checking list for robot test for root cause analysis (e.g. step by step described what has to be checked) |  |  |  | Process Maturity | Logistics Planning | X247
545 | Logistics Planning |  |  | Robot test load carrier | Process | An already released load carrier suddenly did not work in the station any more. | gripper program was changed after releasing load carrier. |  |  | Process Maturity | Body Shop PP | X247
546 | Logistics Planning |  |  | Robot test load carrier | Process | Mismatch load carrier and robot/ gripper | Pins were not maintained in loading station |  |  | Process Maturity | Body Shop PP | X247
547 | Logistics Planning |  |  | Late vehicle order frozen | Timeline | most milestones' vehicle order frozen late, not according to LOG timeline, cause late BOM and late parts demand in system |  |  |  | Process Maturity | Daimler C/PM | X247
548 | Logistics Planning |  |  | Late vehicle order change & code change | Timeline | scrap and airfreight cost | many late vehicle changes/code change requests (even 1 day before production) |  |  | Costs | Daimler C/PM;BBAC RD | X247
549 | Logistics Planning |  |  | Late parts change request | Timeline | for PT1/PT2/ET2, there are many late parts change requests between ETA and production, make warehouse &lineside chaos and confusing. |  |  |  | Process Maturity | Daimler MP;BBAC RD | X247, BEV
550 | Logistics Planning |  |  | parts with quaility problem control | Part | when parts have quality problem need to exchange/check/handle, no clear responsibility & control from quality side ,especially EX33 parts. |  |  |  | Product Maturity | Daimler MP;BBAC RD; BBAC QM | X247
551 | Logistics Planning |  |  | import parts scope | Part | there is no clear scope for import parts, cause much airefreight cost. | parts release late and contract issue |  |  | Costs | Daimler MP | X247
552 | QM |  |  | Vehicle configuration change | Product | Rregular change of PT vehicle configuration after order frozen leads to additional workload | The PTs vehicle configuration(code/EXT color) is still changed frequently after the ordering frozen, increased the workload. DGRC colleagues did not follow the LOG vehicle order timeline/process. Compromise for ordering frozen: 6 months before vehicle tryout. |  |  | Process Maturity | DGRC PM/BMBS | X247
553 | QM |  |  | Torque Release Process in tryout phase | Process | Not clear how to get input in case of changes for torque class, torque target, part changes while tryout phase | no clear process | share information e.g. via Ramp-up meeting |  | Process Maturity | RD | X247
554 | Body Shop PP | All |  | RDS | Process | key user with sufficient training needed; | No clear process in BBAC and RD India | Define process for New type and Series planning; Data preparation India vs. RD China should be discussed |  | Process Maturity | PP | X247
555 | Body Shop PP | Concept |  | Code 18 in PT1 | Part | H247 ET parts not enough | Adaption of distribution of commissioning bodies needed | 1. plan more bodies in early phase and less in later phase 2. Different batches of parts cannot be mixed for earlier Q loops |  | Process Maturity | PP | H247
556 | Body Shop PP | Concept |  | Cycle time evaluation for mix mode | Process | Integra standard did not consider mix mode evaluation. Common evaluation method not existed. | ntegra standard did not consider mix mode evaluation | Improve PLC programming and implement the evaluation methods before PT1 or ET |  | Process Maturity | PP | X247
557 | Body Shop PP | Concept |  | Wrong glue type | Process | Wrong glue until PT3 due to no order information in the first product data and later update didn't recognize | Missing order information | Final ordering should be done with order number only |  | Process Maturity | PP | X247
558 | Body Shop PP | Concept |  | Performance test line condition preparation | Process | For each time performance test, certain line condition is needed to make the test running | Conditions not clearly aligned | Clarify and align all the details about line condition with production before performance test. |  | Process Maturity | PP | X247
559 | Controlling |  |  | BEV EA | Process | lack of clear picture on the EA changes | Premise changes caused sharp EA increase during RD re-structuring time and the launch of new funding system | Foresee the risks and report more frequently |  | Costs | WANG Fuqing | X247
560 | Assembly PP |  |  | Communication | Product | Product issues that are found in Pilot plant are not communicated to PP | Currently there is no structured information sharing of product topics: - production planning is not included in pilot plant activities - regular infromation exchange missing - module planners are attending B-phase in Germany, who is taking over this responsibility in China? | Install a regular reporting during B-Phase |  | Product Maturity | PP, Pilot Plant | X247
561 | Assembly PP |  |  | Collaboration | Process | Maintenance very often rejects to give a Technical Approval |  | Signature of Maintenance should be included into design/concept releses to ensure feedback is given and approved early to avoid late changes |  | Process Maturity | PP, Maintenance | X247
562 | Assembly PP |  |  | New supplier capability | Organization | Local new suppliers often don't know what they bid for and are not familiar with the requirements, that are defined in ECM |  | Provide a mandatory ECM-training for new suppliers |  | Process Maturity | PP, P&S | X247
563 | Assembly PP |  |  | Supplier Set Rating | Process | Some local suppliers don't know about the ECM-specs |  | Add the line item "ECM-trained" in the supplier rating |  | Process Maturity |  | X247
564 | Assembly PP |  |  | Commissioning Parts | Part | Permanent storage area for NTP is not defined |  | Define a process how to handle commissioning cars/parts from purchasing to scrap |  | Process Maturity | PP | X247
565 | Assembly PP |  |  |  |  | Process for cars and parts transportation unclear |  |  |  |  | PP, LOG | X247
566 | Assembly PP |  |  |  |  | Scrapping process for old equipment, parts, cars unclear |  |  |  |  | PP | X247
567 | Assembly PP |  |  | Equipment Concepts | Process | Maintenance requests late changes on equipment, that needs to be equal to other Daimler plants |  | Involve BBAC in the design release for equipment, that was copied from Daimler plants |  |  | PP, Maintenance | X247
568 | Assembly PP |  |  | Q-release and vPFU | Process | Process for vPFU for same equipment with different car models is not clear |  | Define a process for vPFU for same equipment with different car models |  | Process Maturity | QM | X247
569 | Assembly PP |  |  | Q-Audit | Audit | Late changes in Q-Masterlist lead to difficulties in equipment planning requested |  | Q-Masterlist needs to be finished and approved to a certain time in ramp-up-process |  | Process Maturity | QM | X247
570 | Assembly PP |  |  | Safety regulation | Organization | Safety regulation for construction works need to be clear during contract with supplier to ensure all regulations are met |  | Align the safety regulations with safety department for the installation phases and provide a safety requirements training with chosen suppliers |  | Process Maturity | PP, C&A | X247
571 | Assembly PP |  |  | Ramp-up planning | Process | Problems to ensure supplier support for extended PTs onsite, especially for import equipment |  | Make the number of booked ramp-up support transparent to the project |  | Process Maturity | PP, Production | X247
572 | Assembly PP |  |  | Change of persons | Organization | High fluctuation increases interfaces and supports misunderstandings |  | Information about change of responsibilities must be communicated asap |  | Process Maturity | Production | X247
573 | Assembly PP |  |  | Misc. approval process | Process | Approval for NTP topics by Series planning takes a lot of time and causes of lot of difficulties |  | Avoid Series Planning approvals for NTP scope in all systems |  | Process Maturity | PM | X247
574 | Assembly PP |  |  | Roles & responsibilities | Organization | NTP solves issues for SP in series phase during NTP phase of further models |  | Clear definition of Series vs. Project Scope at the beginning of the project |  | Process Maturity | PM | X247
575 | Assembly PP |  |  | Collaboration | Organization | No regular information flow and structured interfac between Purchasing and Planning, |  | Install a regular meeting between Purchasing and NTP during sourcing phase |  | Process Maturity | PP, P&S | X247
576 | Assembly PP |  |  | Communication | Organization | Mistakes, that were made in brother plants happen in the same way in China. Communication with other plants needs to be improved that concepts and problems are known |  | Install a regular meeting with brother plants |  | Process Maturity | PP, CEP | X247
577 | Assembly PP |  |  | Commissioning Parts | Part | Too many expensive commissioning parts were ordered and not really needed |  | Install a steering commitee for commissioning parts ordering and usage (in ordering phase) |  | Costs | PP | X247
578 | Assembly PP |  |  | Communication | Organization | The communication between the single planners of the different plants is not sufficient |  | Strengthen the regular functional meetings between the PGL/Equipmentplanners/Process Planners of different plants |  | Process Maturity |  | X247
579 | Assembly PP |  |  | Collaboration | Organization | Roles & Responsibilities in IPV Process Planning are not fully understood (communicated?) and "lived" between PP series planning and IPV process planning. |  | Precise definition and understanding of the handover scope and date in an early phase and close collaboration between NTP and STP |  | Process Maturity | L3 or higher | X247
580 | Assembly PP |  |  | Meeting collaboration | Organization | No response from local BBAC colleagues on meeting invitations |  | Define collaboration guidelines and policy of respectful interaction with each other at the beginning of a project |  | Process Maturity | L4 Series Planning | X247
581 | Assembly PP |  |  | Roles & responsibilities | Organization | Training documents for worker are created by planning and not by Production (as supposed e.g. in Rastatt -> Serieneinführung) |  | Define Production/Planning interface at the beginning of the project |  | Process Maturity |  | X247
582 | Assembly PP |  |  | Roles & responsibilities | Organization | Participation and role of Production in IPV Release is not understood by Production -> Transfer processes from IPV Releases to PTs |  | Define Production/Planning interface at the beginning of the project |  | Process Maturity |  | X247
583 | Assembly PP |  |  | Roles & responsibilities | Organization | IS-Test topics: Interface between Central Planning, NTP, Series Planning and MOE needs to be clarified. |  | Discuss about R&R with MOE at the very beginning |  | Process Maturity |  | X247
584 | Assembly PP |  |  | Collaboration | Organization | MTM: different understanding of MTM methods between IE GER and IE BBAC --> leads to high amount of MTM measures during IPV Release |  | Discuss about all of the MTM-topics in IPV Process / Have the same standard for MTM and Ergonomics during the whole IPV |  | Process Maturity |  | X247
585 | AK Ramp-Up |  |  |  | Organization | Volumes, Ramp Up Curves Alignment => unclear communication | This is a very important topic for production; all the milestones should fit; proper communication alignment bring more transparence | Align process |  | Process Maturity | WPL | X247
586 | AK Ramp-Up |  |  |  | Organization | Transparent Vehicle Process => results communication Body Shop can be improved for the future projects |  | Intorduce a separate Meeting on the working level for communication Transparent Vehicle Body Shop results in ET and PT’s |  | Process Maturity | WPL | X247
587 | Paint Shop PP | LOT3 |  | Commissioning Carbody Source for TC Process | Process | Commissioning Carbody Source during the Phases is too low. | Commissioning Carbody Source for Color Release and also Color Optimization during the LOT3 -PT Phase is too low. | Paint Shop PP will order Commissioning Carbodys from BS if the Carbody Source from BS is not matching with PS Color Integration Plan. |  | Process Maturity | Paint Shop PP | H247
588 | Paint Shop PP | LOT3 |  | Commissioning Carbody Source for PVC Process | Product | Commissioning Carbody Quality for PVC Appearance Optimization and Leackage issue solving very poor! | The Quality of the Scrap Carbodys which are handovered from BS (Yellow Buy off: Performance Test; etc.) to PS is not accure enough for PVC Commissioning. | BS to check if the Maturity of the Carbodys before PT1 Phase can be produced with a better Maturity. |  | Product Maturity | Paint Shop PP, Bodyshop PP | H247
589 | Paint Shop PP | PT-Phase |  | Color Release Code 18 | Product | Colors with low take rate are not stable and are difficult to reach COK / OK Status for PT1. | Material of Paint Suppliers are not stable due to low take rate. Serial carlines are facing the same issue. | For PT1 Phase only high Runner should be considered. Paint Shop PP and Production to establish a Task Force and push Paint Suppliers to stabilize the Materials. |  | Product Maturity | Paint Shop PP, Paint Shop Production | H247
590 | QM |  |  | Charger station power capacity | Process | BEV charger station power capacity beyond the capacity limit. Transformer planned |  | Future MMA BEV car charging capacity need to be considered in planning phase |  | Process Maturity | BEV | BEV
591 | QM |  |  | Close tracking of China specific testing & government regulations for BEV | Process | Such as battery lifecylce management, RTM regulation etc |  |  |  | Product Maturity | RDC, RD3 BBAC | BEV
592 | WPL office |  |  | Critical parts tracking | Part | Close and early tracking of Battery, eATS, eDrive HW/SW, EE status |  |  |  | Process Maturity | WPL/LOG | BEV
593 | WPL office |  |  | Late parts change | Part | Avoid late code change after ASL frozen |  |  |  | Timeline | PM | BEV
594 | QM |  |  | Code setting process PT cars | Process | Campaign & Handover status of PT vehicles need to be more transparent |  |  |  | Process Maturity | QM | BEV
595 | FSK |  |  | Cars amount in B-Phase | Product | Sufficient amount of cars in B-Phase to ensure the product maturity & training |  |  |  | Product Maturity | Pilot Plant | BEV
596 | AK Ramp-Up |  |  | Capacity alignment | Process | Ramp-up curve needs to be aligned between vehicle plant and CAPA (critical parts) |  |  |  | Process Maturity | AK ramp-up, MP KAPA | BEV
597 | RLM |  |  | WRM to run 3 Month after SoP | Organization | WRM need to run 3 Month + SoP to ensure the continuous topics tracking and solving |  |  |  | Process Maturity | RLM | BEV
598 | WPL office |  |  | Resources transparancy | Organization | Clear communication of Resources planning changes with BBAC |  |  |  | Process Maturity | WPL, TPLS | BEV
599 |  | Design |  | DS tightening with high requirements of process control | Product | Too much DS requirements in the product drawing, it cost high investment for process controlling | RD input, root cause not clear; Compare with vehicle and engine, too much DS tightening is requested for product. | Feedback to RD, but no solution | cost saving | Costs | Product interface
600 |  | Awarding |  | Strategic supplier | Organization | EB5 Grob as strategic partner in Germany projec blocked information sharing towards to BBAC by intensively contract. E.g. heat gluing technology. Also no capacity for China project. | Strategy in Germany didn’t consider China volume | Proposal for future project: - Strategic partner in Germany should not be owener of design and concep - Define in Germany contract, MBAG is owner of all design data | Technical input available | Costs | TPL
601 |  | Commissioning |  | Integra pump doesn’t fit powertrain glue barrel | Equipment | Intec gluing pump in Integra, doesn’t work on powertrain glue plastic barrel. Equipment blow glue out of barrel. | Directly took over Integra device doesn’t fit to powertrain usage | Integra powertrain needs to be developed specifically from Germany | cost saving | Process Maturity | Standardization Team
602 | EP1 | All |  | Language skills in Englisch weren't sufficient | Organization | difficulties in communication in diferent phses of the project. Detailed technical discussions only possible in chinese. | During clarification and shopfloor rounds, time and performance losses on Supplier side detected due to communication barriers. | stick to international business approach! requires good englisch skills even on technical level. Review with supplier language skills and Org Chart <> language skill evaluation. | less misunderstandings | Timeline | PP | M254Step2
603 | EP1 | All |  | Shopfloor management | Organization | less transparency and forward planning | weak project management | focus on supplier ability for proper escalation processes and shop floor management via Shop floor audit process following EB5 shopfloor audit process | ensuring stable supplier transparency | Timeline | PP&MPS | M254Step2
604 | EP1 | PT-Phase |  | Problem solving process | Organization | weak performance of problem solving | competence of supplier on engineer level to analyse root causes and proper solution finding | usage of Mercedes Benz competences to improve suppler skills by teaching the right mind set of Management of supplier for supplier internal traing for these kind of situations | increasing competence of supplier | Timeline | PP | M254Step2
605 | EP1 | All |  | LOP Handling | Organization | the roles & responsibilities as well as the process of working with LOP lists with customer is not sufficient | alignment and process between supplier and customer isn't optimal | Check template, knowledge from SQDMC, EB4/5 project achievements and follow up with supplier for improvement | aligned LOP Handling process with defined R&R and accessibility established. | Timeline | PP | M254Step2
606 | EP1 | Design |  | Innovation & Design ability | Organization | during design phase the abilities to show innovative solutions is weak, honest response without fearing customer reaction can be improved, design proposals could have an earlier high maturity | ability, culture barriers | improve supplier sensibility, collaboration shall be reviewed to adjust with Management support | improvement of competency and speed of clarification in design phase | Timeline | PP&MPS | M254Step2
607 | EP1 | Commissioning |  | stabibility of Project Team | Organization | changing people in central project functions was leading to a lower performance of the project | proper handover, knowledge and skill check wasn't done from supplier | process and risk evaluation need to be considered from supplier. Possible to check processes of Job description and employee allocation in the company to evaluated in bidding and start of the project. | agile project of supplier evaluation leads to more attention on supplier side | Timeline | PP | M254Step2
608 | EP1 | All |  | Communication | Organization | different statements of supplier to equal topics | missing supplier internal alignment | meeting landscape, roles & responsibility and window person communication to be kept | no mis understanding within project communication, clear responsibilities defined` | Timeline | PP | M254Step2
609 | EP1 | PT-Phase |  | Fulfillment of Training scope | Organization | Sub-supplier trainings weren't proceeded by the sub supplier, only by turnkey supplier. Low maturity - low efficiency and maturity of the Training | intention of supplier not clear | Sub supplier trainings shall be considered: Standard: Instruction is always included in the scope of delivery. In addition BBAC order Training following the Project spec book eATS2.0_M3_1.4_03_08 | condition for technical approval fulfilled in time | Timeline | PP | M254Step2
610 | EP1 | PT-Phase |  | Documentation | Organization | The documentation shows very low maturity and leads to postponement of acceptance milestones | priority/understanding from supplier side, started too late | clear responsibility at supplier (window person) with specicific customer related Training background to be ensured | higher maturity of Documentation | Timeline | PP & TSS | M254Step2
611 | EP1 | All |  | Change Managament | Organization | changes integrated on risk, ad hoc implementations with a lot of efforts on customer side | no clear changemanagement process at supplier recognisable | follow an aligned process, supplier and customer need to show up an aligned process. ECM request from supplier 2 weeks after announcement of a change timeline, costs and concept. | agille changemanagement process leads to avoid risks from changes within the project | Timeline | PP | M254Step2
612 | EP1 | SOP |  | Manufacturing of parts/ components | Equipment | parts produced by supplier are having korosion issues. | wrong or missing treament of parts, wrong material choice | during design phase and Buyoff phase drawing and manufactured parts check to be considered | Avoidance of issue | Timeline | PP | M254Step2
613 | EP1 | SOP |  | Manufacturing of parts/ components | Equipment | parts produced by supplier are having faults (Adapter plates holes/pins) -> rework with customer after delivery | missing Q-Gate at supplier | internal Q-Gate before delivery at supplier necessary | Avoidance of issue | Timeline | PP | M254Step2
614 | E&B | PT-Phase | PT-Phase | Certificate and calibration management | Audit | For Zenzefi certificate issue, in EB4 EOL， some times Zenzefi certificate are suddenly invalid with make a big affection to daily production |  | Create certificate and calibration overview for production line | Cost | Costs | Planner | EB5xy
615 | E&B | Design | Concept | Integra stadanrda for E&B | Equipment | Cheap and good local equipment supplier can not be choosen for prodcution line. | MB standard and Mainenance DEEP have defined suppliers who are quite expensive and sometimes even provide low efficient solutions. | 0. In principle, E&B needs specific developed Integra standard, project premise needs to be pre-aligned with standardization team 1. R/Y/G equipment list based on Integra has to align as project premise 2. Follow localization strategy: - Turnkey supplier - System supplier: e.g. EOL - Components supplier: e.g. Integra part 3. Pre-evaluate which standard should be followed in project: Integra 4/5/6/7 4. Blackbox needs to be identified as premise | Cost | Costs | TPL | EB5xy
616 | E&B | Commissioning | Design | Battery adaptor | Equipment | After construction of several HV/LV/Leakage Adpater, RD mostly change the product and then we need to pay for all adapters again | High frequency battery plug changes | Ordering for commissioning 1+1 set, after RD release final design we order the remaining adapters | Cost | Costs | Planner | EB5xy
617 | E&B | Design | Awarding | iCR approval | Organization | Change request approval in WPL level takes too long time | Production change can be easy approved but not for process change. So process change PPT explanation should be as detailed as possible. And using the updated process drawing as evidence to explain the change, it would be more convictive. | iCR meeting participate always by change manager and responsible planner Internal CR/PR questions checklist needs to be prepared for internal review | Timeline | Timeline | Change manager | EB5xy
618 | E&B | Design | Digital-Phase | R&R | Organization | Production involve project late and don’t have full knowledge of process | Different understanding of responsibility from cross-function | Align with maintance and production in project premise: - Early inovlve production and maintenance in spec book phase; - Start on-site operation from installation and commissioning phase | Knowledge accumulate from early phase | Process Maturity | TPL | EB5xy
619 | E&B | Awarding | Digital-Phase | Budget planning approach | Organization | EB5 project over cost target The project budget is easily to be underestimated when the project includes immature product or process. | immature product or process leads to many change request | Proposal approach: - Consider TE support for budget planning and project management clarify before BoD - Budget planning workshop in Germany with strategic planning before BoD preparation; - Global risk workshop before budget planning; - General change cost logic to be re-discuss in the project preparation phase with WPL and E2 - Strategic sourcing for predicting line price (to be checked in compliance) | Cost | Cost | TPL | EB5xy
620 | E&B | Design | Design | R&R | Organization | The responsibility of necessary input for production planning is unclear. Such as reusability list, rework instruction, traceability list, glue material specification. In every project this topic has to be argued among RD, QM, PP, Prod, LOG. | undefined responsibility | Responsibility needs to be defined at beginning of project: Lead plant and pilot plant take responsibility of BBAC project planning, provide input; Establish input checklist and review milestone for RD and Pilot plant - Summary EB5 project lessons learned from rework workshop; - Follow alignment in EB5 project between QM/RD/PP/Prod - EB5 RD open topic list as reference Pilot plant TE contract and expectation can be prepared before BoD - Deliverable list - Event and activity participation (On-shore/ Off-shore) | Time saving | Timeline | Product interface | EB5xy
621 | E&B | Design | Digital-Phase | R&R | Organization | Quality planning guide and check the PLP document which made by PP but later transfer to Q series. Why can't Q planning make and transfer to Q series? | Follow previous project R&R | Responsibility to be discussed for new project: Quality planning should resp. PLP document editing. | avoid misunderstanding and improve effeiency | Timeline | TPL | EB5xy
622 | E&B | Design | Digital-Phase | R&R | Organization | Unsatisfied design procedure considering mechnical and electrical synchronization | Design conduct in series steps. Current approach: Mech design freeze, then elec, design start | Deep dive workshop necessary: - Reference from vehicle Mech &Elec team - Reference from Germany standardization team - Target is quick synchronization during design phase | Time saving | Timeline | Electric Planner | EB5xy
623 | E&B | Installation |  | R&R | Organization | During the installation of steel structures have the interfere with the light strip | On-site building check is not fulfilled before installation started | Faplis checking is required from facility planning and turnkey supplier | cost saving | Costs | Facility planner | EB5xy
624 | E&B | Awarding | Awarding | Increase competition | Organization | Supplier quotaiton is too high, and out BOD approved budget cannot cover the best-pick price. | The market is changing fast, budget planning might not match the cost increase of it. | Proposal procedure: 1. Involve more suppliers, deeper localization as precondition; 2. Comparable quantity breakdown; 3. Synchronize PPV price; | cost saving | Costs | PLP | EB5xy
625 | E&B | Installation |  | Meeting landscape | Organization | PP aligned with stakeholders in small loop in installation phase.No kick off meeting.but already plan Shipping acceptance kick off meeting | Installation conducts parrelly in Shanghai and Beijing. Aligned with line builder and stakehopdlers seperatly. Focus on more priority tasks. | Cross-function project meeting is necessary for communication; Milestone kick-off and wrap-up meeting | Information flow | Timeline | PLP | EB5xy
626 | E&B | Installation | Awarding | Controlling procedure | Organization | Controlling doesn’t address their requirement clear and always changes their procedure.Controlling should track IPR value usage situation. | Procedure is not fully clear. | Complete BBAC PR/PO process training and clarification | Timeline | Timeline | Controlling | EB5xy
627 | E&B | Design |  | Media Supply & Fire-fighting | Organization | Due to regurlation, under steel plate platform, sprinkler should be considered for fire fighting issue. But line builder is not qualified and not common for them. |  | Fire-fighting device responsibility to be clarified with facility | Safety | Process Maturity | Facility | EB5xy
628 | E&B | Concept | Digital-Phase | Integra | Organization | Standards Integra is to restricted and focused mainly on Body shop, for Powertrain demand not really best fit technology’s available. To much driven by PLC function block. Examples: - Only 1 supplier for EC tools, no powertrain typical brand considered - No position monitoring for sequence tightening - No visualization or digital guidance for operator manual process result control or NOK case - Intech gluing, completely over dimensioned pump system, complex compared with standard Dreibond or Dobotech systems for simple gluing applications, for example no selves closing nozzle systems with crash preventing systems available | Top-down decision made for Integra 7 battery, without technical level preparation from MBAG standardization | Integra standard alignment with standardization team for project premise; Consider TE and TA for project resource; Blackbox alignment to be done as project premise; Deeper localization strategy for NTP | Cost | Process Maturity | TPL | EB5xy
629 | E&B | Installation |  | Budget | Organization | Cost situation is not fully transparent | Not planned | Define milestone for cost workshop in PP timeline; Transparency to be created in different level: Project overall cost, shop cost, plus-minus with supplier | Cost | Costs | PLU | EB5xy
630 | E&B | Installation | Awarding | O-chart and qualification | Organization | Cross-function involvement can be improved | Organization alignment was missing in project premise book | Proposal for project O-chart: WC O-chart alignment based on process technology; BC O-chart alignment follow ePK procedure; O-chart considers qualification plan WC & BC | Qualification | Process Maturity | TPL | EB5xy
631 | E&B | Design | Digital-Phase | Product knowledge preparation | Organization | Line builder Supplier Product and Process Knowledge at start the design meeting very low | No chance for BBAC and line builder to approach to product in early phase | Early input from NVTV, product knowledge to be catch by NVTV from Germany | Reduce CR | Costs | NVTV | EB5xy
632 | E&B | Awarding | Awarding | Supplier selection | Organization | When selecting suppliers, there are multiple indicators. How to rank the importance of these indicators and provide technical ratings for suppliers based on each indicator requires a unified method. |  | Using the method of judgment matrix, compare the importance of different indicators in pairs, and ultimately determine the proportion of each indicator. The process of comparing importance is decided by a show of hands among team members. | cost saving | Process Maturity | PP | EB5
633 | E&B | Design | Awarding | LOP list unify | Organization | Different functions use different LOPs, and there are differences in updating LOPs between Planner and suppliers. The transparency level is not high enough, and the solved problems cannot be traced well. |  | Use an online document platform to update LOPs in real-time, ensuring a unified LOP list. | Efficiency | Process Maturity | PP | EB5
634 | E&B | Installation | Commissioning | MET | Part | MET part is not qualified, with dimension and function | In BC1 and BC2 sampling phase, part supplier only provide prototype part, with low quality | QM/MP collect quality checking report from part supplier, use them for commissioning For HV testing battery sample, also ask for qualification testing report | Saving part quantity from commissioning; support to find out root cause of process issue | Process Maturity | PLP | EB5xy
635 | E&B | Design | Digital-Phase | MET | Part | MET can be only ordered by set (whole battery) but not by part. Many parts are not necessray for commissioning and expensive. | EX33 process | WPL/E3/E2 alignment necessary: MET should be abled to order by part. The EX33 process should be flexible. | cost saving | Cost | WPL | EB5xy
636 | E&B | Commissioning | Awarding | MET | Part | PP cannot receive import and local parts in time. EX33 and logisitc cannot fulfill PP MRD requirement. | Lack of know-how, communication issue between EX33, logitic. | Proposal;: - Each project, based on BOM, EX33 delivery lead time need to be confirmed; - PR-PO timeline set up accordingly; - Nominated overall MET responsible person for MET process - Complete MET demands in SAFIA system 8 months before MRD | Timeline | Timeline | PMO | EB5xy
637 | E&B | Installation | Installation | MET | Part | MET planning needs to be updated during project phase | Premise change, timeline change | 1. Establish MET PR-PO-MRD timeline 2. Miilestone review before each MET batch PR | Cost | Costs | PLU | EB5xy
638 | E&B | Commissioning | Installation | MET | Part | MET doesn’t highly utilized, some part lost and waste |  | Battery by battery ramp-up plan alignment | Cost | Costs | Launch | EB5xy
639 | E&B | Installation | Commissioning | Customer demands | Part | PP don't know the reuqiremnt and the test behind for OT battery | Info sharing is not transparancy | RD provide demand list with requirements part by part, then battery could be produced concentrate on requested process | Timeline | Costs | RD | EB5xy
640 | E&B | Design | Design | Cycle time saving | Process | Pick and place tooling (like label tooling, inserting tooling etc.) takes long cycle time and cause MV. |  | Integrate tooling onto a hard connected device to maintain its position at all times or simply pull down to achieve positioning. | Efficiency | Process Maturity | PP | EB5xy
641 | E&B | Design | SOP | Flow production validation | Process | Flow production battery as 1st time implement, Pro and Con need to be evaluated with series production condition | New technology trial | Evaluation workshop to be organized after go for 90, with production/ series planning | Efficiency | Process Maturity | Manual Planner | EB5xy
642 | E&B | Installation | Awarding | Timeline shorten | Timeline | SA took long time period within project phase | Current milestone: - Shipping acceptance, release shipping - Payment milestone, production line power-on at BBAC | For shorten master timeline: - Chance to evluate necessity of shipping acceptance - Decision as premsie for each NTP project | Timeline | Timeline | TPL | EB5xy
643 | E&B | PT-Phase | CC | OEE | Process | OEE loss is being calculated includes product quality and assembly quality issue | OEE Equipment Capacity. Battery follow the logic for all equipment + complete line output = OEE85 This is waist for example for equipment like testing EOL or Helium leakage test. Here we should target OEE97 and accept losses due to FTC losses caused by wrong assembly | Accept ramp up losses due to low product quality matureness and production FTC. This should be strong driven by KPI control and not compensate by Equipment capacity. Only new process developed Equipment or a strong PMI related process should be below OEE90
644 | E&B | Installation | Digital-Phase | Planning Team organization | Organization | Team organization set up within PP: - Define group according to function Auto/Manual/Testing/A&C |  | Team organization set up within PP: - Define group according to function Auto/Manual/Testing/A&C | Collobration | Process Maturity | TPL | EB5xy
645 | E&B | Design |  | DS tightening with high requirements of process control | Product | Too much DS requirements in the product drawing, it cost high investment for process controlling | RD input, root cause not clear; Compare with vehicle and engine, too much DS tightening is requested for product. | Feedback to RD, but no solution | cost saving | Costs | Product interface | EB5xy
646 | E&B | Awarding | Digital-Phase | Strategic supplier | Organization | EB5 Grob as strategic partner in Germany projec blocked information sharing towards to BBAC by intensively contract. E.g. heat gluing technology. Also no capacity for China project. | Strategy in Germany didn’t consider China volume | Proposal for future project: - Strategic partner in Germany should not be owener of design and concep - Define in Germany contract, MBAG is owner of all design data | Technical input available | Costs | TPL | EB5xy
647 | E&B | Commissioning | Digital-Phase | Integra pump doesn’t fit powertrain glue barrel | Equipment | Intec gluing pump in Integra, doesn’t work on powertrain glue plastic barrel. Equipment blow glue out of barrel. | Directly took over Integra device doesn’t fit to powertrain usage | Short term solution: Change equipment, apply blackbox principle Long term solution: Alignment during specificationi phase, align Integra hardware list with standardization team | cost saving | Process Maturity | Standardization Team | EB5xy
648 | E&B | Installation | Design | Facility layout interference | Equipment | Production line has phycisal interference with existing facility, for example the emergency button box on the top of pillar, interference with steel structure of production line | Layout of facility didn’t including detail hardware which installed later after building handover; production line supplier didn’t check in time the layout and on-site situation for installation | Plant building layout update before input to turnkey supplier, on-site check is mandatory for validation; Interference check, especially for layout drawing and on-site facility check after design release. Raise up change request to facility earlier when it's necessary | Timeline | Timeline | Facility layout Production Planning | EB5xy
649 | E&B | Installation | Design | Construction area protection by fence and curtain | Equipment | Produciton line installation will normally generate dust/noise to influence running project | Brownfield project should consider construction under same roof with series produciton project | Make fence for construction area, including fence on the ground and curtain from roof, could achieve following benefits: - Cleanliness for series production area under same roof - Noise control, special earplug provide by turnkey supplier - Clear safety area responsibility - Better external supplier control - Reuse fence and curtain from previous project, save cost | Safety, cost | Costs | Production Planning | EB5xy
650 | E&B | Installation | Installation | Space preparation for installation | Equipment | With brownfield project, battery plant didn’t have enough space for storage all equipment and prepare for installation. Neither for MET parts. | Brownfield project | Pre-plan the equipment shipping and installation plan, for equipment and MET part prepared short storage space for rushing time during line transportation - EB5 borrow the space from logistics in-bound and out-bound warehouse temporary | Cost | Costs | Production Planning | EB5xy
651 | E&B | Commissioning | Design | Consumable matieral | Product | During EB5 commisionning phase, PP found out fixation glue has short valid duration and long lead time. | · Consumable ordering and tracking process to be optimized, compared to EB4 (keep timelines of project with deliveries, track expiration dates of glue etc., reordering process which is transparent and reliable before SOP) | Workshop with Log. Improve the parts localization and shorter lead time. | Cost & Timeline | Costs | All | EB5XY
652 | [5 empty] | EB4 |  | · Deep dive check of battery data storage and transfer to vehicle and QM archive systems to avoid later complaints after Code18 batteries are shipped out
653 | E&B | PT-Phase | Concept | PP / Logistics Alignment | Equipment | AGV systems of Logistics and PP cross each other's way in the factory causing collision and interfere on a WiFi control level causing shutdowns | No clear alignment of design and technical setup of AGV systems form PP and logistics (independent setup) and no sufficient testing before PT phase etc. on a component level | Overlay logistics and assembly AGV routes and transport systems, including WiFi control system architecture (EB4 had physical and IT system interference) | Reduce shutdowns and extra effort to reroute AGV paths and less control system issues | Process Maturity | PP / Logistics | EB5xy
654 | E&B | PT-Phase | Design | PP / Logistics Alignment | Process | Load carriers from part suppliers have issues working smoothly in the assembly stations after loading (tolerances of SLT and machines different) | No clear alignment of design and tolerances of load carriers in comparison with PP machine requirements | Optimized check of logistics inbound load carriers from supplier (e.g. GOT) to ensure they run smoothly in the Kuka machines (same tolerances, same requirements etc.) | Reduce machine shutdowns and extra cost to optimize station and load carrier | Process Maturity | PP / Logistics | EB5xy
655 | E&B | PT-Phase | Commissioning | RD SOMA | Organization | SOMA organisation very short notice, documentation / material / manpower needed, which caused high extra effort in EB4 | (Check for optimized organisation and clear responsibilities for individual prep. Tasks) | Optimized SOMA organization (for early enough blue collar planning, special material procurement and limited audit influences) | Reduce preparation effort of PT / series production and extra manpower needed | Costs | Launch | EB5xy
656 | E&B | PT-Phase | Commissioning | Onsite support | Organization | Insufficient onsite support from CoC, especially during PT milestones. Only 1 CoC Support remotely. |  | More support for critical applications needed to ensure quick reaction in case of problems. |  | Process Maturity | IT | EB5xy
657 | E&B | Concept | Commissioning | EB4xy CATL Communication with EDI supplier | Organization | Support needed from BBAC and Daimler side. Investigation needed to be done before collaboration with supplier. |  | Collaboration mode and R&R need to be established from BU side. E.g.EDI. If any change, MP and Purchasing should inform supplier.Ultilize project meeting and L3 to align with cross function. |  |  | PP/IT
658 | E&B | Concept | Design | Process planning need to be improved | Production | Rework after final Ok, hard to get the whole picture from PP side. Process's not mature enough both from IT and planning side. | EB4 NOK process, | Transparency needed from BU side when any changes occure related to IT. Align NOK process and RW concept with Production. Any change related with IT, inform IT earlier. Organize RW WS to transfer doc. And info. |  |  | PP/IT
659 | E&B | All | Commissioning | Data validation | Production | Data validation is not essential by the BU. (PQD/VID) |  | IT proactively perform the data validation in all IT system and avoid any audit IT findings during PT phase. Conduct the data validation from QM and BU also needed. ET do audit to check data validation. |  |  | PP/QM/IT
660 | E&B | Design | Design | cooperation mode | Organization | Process planing solution and support mode need more involved with production and quality depart. in initial phase. (Rework process/normal/NOK process) |  | Transparency needed from BU side when any changes occure related to Quality and Production. |  |  | PP/QM/IT/Prod.
661 | E&B | Design | Design | Diff. standard SPPA&Integra | Process | Battery final deliver status picture archiving camera cause CR. (FA11) | It is required in SPPA system but not in Integra system. In this case battery production is more fit with SPPA standard bcs battery is still in the middle of delivery chain but final product. | Consider about production environment and adjust. | Reduce CR | Process Maturity | PP | EB5xy
662 | E&B | Design | Design | Gluing tech. design | Process | For heat glue, dispensing on GUT and load module inside maybe more stable and easier to control | Different technology scheme selection. EB3, EB4 and compititor dispense on GUT. | Consider the benefit and defect of different gluing process and deeply compare.EB5 won't change immediately. | Efficiency | Process Maturity | Production Planning | EB5xy
663 | E&B | Design | Design | Key technology le&le | Process | Through current line running accumulated experiences for key tech control. New variant planning phase should fully consider the points. | E.g. Torque. | Full preparation during design phase for key tech of le&le for the running process. Lessons learned based on Tech. should be organized in Design phase. | Efficiency | Process Maturity | Production Planning | EB5xy
664 | E&B | Design | Design | Efficiency control for manual station stop go mode | Process | For manual station stop go mode, there'll be efficiency losses compare with the flow mode. | - | Better to consider how to give hint to operators to let them know where they're in the CT. | Efficiency | Process Maturity | Production Planning | EB5xy
665 | E&B | Design | Concept |  | Product | Critical Parts speciality not considered. Such as CB acclimatization, leaving a potential risk | high requirement of RD design | RD design reconciliation ? Assembly countermeasure ? risk analysis of holistic process ? Backup plan ? | cost | Costs
666 | E&B | Concept | Design |  | Timeline | line side material presentation and material handling didn't follow New Lean Concept, in-line delivery at GU11(pre assy.) is still a pain point to LOG | production' focused planning concept, less consideration on 'massive material flow' | "line back" principle and SC target image must be considered to allow enough space for material line-side storage | cost | Costs
667 | E&B | Design | Installation |  | Organization | no precise plan for NVTV and NVTV WH due to the blur of R&R | R&R missing | a joint NVTV+NVTV WH can be considered in EP2 &BP (EP2 transformation?) | efficiency | Timeline
668 | E&B | Concept | Design |  | Process | Lack Facility planning's inputs on the feasibility study on plant modification /extension | no expert available, no R&R defination | Facility must consider enough resources and capacity in the early planning phase, so that we can get clear answers on the feasibility and details | Timeline | Timeline
669 | E&B | LOT1 | LOT1 |  | Process | No NVTV load carrier for OT bat | no R&R for NVTV LT | one-way package (disposable) added to the funding list. High risk to count on 'series LT' due to long/complex developping process. Solution: in next generation, consider package budget at the beginning. Custmer buy package. | efficiency | Timeline | PMO
670 | E&B | Installation | Installation |  | Timeline | No storage space planned for line builder's equipment/robot | consideration missed | add to the general reqirement in SPEC before RFQ next time… | safety | Timeline
671 | E&B | Design |  | Milestone Switchover | Timeline | Design phase not completed and project phase already moved to shipping phase and installation | Transparency of supplier in that design documentation submitted very late with little time to react. | Finalize Design phase and submit documentation on time as per milestone allignment , this will ensure a smooth trasnition between the different phases e.g Non Aligned parts used onsite , quality of 2D Drawings etc.. | Quality | Timeline | PP
672 | E&B | Installation |  | Shipping Acceptance Alignment |  | Shipping Acceptance requirements not clear to the line builder | Alignment meeting did not include main stakeholders where information could easily be transferred to line builder working team | Invite the correct stakeholders to the alignment meeting ensure the points agreed upon in this round is carried out to the right personell and that when SA takes place the line builder is well prepared and can deliver |  |  | PP
673 | E&B | Installation | Design | AO drawings list | Product | No drawing list to indicate totally how many AO drawings will be released from RD and dialog system | In the past, AO drawing only able to be downloaded from Dialog by proactively know it. There's no overview to show the total amount, during EB4 project, there was AO drawing release, but nobody informed by EC release. In the end, it caused tightening sequence need to be changed after PT | Implemented solution in EB5 project: - Regular meeting established between PP and BBAC RD, stablized communication for regular topics - RD established drwaing list within Dialog, shows AO drawing list and status/ version, available for EB5, but not up to date always - Regular screening the list, align with RD in each project phase for updating. | Reduce CR | Process Maturity | RD | EB5
674 | E&B | Design | Design | Drawing lanuage | Product | Lanuage in some drawings are German, hard to understand | RD input not clear. | drawings should all in english description. | Technical input available | Process Maturity | RD
675 | E&B | Commissioning | Commissioning | torque parameters setting | Process | Dialog defined some tighten steps requirements (e.g. target torque value + degree), but on-site EC controller didn’t configuration/ programming accordingly | when supplier setting the parameters in controller they didn't consider the tighten steps requirments from Dialog | Planned approach in EB5: - Torque workshop will be organized by Production torque engineer, prepared with lessons learned from EB4 line; - Defined process to transfer Dialog -> Joint list -> EC controller, turnkey supplier & EC supplier need to program according to joint list; - Production torque engineer checking during handover process General lessons learned: - Special requirement from Dialog, general noms/VA provide by QM as project premise | Quality | Process Maturity | PP | EB5
676 | E&B | Commissioning | Commissioning | Position system for logistic trolley | Equipment | Position system for logistic trolley does not consider the requirement for the test equipment, which cause the test result shift for same battery at different test round. | Position system for logistic trolley does not fulfill the requirement for the test equipment, | In process line design phase should consider the Position system for all test in line | Save the commissioning time and cost for Nok in series | Process Maturity | PP
677 | E&B | Commissioning | Commissioning | Drawing requirements | Product | For Heat psate requirements, RD have change the requirement from very strict(process not possible fulfill) at the begining to cancel at the end. | RD have not fully consider the necessarity for some requirement and also not fully consider the Manufacturability for PP. | In product design phase, the Design for Manufacturability and Assembly should be considered | Save the commissioning time and cost | Product Maturity | RD
678 | E&B | PT-Phase | PT-Phase | Drawing requirements | Product | Many thermol propagation changes in PT phase from RD which should be solved in product design phase(design verification). | RD have not fully consider TP fulfillment in design verification. | In product design phase, the TP design verification should be fully considered | Save the timeline and cost | Process Maturity | RD
679 | E&B | Installation | Installation |  | Product | EOL charging & discharge function not implemented | Not implemented or considered in planning phase comparable to our competitors | Should be considered to reduce the long duration time in analysis testing and also be able to detect failures prio the Q-loop 3 test phase. Premise and concept phase , require QM input VA to Project. | Effective results and time reduction | Product Maturity | PP
680 | E&B | Design | Design | SLT feeding concept | Process | EB3, EB4 and EB5 project all had long conveyor designed for SLT feeding, occupied big space and high investment | Long SLT feeding conveyor designed according to MB lean concept requirements, certain reaction time requested to be secured for logistics feeding. | Review desgin input in new project; Refer to MB bodyshop 0.x bins concept, saving conveyor and space | Cost | Process Maturity | PP/LOG | EB5
681 | E&B | Acceptance | Shipping acceptance | Shipping Acceptance Alignment | Organization | Shipping acceptance on-site team didn’t organized well to have same time for meeting and same way for LOP list documentation | Due to cross-function join the shipping acceptance on-site in differnet time, the team can't be prepared together, to make sure everybody knows the agenda and schedule; Turnkey supplier is not focusing on open topics documentation, the issue list didn’t summarize properly. | Well organize shipping acceptance (or any acceptance event) with clear agenda and guideline, prepare documentation and checklist as package, align agenda and nominate clear overall responsible person for entire activity. | Timeline | Timeline | PP | EB5
682 |  | Shipping acceptance | Awarding | Shipping Acceptance Alignment | Timeline | During shipping acceptance, project team check with supplier with high requirements and highly sensitive for shipping decision making. Too much open topic from turnkey supplier, but hard decision for holding shipping that it will leads to project delay | Payment miliestone and pre-condition is not clear and transparent within project team. Actually, shipping acceptance has no related to payment milestone. The shipping payment will happen after production line recovered at BBAC and all shipping acceptance open topic closed | Transparent payment milestone and pre-condition in production planning E4 timeline, ensure all cross-function has same understanding, support decision making process. Check if setting up premise book at beginning. | Timeline | Timeline | PP | EB5
683 | E&B | Design | Design | PLC function development | Equipment | Sensorpart type selection not choose from the robot technology documentation |  | Supplier robot planner should check the documentation before choose the camera type.ECM b3.40. robot documentation. KOP-Bidding phase, supplier should define which function not included in integra. |  | Costs
684 | E&B | Design | Design | Robot technical clarification | Organization | Supplier robot programmer is not invove in the design phase, lead to calirication is too diffictult |  | supplier should arrange special guys involve design phase.Add requirement and more clear in spec book.Organize tech. exchange meeting to explian during bidding and design phase.
685 | E&B | Design | Design | Design alignment | Equipment | the conveyor not accurate hole to messured by FARO to calculate the base 输送线上没有精定位的孔位用于FARO测量机器人base |  | with supplier desiner and simulation confirm the concept of base calibration make 4 plate and have the accurate hole to measured by Faro 与规划和仿真人员一起确定在4个金属板加工精确的孔用于FARO测量base.
686 | E&B | Design | Design | Technical clarificaiton | Equipment | Integra standard some technology dersspackage not involed in order list |  | clarify the oder scope with supplier during bidding phase clarify the dresspackage concept with TSS and supplier
687 | E&B | Design | Design | sensorpart | Equipment | GU11 010 station robot pick up the cover of the material box |  | use the sensorpart take the hole positon to change the base data, reduce the linestop error
688 | E&B | Design | Design | sensorpart | Equipment | Sensorpart type selection not choose from the robot technology documentation. The robot technology release type: 1.V20-RO-A3-R-M-M2-AL-P1-40-20 2.V20-OB-A3-R-W-M2-L-20 (Wide) 3.V20-OB-A3-R-M-M2-L-20 (Medium) 4.V20-OB-A3-R-N-M2-L-20 (Narrow) |  | Supplier robot planner should check the documentation before choose the camera type. The documentation path: ECM→Volume3→ folder 40 robot technology. During the desigh phase supplier should arrange robot expert involve the clarifiation
689 | E&B | Design | Design | Technical clarificaiton | Organization | Supplier robot programmer is not invove in the bidding and design phase, lead to calirication is too diffictult. RFQ requirement can't execute and cause the deviation for the requirment |  | supplier should arrange robot special guys involve bidding and design phase
690 | E&B | Design | Design | Faro | Equipment | the conveyor not accurate hole to messured by FARO to calculate the base, it will cause the offline program can't use directly after download to the robot controller |  | with supplier desiner and simulation confirm the concept of base calibration make 4 plate and have the accurate hole to measured by Faro this concept also can be used for the following project same situation
691 | E&B | Design | Design | dresspackage | Equipment | Integra standard some technology dersspackage not involed in order list Integra. So will the supplier to define the dresspackage function and cable type and have documentation to description very clearly |  | clarify the oder scope with supplier during bidding phase clarify the dresspackage concept with TSS and supplier define how many cabel and pipe will be used and more special information
692 | E&B | Design | Design | program naming standard | Simulation | some technology abbreviation/tool base naming/subprogram naming not decription in integra standard. it will cause the simation naming not correct and have to change during commssioning phase will lost a lot manpower to do this |  | define some naming rule with supplier and TSS accroding to EB projet real status. create the documentation to descripation tool, base, program naming very clearly.
693 | E&B | Design | Design | KOP concept | Process | KOP concept Supplier robot programmer is not invove in the bidding and design phase, lead to they can't identify the risk and prepare the right person think about the implementation of the concept |  | supplier should arrange robot special guys involve bidding and design phase otherwise some deviation items should take the cost change
694 | E&B | Commissioning | Commissioning | OT production build-up plan | Timeline | OTs production build up plan will block PP commissioning progress.NVTV production plan(4 batteries/4 days) cannot be changed. If PP need to switch commissioning to other varient, we need to wait until current varient production is done. Ots production duration is too long for PP and will shorten commissionning duration. | RD requires PP provide automatic process too early. NVTV working process cannot be changed. | Ots production phase should be consider during concept timeline build-up phase, PP should extend commisionning phase accordingly. | guarantee commissioning time. | Timeline | PP, Launch | EB5xy
695 | E&B | Commissioning | Commissioning | Supplier Management | Organization | Suppliers change frequently, engineers during commissioning phase are not the original ones. | Line builder hires 3rd party suppliers, this situation make them cannot garrantee stable organization. | After BBAC approval, original Line builder should come onsite for commissioning - key person should stay the same throughtout the build up and commisioning to ensure smooth progress and stabilty.PP PM should address this topic with linebuilder. | Line builder has long-term organization | Organizaiton | PP | EB4
696 | E&B | Commissioning | Commissioning | Line capacity | Process | Anlage does not reach the volume/ output during PT. | Stresstest in Production conditions (Time, Temperature, etc….) Output audit planned after SOP / after Go for 90 (series production conditions needed) | Prepone line capacity check. Check how much JPH the line could reach during in ET and optimize and accerlate line between ET and PT. | Reach 25% line capacity in PT1, 60% in PT2, 100% in GO FOR 90 in time. | Performance | PP | EB4
697 | E&B | Commissioning | Commissioning | Andon board | Equipment | Very late installation of Andon Board for PT2 and still connection issues before SOP | Late order and installation | Early planning and procurement of ANDON boards to ensure early installation and setup. AC installs Andon board and tracks timeline. | Andon board installed and used by production in time. | Equipment | AC | EB4
698 | E&B | Commissioning | Commissioning | Emergency measure of power off | Equipment | PLC & Robot recovery function when power off should be tested before final buyoff | Annual shut down. | Do the shut down test (AC). Set program in PLC, save the data when power off. Add in YBO,align with AC. | Avoid unclear risk of shut donw | Performance | AC | EB4
699 | E&B | Commissioning | Commissioning | Tightening NOK concept | Process | NOK tightening failure detection process which can avoid battery waiting | NOK tightening failure | Check NOK concept of EB5 for the most efficient way that follows Q requirements | avoid line stop | Performance | PP | EB4
700 | E&B | Commissioning | Commissioning | Sensorpart | Equipment | Q-gate will receive wrong NOK: Sensorpart camera is very unstable | Unstable sensorpart | Sensopart camera is very unstable that any small deviation could lead to wrong NOK. The method how camera judge The feature is quite limited. - Consider to make base for The workpiece first because small deviation of battery itself could lead to wrong result. - Use agile robot but not regular robot for a small camera. Which better way for implementing The Sensopart camera has been found in EB5 compared to EB4 to improve system stability | Improve Q gate accuracy | Performance | AC | EB4
701 | E&B | Commissioning | Commissioning | SLT loading | Equipment | SLT part loading to JEE machine - errors / mechanical issues / downtimes | SLT gripper issue | Confirmation from logistics and MP needed that supplier for SLTs can keep the agreen drawing requirements, else machine gripper design will not fit anymore to SLT PP will follow drawings of packaging supplier to design the grippers fitting to the measures and tolerances (possible risk as of timeline for EB5) | SLT loading parts on the line in right way in time. | Timeline | PP | EB4
702 | E&B | Design&Commissioning | Design&Commissioning | Project Management | Change request | Change request during the commissioing and design needs alignment in advance | lack alignment with AC | Request check list and automaiton control discuss to avaid timeline postpone To be checked for EB5 | Improve communication with stakeholders | Timeline | PP | EB4
703 | E&B | Commissioning | Commissioning | Project Management | Linebuilder manpower | Bring more OT in line much earlier, tryout OT and MET. Keep line running.Line builder capacity should be increased. | Line builder wasn't aware of OT build-up plan at beginning. | Add OT build-up possibility into original contract content, require line builder consider this task from the beginning. | Make OT production and commissioning implement in time. | Timeline | PP | EB5
704 | E&B | Commissioning | From installation until SOP | Spare part | Equipment | No spare parts during commissioing, e.g. spindle,adaper, Supplier should purchase earlier.Spare parts should be arrived when 1 station is arrival. | Some equipment's quality is poor. Line builder doesn’t plan spare parts before SOP. | Purchase easily damaged parts(e.g. spindle, nozzle and etc. )earlier, and require line builder to receive these kinds of consumable before commissioning phase. | Make sure OT production and commisioning go smoothly | Timeline | PP | EB5
705 | E&B | Commissioning | From commissioning until SOP | Project Management | Linebuilder organization | individual team for different anlage. Manager, PLC and etc. | linebuilder plans few managers to be onsite. | Require linebuilder to plan individual station lead for PP planner. | Ultilize linebuilder capcacity | Organization | PP | EB5
706 | E&B | Commissioning | From Design until GBO1 | LoP list | Tracking method | LOP , closing progress. Discuss with KUKA management level. | Digitalize LOP tools from excel to Coman, no regular tracking frequency anymore. | Track linebuilder provide LOP closing ratio weekly. | Close and double check open topics in proper speed. | Buyoff | PP | EB5
707 | E&B | Commissioning | Commissioning | OT production build-up | Stakeholders cooperation | Process about complete battery assembly before line is ready.PP require from NVTV.Launch should coordinate. | Series line produce OT before ET. | NVTV.Launch should coordinate and support OT production in series line before ET. | OT production | OT production | Launch
708 | E&B | Commissioning | Commissioning | Commissioning support | Stakeholders cooperation | PP planners needs cooperation with Production process engineers. | Production plans to take over from SOP, instead of get involved at beginning. | Production process engineers get involved in project earlier. | Performance | Process Maturity | Production
709 | E&B | Commissioning | Commissioning | Parts number changes | Parts | During commissioning found some parts provided wrongly | Deviation between supplier production status and BOM list. | Before commissioning, need to double check the part based on released DMC list | Stable Production | Timeline | Production
710 | E&B | Commissioning | Design | Supplier organization | Organization | In the beginning of commissioning, new PLC engineers not familiar with MBFS telegrams, it took more time on telegram communication and testing. | Supplier doesn't have stable organization | Before commission work start, commissioning related training needs to be arranged, pretest in virtual commissioining | Supplier Performance | timeline | AC
711 | E&B | Commissioning | Commissioning | Controls | Process | During ET1, found some AGV still linked with test battery, pipe cleaning-data/orders. | Need to pre-check before PT | pre-check before PT , make sure no AGV linked with any battery, and data/order clean, update BOM based on parts arrival status. | BOM-parts match | Process Maturity | IT
712 | E&B | Commissioning | Design | Robot program | Robot program | Prevent CB fall down function: CB gripper prevent the CB fall down function, only can open it by operator at the pickup and putdown position upside roughly 200mm | Cell block fall down from gripper risk when operator press release button on smartpard | shipping phase the CB fall down to floor, AC creat program in order to avoid CB falling down. Consider this function in Design phase. | Avoid CB fall down | Safety | AC
713 | E&B | Commissioning | Commissioning | Robot program | Robot program | Robot and Robot prevent collision function: Robot and robot collision function check and test carefully, and update the new version collision documentation by real program. the dry run mode and different robot running different speed is a very useful method to check the collission program bug.(avoid collision when same area robots run in different speed.) | Robot collision risk | other project somet times collision. Test in line based on some robot run speed pairs: 10% vs 100%. | Avoid robot collision | Safety | AC
714 | E&B | Commissioning | Commissioning | Robot program | Robot program | Counting function：the gripper have the CB, when the PLC sent the pickup CB command, how to deal with it? Compare the PLC and robot CB number to prevent robot collision. Before pick up, PLC get contact with sensor. | Robot collision risk | Prevent the plc send out wrong command lead to collission. Implement. | Avoid robot collision | Safety | AC
715 | E&B | Commissioning | Commissioning | PLC program | PLC program | The servo motor power cable must be grounded, otherwise it will cause signal interference to the sensor | signal interference to the sensor | servo motor power cable must be grounded | stable servo motor | Safety | AC
716 | E&B | Commissioning | Commissioning | PLC program | PLC program | The long-stroke cylinder needs to be controlled by a three-position 5-way valve and a pressure holding valve, otherwise it cannot be stopped immediately during the emergency stop | it cannot be stopped immediately during the emergency stop | used the right valve for long-stoke cylinder | stable cylinder | Safety | AC
717 | E&B | Commissioning | Commissioning | PLC program | PLC program | In the MBFS function block of the PLC program, the receiving block of the same type of telegram needs to be shared and there is only one, and the sending block cannot be shared | MBFS telegram does not work | as the issue description | stable MBFS | IT system | AC
718 | E&B | Commissioning | Commissioning | PLC program | PLC program | The function blocks related to MBFS messages in the PLC cannot be set as optimization blocks | MBFS telegram does not work | as the issue description | stable MBFS | IT system | AC
719 | Assembly PP | Digital-Phase | Design | Availability of testing parts for equipment commissioning | Timeline | Testing parts are required for equipment shipping release. As the equipment installation can just be performed during the shutdowns, parts are required at least two months before installation date (either CNY or GW). Parts are normally available 7 months after PDR. For V540 project, there is a conflict as commissioning parts are required before Lot1. | V540 timeline postponement as route cause for timeline conflict. Missing transparency as part requirement for equipment testing was neither considered in the product timeline nor in the L3 timeline for tracking. | Close tracking of parts availability for equipment shipping release in L3 timeline. Adding commissioning date for AS parts in L3 timeline with critical path to Lot1. Raise awareness of corresponding risk and preparation of back up solutions. | reduce the risk during shipping release, increase the majurity of the equipment reduce downtime during the ramp up phase | Process Maturity | WPL office | V540
720 | Assembly PP | Digital-Phase | Digital-Phase | Step by step handover to series planning | Process | Positive feedback: Step1 handover for V520 to series planning is done after IPV product. Teams access for BBAC colleagues pending. | Prevention of issue in PT2 | Step by step handover to series planning in corresponding project phase avoids unnecessary discussions to later point of time | Reduced effort as handover documents are collected in corresponding project phase. | Process Maturity | Assembly PP (Process) | V520
721 | Assembly PP | Digital-Phase | Awarding | Collaboration with P&S | Timeline | Awarding delays & awarding strategy changes. Regular L4 meeting between PP AS and P&S to discuss and align awarding strategies. There have been short notice decisions differing from previous alignments - examples: 1. Declined CR request of single source for ATC relocation B140 2. Delayed supplier set alignment | Late involvement of L2s | Earlier L2 & L3 involvement (monthly PP & PS L2 meeting) to discuss potential disagreements in early phase | Quick purchasing process | Timeline | Assembly PP | V540/V520
722 | Assembly PP | Digital-Phase | Concept | China specific product scope and situation in BBAC AS shops have low priority in early phase | Process | Examples: 1. Equipment, special tool concepts & process are copied from lead plant 2. PPG (produktionsgerechte Produktgestaltung) concept for V-specific topics like 6 seater carpet not considered, no lessons learned from V254 3. KLH includes inhouse assemby of sub components although there are space restrictions at BBAC, see front bumper radar outsourcing | No staff available at BBAC in early phase | How to add PP China voice in module group of RD? | Avoiding late changes for product, process, equipment, special tools | Process Maturity | TPL product? (Germany) | V540/V520
723 | Paint Shop PP | Digital-Phase | Concept | Universal design of process holes | Product | Some of the LLs are not been considered for implementation on MB.EA-M: unified size of the lock holes on the doors (avoid to develop another type of top coat jigs, cost saving) | No information sharing | 1. LLs sharing between the BTVs in the early phase of the new project 2. Implement the new design before DPT-E or even early | Standardization, less rework | Product Maturity | Paintshop PP | V540/V520
724 | Paint Shop PP | Digital-Phase | Concept | MO-Testat in early phase (from DPT-E) | Product | No process feasibility assesment in the early phase, need manual rework for the design of some parts | No in-depth coverage of PP/CN | 1. MO-Testat in early phase: DPT-E 2. Exchange the requirement according to CN process & equipment 3. Optimize the design according to actual application situation of CN PS plant. | Avoid addiotinal invest & rework time | Product Maturity | Paintshop PP | V540/V520
725 | Paint Shop PP | Digital-Phase | Concept | Earlier escalation of product issue (sidewall) involving relevant workpackages (Body Shop/ Paint Shop/ Assembly Shop) | Process | Known issues in design of sidewall causing late product changes. These changes have impact on scope of other work packages (body shop, paint shop, assembly). | Lessons learned of V214 not carried over in early design of V520. Too late (DPT-BV) escalation of issue in other workpackages. | 1. consequent carry over of lessons learned in early design phase of product (ppg mirror to RD) 2. earlier and active involvement of other work packages in problem solving approach. | Reduced hpv and invest due to possibilities of redesign in early phase. | Costs | Paintshop PP | V520
726 | Paint Shop PP | Digital-Phase | Installation | ED-Oven Extension in MRA2 PS | Equipment | Finish the work within a limit time with great success. Despite encountering some difficulties. | Perfect plan, flexible on-site problem solving, perfect collaboration | 1. 8h+8h+8h working hours instand of 12h+12h; 2. Pre-check oven&mitigation plan; Gradual renewal of old equipment through series investment 3. Identified risks occurred during construction period, critical review and "back up plan" etc. | Improve efficiency | Timeline | Paintshop PP | V540/V520
727 | Paint Shop PP | Digital-Phase | Installation | Broad bake E-coat material introduction | Process | Complete material replacement within the plan and without big quality defect | Good preparation | 1. Knowledge exchange and LL by common workshops with Rastatt, Kecskemet and Breman plant 2. Support of PPG China launch team visit in Europe by plant Rastatt and Kecskemet 3. On-site support for material introduction and ramp up by Rastatt specialist etc. | Improve efficiency | Timeline | Paintshop PP | V540/V520
728 | Pilot Plant | Digital-Phase | Design | Cubing cost effective attack | Equipment | Repeating spending of approx. 9.3 Mio. RMB for each new NPP project | For each new NPP project, BBAC need to pruchase a new set of Cubing to ensure product maturity | Cubing cost reduction can be achieved with modular swop. Recycling process afer EoP is according to the current BBAC running scrapping concept. For future carlines Cubing, whether exchangable modular should be checked in advance. | According to the current Cubing (asset) scrapping concept and currently running and planned carlines, BBAC can get back recycled valve around 1.064 m. RMB until 2034. | Costs | Pilot Plant | V520
729 | Pilot Plant | Digital-Phase | Concept | Timeline IPV & MO Testat (DPT/AV) | Timeline | Timeline mismatch between IPV & MO Testate DPT/AV | China MDS is longer then Lead MDS. Assembly sequence will be provided after / before IPV, not matching to MO Testat DPT-AV decision for upcoming carline, check content and timeline. | Mapping between MDS & IPV Timeline with consideration of difference between China MDS Lead MDS. | 1. Higher data maturity (assembly sequence) 2. Avoidance of timeline mismatches | Timeline | WPL office, Assembly PP | V540/V520
730 | Pilot Plant | Digital-Phase | Design | HV-connection after marriage for V540 6-seater | Product | Accessibility issue for HV wiring connector’s plug-in through repairing hole under seat | No cut out in carpet for HV wiring connection after carpet assembly (after marriage), carpet is one piece. | HV wiring connection Assembly concept for 6-/7 seaters need to be evaluated and secured within early digital Phase MO-Testat DPT-C/E | 1. Ensure accessibility for HC connection installation 2. Avoid task force solution finding process in late project phase close to B-Phase | Product Maturity | Assembly PP, Pilot Plant | V540
731 | Conveyor - Bodyshop | Digital-Phase | Design | Conveyor platform heigh Interferes with LOG/process | Organization | After conveyor platform design release, Robot kick out many collision points were found in layout meeting | Process design supplier did not fully check and use conveyor layout in Faplis. CR changing for the platform heigh and routing. | 1. Faplis update must be regularly and checked 2. Height requirements should be checked and aligned in early phase as well as documented in FLH 2. Optimize regular FAPLIS meeting with LOG/Process/ Conveyor to avoid interface issue happen | Enough time and budget to realize the required functions | Costs | PP Shops | V540/V520
732 | Conveyor | Digital-Phase | Design | ETS skid | Product | MO-Testat result shows ETS skid collision with under car body bolts | RD design screw in the conveyor pick-up area | 1. Engineer client 3D drawing update must be in time and checked 2. Discuss and align Back-office (P6)/RD/BBAC related topics to solve issue happen | Reduce impact on product design | Costs | Conveyor | V540/V520
733 | Conveyor - AGV | Digital-Phase | Commissioning | AGV running mode | Organization | B240 Trim line POR is clocked mode. But after commissioning and running line test production request continuous mode. That impact AGV overall distribution of AGVs quantity/speed/safety also need resetting | Process design not fully align with production. After shutdown modification has online re-setting AGV. Risk for line stop and safety. | 1. Introduction of Process design to production and align ahead of onsite modification 2. Conveyor do Virtual Commssioning in advance with process together | Reduce impact on production | Process Maturity | PP Shops | V540/V520
734 | Press Shop PP | Digital-Phase | Digital-Phase | Sidewall Surface Defect | Product | Sidewall surface defect below traingle-window in prototype die | Styling related surface defect | 1. Adress & implement styling related MO-Testat topics in early stage 2. Implement countermeasure from V520 to upcoming carlines with the same issues in early stage | 1. Avoid proudct issues & ensure Mercedes-Benz quality in early stage 2. Avoid costly & time intensive late stage product & process changes | Product Maturity | Press Shop PP (+ Bodytech) | V540/V520
735 | Press Shop PP | Digital-Phase | Digital-Phase | Parts Supply Programm | Process | Parts supply program several times increased press parts amount after supplier awarding | Late change requests of parts quantity from stakeholders | Freeze press parts quantity in parts supply programm before press dies have been awarded | 1. Avoid risks of lacking press parts for commissionning & vehicle demand 2. Avoid contract changes after awarding | Process Maturity | LOG. BS, Pilot Plant | V540/V520
736 | WPL Office | Digital-Phase | Concept | Shortened industrialization timeline from Blank Rel. to SOP | Timeline | Industrialization timeline needed to be shortened to ensure SOP in a late project phase | Late EXT Design change decision led to SOP postponement. Task to prepone the SOP as much as possible to PoR status | 1. Using 1st HL press parts for Lot3, without complete Q loop after shipping 2. 2 Q-Loops (Q loop 3 is cancelled and Q loop 4 is shorten) replaced by one long Q-Loop (Q loop 5 extend from 9 to 14.5weeks) to ensure the matching process between Lot4 and PT1. 3. Lean DbD plan to ensure RGA duration 4. BS line preparation shorten by getting more integration window time from production 5. Increase daily production volume output in PT2 to shorten PT2 volume accomplishment | 1. Shorten industialization timeline by around 15% 2. Ensure maturity level in PT1 V540: From DPR to SOP, -8 weeks From “_” rel. to SOP, -12.5 weeks V520: From DPR to SOP, -4 weeks From “_” rel. to SOP, -9 weeks | Timeline | WPL office | V540/V520
737 | WPL Office | Digital-Phase | Concept | Code18 to PTQ (Cycle II&III) | Process | If cannot reach code18, project should scrap PTQ vehicles and pay for that (QM Funding) | BBAC special regulation : 3 RGA rounds. Whether CycleII & III could reach code 18 during PTQ will be discussed project by project, depends on HW and SW maturity readiness time. | 1. Involve BBAC/RDPV Lifecycle Management in the dicussion of CycleII & III as early as possible 2. Plan PTQ vehicles budget from beginning of project | 1. Involve the right stakeholders in early phase for common planning status 2. Avoide to use contingency in late project phase | Costs | WPL office, QM | V540/V520
738 | WPL office | Digital-Phase | Concept | Outsourcing Pre-Assembly Frontbumper Radarset | Process | Inhouse pre-assembly of Frontbumper radar components (Tranceiver, Camera, Radar) leads to ergonomical issues as well as quality risks due to doublehandling of the frontbumper to pre-assemble the components on a seperate pre-assembly area. | Pre-assembly of Frontbumper Radarset was not awarded to Bumper supplier together with the general Frontbumper nomination, on the other hand PP Assembly Process Team planned with this pre-assembly scope as external and did not consider it as PoR. | 1. Define outsourcing Timeline + deadlines and include it into the MBEAM L3 Timeline Assembly 2. Reflect the process of outsourcing of critical scops in early concept phase and add more detailed pre-assemly outsourcing premises within platform/concept book (+ get in contact with CGL/MP to align outsourcing scope before nomination/awarding) | 1. Avoidance of ergonimics & quality risk 2. Safeguard delivery of pre-assembled parts for start B-Phase and also process validation already in Pilot Plant 3. Ensure planning transparency from very early phase between PP & RD/MP | Process Maturity | Assembly PP, Germany?, WPL office | V540/V520
739 | Facility | Digital-Phase | Installation | Input | Process | Final shop input (FP scope requirements) was unclear, inaccurate and not provided in time, resulting in changes even after FP construction started (such as electrical work), especially affecting shop Handover date (BS/AS). | Input from shops not provided on time | 1. During the early stages (process bidding phase) and modification period (after the process supplier is awarded), provide timely feedback and communicate up-to-date input (such as AIB) to FP to reduce unnecessary change requests (CRs). 2. Any design changes from the shops should be completed before FP construction begins, in order to avoid contruction rework and repeated power shutdowns. | Reduce additional construction time | Timeline | Process | V540/V520
740 | Facility | Digital-Phase | Installation | Facility-CR | Process | For newly added CRs the shop didn't consider the process flow of the FP-CR, which resulted in FP having to delay the construction handover date (process required). | CR from shops not provided on time | For expense-related CRs, the approval process generally takes 1-2 months (7 steps, depending on the amount). Input from shop should be as accurate as possible, and budget approval should be obtained as early as possible. | Reduce timeline mismatch | Timeline | PP Shops | V540/V520
741 | Facility | Digital-Phase | Installation | Construction communication | Organization | During construction phase, the responsible person from the series team (Production/Logistics/TSS/ Maintenance) was unclear which sometimes made it difficult for FP to push construction forward. For example, modifications in Paint Shop took half day for the pre-application of fire/height permission tickets. | Communication with the series team is not smooth | During planning phase, maybe more transparant to series team will improve later coordination in construction phase. | Improve smoothly construction | Process Maturity | PP Shops | V540/V520
742 | Body Shop PP | Digital-Phase | Installation | Activity conflict on site during GW integration | Organization | During GW and other longer integration window time, onsite there are some activity collisions among Body Shop and other stakeholders due to lack of information transparency in advance. | There is lack of overview from some stakeholders about their impact on other teams | 1. Body Shop should be the information hub regarding all the activities during certain window time in the workshop. Related stakeholders who have activities in parallel should keep transparency to Body Shop. 2. Use WPL PM meeting as a platform to address the lessons learned and implement the new process from next longer shutdown window time. | 1. Maximum creating a holistic picture reg. the activities and therefore avoid collision by leveraging pre-planning, communication, negotiation etc. | Process Maturity | 1. WPL & PMO office --> address new process 2. Body Shop --> collect all related information 3. Stakeholders --> ensure fluent info flow to Body Shop and support avoiding collision | V540
743 | Body Shop PP | Digital-Phase | Installation | Manpower support from some stakeholders are limited due to overtime control | Process | For an integration project most work onsite are implemented during shutdown time where there are limited people from supporting department onsite. Having supporting department join the integration requests them to have additional manpower planning. Facing the resource and cost control initiatives, PP sometimes could not get the support on time. | Different teams are driven by different targets --> PP is driven by project delivery on time, with the right quality & on good cost base; other teams are driven by cost control on overtime etc. | 1. Pre-align the manpower request like now --> Body Shop 2. Escalate to L4 or L3 when there is risk providing the support, to finalize the balance between request and offer. | Maximum reduce the mismatch between manpower request from PP & manpower support provided by stakeholders | Timeline | 1. Body Shop: pre-plan and pre-discuss with stakeholders 2. WPL: offer separate discussion rounds when there is mismatch. | V540
744 | Body Shop PP | Digital-Phase | Installation | Arrange proper line handover process after modification | Production | Best practice of existing process: arrange line handover after big modification to ensure customer acceptance and restart series production smoothly | Long-existing best practice in Body Shop | 1. plan the handover session with production, introduce the modification content, bring them to check the modificaiton onsite and offer Q&A consultancy. 2. Prepare standby from Planner & Line Builders after the series production restarts. | 1. Minimum impact on series production after modification 2. provide technical info to customer team when they encounter issues related to modification. | Process Maturity | Body Shop--> Continue applying the process | V540
745 | Body Shop PP | Digital-Phase | Awarding | Z1 Subs out of Series Equipment | Equipment | Best Practice alignment Z1 Subs out of Series Line defined (Roles & responsibilities) | During the Big Design Changes in 2025 after awarding.Bodyshop Product release dates was postponed and the Z1 Subassemblies (RF&EC) was less impacted. | If there any Timeline change directly after awarding then Project need to check if that possible bring some BiW Parts out of Series or even Whole BIW out of Series (Evaluation based of 6 Factors GO4 BIW out of series Equipment) Generaly Bodyshop will award Z1-Z4 late as possible in all Greenfield Projects.. In best case start Design Phase with DPT-AV (W Release). | Build of up Z1 Subs out of series Line and save Invest from Pilot Plant . Additionaly start Q Loops directly out of Series Line | Costs | Equipment Readiness for LOT1: PP Production resposible to build up the offical cars similar R&R with HOP. | V520
746 | Body Shop PP | Digital-Phase | Design | Optimaze Robot Release & Robot utilization process | Equipment | After the Reengenering Phase Bodyshop define the Robots amount based of the Process & Product dats (P-Release). Tramsparency to release the right Robotamount with maximum Robot utilization vs. Overall Invest by using existing tools was not deeply decipted. |  | Out of Deep Dive Investigations from Bodyshop Planners, we defined Utilization Range & KPI Targets for Robot Release Process.With that process we can ensure to release the right Robot amount by focussing first overall busness Case (Invest) and a balanced Robot Utilisation. | Create awarness to all Planners to save Potental PI Costs and incriese effiency | Costs | Body Shop PP | V540/V520
747 | Body Shop PP | Digital-Phase | Installation | Infrastructure readiness | Timeline | Bld.122 floor slab mismatch - section of oniste floor does not fulfill Bodyshop process equipment requipments | Insufficient verfication and assessment of reuse floor - technical drawings indicate the floor fulfills requirements, but on-site status is otherwise. Fortunately, we were able to shift our layout to avoid the compromised area, if not impact to start of B-phase would be delayed. | Drawings & documentation of old buildings not up to date. A reliable system of recording building data needs to be used/established. If this is not possible/guaranteed, risks of uncertainty need to be mitigated by proper assessments done by a relaible contractor/engineering consultant. Additional costs may incur if a complete refurbishment of the floor becomes necessary. | Prevention of future cases as this which could jeopardize project timelines | Timeline | FP | V540
748 | Bodyshop | PT-Phase | All | Production Dimension/Joining Team Issues | Organization | Team/supplier/PP faces alignment issues with excess argumentation. Lack of part supply planning at the start. | Commissioning parts function is not clearly defined with all parties. Overlapping and unclear responsibilities. | 1. Define all commissioning parts functions clearly with all stakeholders. 2. Align part quantity order with all parties before planning. 3. Manage part usage with a transparent share in weekly meetings. |  | Costs | PP (Bodyshop) | MMA Bodyshop
749 | Bodyshop | PT-Phase | All | Engineering Changes (EC) Implementation Delay | Product | ECs are implemented late, even after SOP. Expectations to start earlier to avoid quality issues and rework | Lack of sufficient communication and agreement between PP, RD, and production. | 1. Enhance communication and discussions between PP, production, and RD. 2. Align timelines for ECs and finalize early with special planning for tight schedules. |  | Costs | RD/PP | MMA Bodyshop
750 | Bodyshop | PT-Phase | Digital-Phase | Spare Part Freezing Process | Process | PP invests excessive effort in freezing spare part lists with TSS, focusing on lists with low-budget options despite contract specifications. | TSS is not taking full responsibility for list preparation. | 1. Discuss shifting 3% spare part budget from PP to TSS. 2. Transfer responsibility for spare part list preparation to TSS. Transparency on what kind of spare parts are available in TSS should start in Bidding phase in order to contract the right amount of spare parts. |  | Costs | TSS | MMA Bodyshop
751 | Bodyshop | PT-Phase | All | TSS Spare Part Testing on Series | Equipment | TSS spare part testing is disorganized, impacting car body quality, especially for critical components during design. | Lack of clear supplier responsibility and delays in spare part delivery. | 1. Freeze the spare part list earlier in the design phase. 2. Push suppliers to deliver spare parts for Lot Phase testing. |  | Costs | TSS | MMA Bodyshop
752 | Paint Shop | B-Phase | B-Phase | Door lock punching issue affecting paint jig assembly | Product | high risk of misalignment of the parts which leads to a “cat eye” and problems with the jig installation in the paint shop process. | hole diameter combination between door inner panel and reinforcement part. In MFA2 car line the hole combination had more spread (inner hole for reinforcement is bigger). | Increase the hole diameter for the reinforcement part on all 4 doors of V174 from currently 6mm to at least 6.5mm. With this diameter combination the process tolerances can be compensated, the tolerance chain can be fulfilled and the assembly of jigs in paint shop will be stabilized. Furthermore, other MMA derivate must be checked for the same issue and ideally follow the change. | prevent issues, different punching tools or special jig design in the future. | Costs | RD | V174
753 | Paint Shop | B-Phase | B-Phase | New Color Availibility | Timeline | new color aquamint not available on site at planned commissioning date | Only one released paint supplier caused delay in purchasing process due to cost | Consider purchasing timeline and color release of min. 2 suppliers in cPlace Timeline. | Early identification of timeline risks due to improved transparency | Timeline | PP Paint | V174
754 | Paint Shop | B-Phase | Installation | Asset Transfer for re-used equipment | Equipment | No approval to dismantle old PVC robots & delay of PAD equipment installation | Asset transfer approval needed to dismantle old robots for reuse in MRA & SY Paint Shops. | Consider approval process in cPlace timeline | Early identification of timeline risks due to improved transparency | Timeline | PP Paint | V174
755 | Paint Shop | B-Phase | B-Phase | solution of filter residue runners caused by body structure | Product | ED runners are prone to splash the front door hem and B-pillar because of body structure | The position of weld point on the body parts is inappropriate, resulting ED runners splash | Consider optimize the parts and the weld position to solve filter residue runners caused by body structure | Prevent filter residue runners caused by body structure | Costs | PP Paint | V174
756 | Paint Shop | B-Phase | B-Phase | TC jig collision with rear door | Product /Jig Design | TC jigs has the interference with rear door lock hole, and during the paint process touch the door. | Kick up of rear doors and also the hole of the rear door lock on the sidewall exceed the lower limit. | Paintshop jigs thinner or smaller, and the hole of the lock from BIW go to the middle of the tolorence. | prevent issues, during the production process the tool can't be used. | Costs | PP Paint/RD/PP Body | V174
757 | Paint Shop | B-Phase | B-Phase | Spot repair IR lamp baking | Product | side wall near C-piller happen dent in under IR lamp baking with 140C/22min. | The dent in issue happned in Rastatt also. Root cause could be the side wall panel design and material scheet thickness. | when new model come in PS, need test this dent in issue with IR lamp baking first. | prevent issues, influence the prodution pocess in the future. | Process Maturity | PP Paint/RD/PP Press | V174
758 | Paint Shop | B-Phase | B-Phase | Wax Nozzles maturity | Timeline | nozzels on site test with deviation, and take long time for checking and optimization with German side. | Nozzle not test in Germany before shipping to China, due to timeline. | Consider lead Plant testing in development timeline, then RD and Nozzle designer support on site lead plant and BBAC. | Early identification of timeline risks due to improved transparency | Process Maturity | PP Paint/RD | V174
759 | LOG | CC | B-Phase | TEO Changes | Part | TEO changes too much and on short term cause rework of SC picking | late TEO changes | Defined milestones for TEO latest freeze date, station list freeze date and linefeeding list freeze date before each LOT Phase with PP and RD. | Avoid too much rework in PZ | Process Maturity | LOG Planning/PP AS/RD | V174
760 | LOG | CC | B-Phase | Battery delivery | Process | Series battery delivery process can not be tested during B-phase | Battery safty equipment not onsite, EB5 are not allowed to be stored in battery storage area. | Required safety equipments for new process need to be clarified and purchased onsite before CC. | Problems for new process can be identified earlier | Process Maturity | LOG Planning/PP AS/Production/ LOG Production | V174
761 | LOG | CC | B-Phase | Common part line feeding | Process | No common understanding btw. LOG and production during CC preparation about common parts line feeding for B-Phase | No clear process definition about common parts line feeding for B-Phase | Set up a standard process for common parts line feeding btw. LOG Planning and AS → LOG Pick common parts with separate package and speical lable. Handover to Assembly Team leader according to aligned delivery plan | Clear R&R for following B-phase | Process Maturity | LOG Planning/Production | V174
762 | Logistics | B-Phase | B-Phase | eATS delivery | Part | CC eATS dispatch critical and LOT1A&LOT1B&LOT2A miss match usage sequence. | - UT plant production miss the demand. - UT packaging center dispatch eATS without checking the SAFIR ID and order match rule. | MBGC/FSK&eATS PM + MB/eATS planner - Check overall demand and follow with UT production to ensure milestones. - Check the whole NTP Bphase eATS and Vehicle match rule for reference of UT plant before dispatch. - More transparency is needed to ensure timeline, otherwise high risk for upcoming projects, PT coordinator is necessary. | - Ensure the right eATS be delivery via right order for right batch. - Ensure the production readiness,avoid wrong assemble, avoid line stop; | Process Maturity | MBGC/FSK&eATS PM + MB/eATS planner
763 | LOG | CC | LOT4 | eATS delivery transparency and demand overall management need improvement | Process | CC build up endangered due to missing eATS from Untertürkheim, No transparency of internal processes in Untertürkheim cause instability throughout the whole supply chain. With BBAC/MBGC/SC WTO supported, use Homologation team stock for CC production. | CC eATS demands not transferred within plant Untertürkheim from RD system to production planning, cause no raw material ordered for production. | Powertrain especially eATS demand need to be overall checked and need to be followed with Untertürkheim production to ensure milestones. | Ensure eATS further delivery on time. | Process Maturity | UT plant
764 | Logistics | B-Phase | B-Phase | ARTEMIS delivery &CCC status | Part | - ARTEMIS delivery critical from LOT1A to PT1A - ARTEMIS missing CCC docu in B-phase. | - supplier have critical SW issues on parts and production line - ARTEMIS CCC not ready, need CCC Free application each time for customs clearance. | RDC & BTV &PLE - Follow critical parts status at supplier side to have more transparency and find supporting in advance. - Implement of AKKRIT for import parts in China necessary. - Follow all CCC related parts CCC status, consider China tryout timeline and logistics time. If parts need to be sent out while CCC not ready, should prepare CCC free application and inform Logistics in advance. | - Avoid line stop, - Avoid additional cost for FLASH, - Avoid customs punitive charging or rating downgrade | Process Maturity | RDC & BTV &PLE
765 | LOG | B-Phase | B-Phase | PR/PO Parts Punctuality & Transparency Improvement Needed | Process | During LOT4A: 55.6% PR parts arrival before MRD; 7.5% PR parts arrival within one week before ASSY start. - Disrupt parts picking and several transfer steps cause additional cost. - Decrease Gitterbox party effectiveness. - No C/M time to keep original linefeeding timeline when parts with quality issue. - Cause additional cost of parts handle, coordination, truck transportation and information synchronization. | - Late EC change and parts improvement timeline. - Late tooling modification. - Start to push open parts delivery after MRD. | Part modify plan need take logistics process leadtime into consideration and match with logistics timeline, ensure parts can be checked and delivered to lineside on time. | - Decrease linefeeding risk. - Saving additional cost of manpower&cross-transportation. - Improve Gitterbox Party efficiency. | Process Maturity | P&S + RD
766 | LOG | PT1 | PT1 | PT1A import parts release & SDR | Process | 37/97 Import parts not release and SDR missing until order release milestone, cause late order and delivery risk. | - Import parts PPAP release late. - SDR not prepare in advance. | BTV &PLE: Ensure import parts PPAP release before PT phase parts order release milestone | - Avoid line stop. - Avoid additional cost for FLASH. | Process Maturity | BTV &PLE
767 | RLM | B-Phase |  | Organization | Product Issue Solving Process: Complicated product issues(RD side) solving in CC/LOT3/LOT4, difficult to open a ZEUS In B phase tryout process, some complicated issue involve many areas, can’t find the clear IRA | No official standard | Need a clear official standard to define who is the correct IRA, in which case we can open a ZEUS, in which platform to track the issue, in which case to escalate it, in which escalation platform, how often to track every issue and etc. We do all those job during V174 B phase , but for some special topic we have different opinion, an official standard is necessary. | Clear responsibilities | Process Maturity | RDPV/RDPE/AS-Prod. | V174
768 | RLM | B-Phase |  | Organization | Process Issue Solving Process: Complicated issues (process/equipment/special tool/torque side) solving in CC/LOT3/LOT4, need a clear standard to guide how to solve it | No official standard | V174 PP side issue solving doing well, but we still need a clear official standard to define how to solve it. Like : by which platform, how often to track every issue, who is the right IRA, in which situation need to escalation, in which escalation platform and etc. | Clear responsibilities | Process Maturity | AS-Prod./AS-PP | V174
769 | RLM | B-Phase |  | Organization | V174 tryout lineside feeding process not clear Misunderstand between AS and LOG, about common parts delivery, manually handover the parts or using part requesting device to handover the parts | No official standard | Common part means same part number with series carline. From CC to Lot4 (before LOG series process switch), LOG pick the common part with separate package and special label. Handover to Assembly Team leader according to aligned delivery schedule. BBAC need a new official standard document about those process in different tryout phase LOG need consider this process and require a special budget in advance | discribed process | Process Maturity | LOG Planning/AS-Prod. | V174
770 | RLM | B-Phase |  | Organization | Changes without AWB: RDC NVH team initiates special build up requirement to verify code018 status in advance in NVH Golden Car in LOT4a, but not triggered AWB process before LOT4a start (alignment directly with BS-PP) Issue during assembly build-up (found ground harness welding screw under BIW is in the wrong position) | Knowledge gap | Feedback to RDC PLE, to communicate with RDC CGLs/NVH team for better handling this type of issue in the future (using the exciting AWB-Round) Production: Do not carry out deviating build ups without an AWB | Avoiding of issues during build-up | Costs | RDC PLE/ PP / Production | V174
771 | AK&PA | LOT1 | PT-Phase | SoMA to solve the headlamp sagging issue.(Same issue with Germany) | Product | Transition from lightband to headlamp was out of tolerance. | Front end module with import headlamp dimension was out of tolerance. Import headlamp NOK. Germany use the SoMa to cover the issue in their PT1&2 | Special headlamp adjustment method with high efficiency. | Reduce the offline rework cost; Reduce the campaign risk; | Process Maturity | AS/AK | CV174/178
772 | AK&PA | LOT3 | All | Solve the hood setting viariation between BS and AS | Process | Transition form hood to fender was out of tolerance. | Kick-up value in BS work-card is equal to final car standard. | Change the hood setting kick-up value from -0.9mm to -1.6mm. | Reduce the inline and offiline HOP adjustment cost | Process Maturity | BS/AK | V174/X244
773 | assembly shop | B-Phase | B-Phase | equipment design | Equipment | one box gripper doesn’t match with series package | in design phase the series package is not considered | Early alignment with Logistic for series package information, in design phase. by design release. Measure : add check point to in Design phase. | avoid equpoment error | Costs | Zhou Zhisa | V174
774 | assembly shop | B-Phase | B-Phase | R&R Q audit | Process | peel off test no R&R for handling and checking | no one take responsibility | QM and production need to assign somebody for the job in series phase. | right colleague need to take the job | Process Maturity | QM / Production | V174
775 | assembly shop | B-Phase | B-Phase | time line postponement | Timeline | late changes from project for the milestones, (lots plan, loading plan), urgent arrangement for supplier support, potential risk for additional cost or lack of sufficient support | so much uncertainty of the project. | Project must make sure the planning certainty. Production control always late information for shut down time. Positive: so far the supplier provide sufficient support without additional cost. | avoid additional cost for short notice arrangement | Costs | project / production control team | V174
776 | assembly shop | B-Phase | B-Phase | special tool | Equipment | some of the jigs was not verified good enough in Pilot plant, that issues are identified in assembly shop. | 1. late delivery of the tools, 2, process and production need to be batter prepare for the pilot plant evaluation | To delivery all the new tools before Lot 1 to pilot plant Process need to have better understand before the verification, and contribute knowledge of the usage of the jig Production need to join the verification and contribute knowledge from production experience. | avoid late delivery | Timeline | Li Nan/Li Chao/Jia junqiang | V174
777 | assembly shop | B-Phase | B-Phase | IPV time line | Process | Timeline planning of IPV Process and B-phase | Due to timeline restrictions, V174 IPV Process and LOT1 started in the same time. Process planners NTP and STP have to be onsite at both locations (BDA and MFA plant) and take topics in both directions. | Though synergy effect could be used, for future projects it should be avoided IPV parallel to B-phase, preferred even IPV finish before LOT1. | avoid activities conflict | Timeline | Li Muyi | V174
778 | assembly shop | B-Phase | B-Phase | BOM issue | Process | during B phace late discovery of missing parts and EC‘s to add them into ZB | Lack of transparency of outsourced BOM of ZB’s (e.g. Cockpit) resulted in late discovery of missing parts and EC‘s to add them into ZB. | A double check and BOM confirmation by BTV onsite during B-phase will contribute to timely discovery and solving of such issues. | save more time and easy to solve issues | Process Maturity | BTV | V174
779 | assembly shop | B-Phase | B-Phase | training | Process | B-phase cars were built up hastily. Many buildability issues were not solved properly and discovered later in CC/LOT3. Production could not get familiar enough with the product due to hasty build-ups, which caused downtimes during ramp-up. | Production could not get familiar enough with the product due to hasty build-ups | production need to focus more on the buildability focus and Production training | increase effience of problem solving | Process Maturity | Production | V174
780 | WPL | B-Phase | Digital-Phase | Camouflage | Organization | Camouflage Concept and Roles and Responsibiloties not clear | No clear R&R for Camouflage scope 1. Communication 2. Concept alignment 3. Parts |  | Clear R&R for following B-phase | Process Maturity |  | V174
781 | WPL | B-Phase | Digital-Phase | Hardware demands | Process | Hardware demands, late TA demands in PT1 and special customer demands in LOT3 and LOT4 (R&R and process unclear) | CEP responsibilities changed, late project involvement and no standard approach available | Early involvement of RLM (for production vehicles) and alignement of possibility for double usage. Create standard approach of hardware demand requirements | Clear R&R and no useless money spending | Costs |  | V174
782 | WPL | B-Phase | Digital-Phase | Dialog P Filling | Process | Delay in Logistics Timeline (BOM freeze, BVA defined, …) | Dialog P filling was too late, overall coordination of parts missing | Trigger Dialog P filling at an earlier stage in time | No delay in Logistics Timeline | Timeline |  | V174
783 | WPL | B-Phase | Digital-Phase | Integration Timeline | Timeline | Integration time for 2nd and 3rd new carline in Brownfield integration need to be considered in regard of: 1. Time between EOP of previous carline and LOT1 Start of the new carline (min. 3 Months) 2. Available Integration timeslots | No other plant yet did integration of three car models into existing running 3+1 Body shop (Brownfield) | Evaluation of Situation in MMA project was done, Standard for integration into running body shop was developed. See details attached. | Functional timeline with project start | Timeline |  | V174
784 | WPL | B-Phase | Digital-Phase | Code 18 | Product | Code 18 in LOT4 for plant processes. Code18 might be able to be reached already until Lot4 (MDSfuture) at BBAC. | BBAC strives for Code18 readiness for LOT4 but the overall vehicle Code18 requirements can´t be met at LOT4 due to Supplier (MP&RD- timelines) are not set up to reach PPAP releases earlier. Code18@Lot4 is not MDSfuture standard target, defined as BBAC specific target. MDSvision considered PROZ as Code18. | Pre- steering of Q- Masterlist requirements within the project to be started in preparation of CC. RD and MP to be involve into project premise Code18 requirements before BoD approval / awarding of parts LL for V178 and X248 will be implemented. and inform V5XX for potential implementation | Earlier Readiness ensures product and process maturity and is an enabler for Future timeline shortening | Process Maturity |  | V174
785 | WPL | B-Phase | B-Phase | Shutdown Activities | Timeline | consider central areas e.g. Log and IT, Inventur regarding their demands during a shutdown | 1. Clash between different shops regarding time demand and dependencies during Shutdown not fully clear 2. Inventory (Year end) not considered in Shutdownplan which caused a clash with Bodyshop PT1 | Early clarification of all Shutdown demands and dependencies in Project Meeting Implement Inventory into Program Planning Shutdown overview in order to make sure all stakeholders know the latest Shutdownplanning. | Functional timeline and clear overview of all demands | Timeline |  | V174
786 | WPL | B-Phase | B-Phase | Vehicle Routing | Process | Routing of vehicles in general for a project/ Special cases between pilot plant/ homeline (e.g. unusual builtup location, LOT2 in homeline) | Routing not defined between pilot plant and homeline | Early clarification of the different routings in B- Phase in alignment with production control Example: Lot2 BS in homeline - LOT2 PS in homeline - LOT2 AS in pilot plant | Clear routing ensures no time delay and no additional effort on short notice | Process Maturity |  | V174
787
788
789
Note on E1: • Subject: This column should contain a brief attention grabbing headline that describes the subject of the lesson learned.
Note on G1: Issue description: This column should be populated with a detailed description of the situation learned from.
Note on I1: This column should be populated with a description of the lesson learned from the situation described. Include recommendations regarding the outcome of the corrective action, to help guide future project managers/members.
Note on L1: Name the responsible person for this topic. TPL shop should be responsible if the topic can be solved in the current/scope of function

## Sheet2
Project Phase | Relevant Project Phase | Category | Benefits
Digital-Phase | Digital-Phase | Organization | Timeline
Concept | Concept | Product | Product Maturity
Design | Design | Process | Process Maturity
Awarding | Awarding | Timeline | Costs
Installation | Installation | Equipment
Commissioning | Commissioning | Audit
White Buy-Off | White Buy-Off | Production
B-Phase | B-Phase | Part
LOT1 | LOT1
LOT2 | LOT2
LOT3 | LOT3
LOT4 | LOT4
CC | CC
PT-Phase | PT-Phase
PT1 | PT1
PT2 | PT2
PT3 | PT3
SOP | SOP
All | All